Note: This terms of reference is designed for non presence situations and should be adapted where used in cases of an existing CARE presence.

CARE International

Assessment and start-up response to the humanitarian crisis in xxx

Terms of Reference

Purpose: 	Conduct a field assessment in xxx to assess the humanitarian situation and identify appropriate options for a CARE humanitarian response.  Provide clear recommendations to CARE decision-makers on an appropriate response based on the humanitarian imperative and needs, CARE’s strategic priorities, capacity and potential to add value in responding to this humanitarian crisis;

Objectives: 	a) to identify humanitarian needs and capacity of humanitarian actors on the ground and analyze the humanitarian service gaps, including scope and type of required interventions

b) to analyze the security environment, determine limits to operational considerations and appropriate security measures

c) to provide options and relevant recommendations for a strategic humanitarian response by CARE;

d) Develop initial program strategy (including viable exit strategies) and produce specific proposals for donors;

e) to develop an initial 30 day operating plan including program support requirements and describe options and recommendations, including identifying required immediate next steps to implement the operating plan;

f) as appropriate to start preparations for/begin with implementation of potential response operations.

### Area of Focus:	XXXXX

Duration:	Assessment 10 days, potential start-up response up to 6 weeks

## Background:

Insert background to disaster

Assessment Methodology:

The assessment team will use the methodologies as appropriate that include interalia PRA techniques and tools, review of key reference documents, semi-structural interviews, key informants, interviews of technical staff, general observations, and focus group discussions.

Activities related to objectives

a) to identify humanitarian needs and capacity of humanitarian actors on the ground and analyze the humanitarian service gaps, including scope and type of required interventions

- Undertake background reading and briefing to understand context and key actors

- Undertake community consultations and field based assessment of the humanitarian impact of the crisis

- Co-ordinate with INGOs and UN agencies such as OCHA, UNICEF, UNHCR to identify key sector areas and/or geographical niches for potential CARE humanitarian relief operations taking into consideration sector areas in which CARE has experience and capacity and to ensure there is no duplication.

- Assess UN agency, multilateral agency and private sector planning to determine the existing service coverage, gaps and scope for partnership

- Assess relevant National NGO emergency programs and plans and determine their capacity, willingness and scope to partner with CARE in humanitarian relief operations.

- Provide a rapid assessment of the capacity of Government Authorities and UN agencies to coordinate and respond to the crisis. Review potential role of Government Authorities in supporting or hindering potential relief operations, incl. the impact of widespread corruption.

b) to analyze the security environment, determine limits to operational considerations and appropriate security measures

- Thoroughly analyze the security situation for international and national NGO staff, identify risks and possible security measures and determine limitations to humanitarian response options.

- Ensure coordination and liaison with relevant actors including the UN, ICRC, local partners to ensure the most complete assessment

- Ensure programming recommendations of the assessment can be feasibly implemented within acceptable safety and security limits

c) to provide options and relevant recommendations for a strategic humanitarian response by CARE;

- Undertake quick mapping of responses and targets to date using UN Cluster information; local Coordination groups; meetings with INGOs etc

- Analysis of CARE Strategic Plans and analysis the country context

- Quick SWOT with partners and community participants/leaders (including assessment of local capacity, priority needs, CARE competence/experience, gaps in response and access/security for response

- Recommend appropriate response options and as agreed with CI ERD develop a strategy and program of initially 30 days for the chosen response option, framing this within longer-term response options which include viable exit strategies, to address prioritized humanitarian needs, capacity of CARE and other INGOs and the UN, along with an analysis of the policy and operational environment.

- This should include interalia: recommended programming option(s), program sectors; provide guidance on options (and associated risks) for CARE to enhance protection of affected populations, geographical focus; recommend appropriate M&E systems and required capacities and a clear management framework.

- Listed recommendations shared and discussed with Government and local partners

d) Develop initial program strategy (including viable exit strategies) and produce specific proposals for donors;

- Conduct planning meetings with beneficiaries and partner organisations

- Liaise with donors and CARE members, confirm the sectors that donors are interested in funding, the willingness of donors to fund CARE and the potential funding that is expected to be available.

- Based on assessment of humanitarian situation and recommendations for CARE’s strategic role (a and b) above, develop initial program strategy with program objectives, areas of intervention, modalities and exit strategy

- Prepare written concept papers and proposals, with appropriate budgets for submission

e) to develop an initial 30 day operating plan including program support requirements and describe options and recommendations, including identifying required immediate next steps to implement the operating plan.

- Visit the affected areas to gain an understanding of the current extent of the crisis and the operating environment. Consider any potential site selection, logistical and warehousing issues, transportation, telecommunications requirements, office needs, security measures and human and financial management issues.

- Assess resource requirements and constraints (human, financial, material, logistic) and costs (salaries, rent, transport, favourable exchange rates, etc) associated with starting humanitarian relief operations.

f) as appropriate to start preparations for/begin with implementation of potential response operations.

- Map staffing requirements, local and international and develop recommended staffing structure

- Develop a list of key contacts specific to proposed activities.

- Check legal authority to operate in country

- Team should collect copies of the Labour Law and any temporary legal provision for the emergency period

- Establish location of response base and all related logistics

- If appropriate and feasible, commence relief operations if agreed with CI ERD, following consultations with the Crisis Coordination Group.

Assessment Team:

1. Team Leader

- Overall coordination of assessment and team management

- Liaison/external coordination (focus Donors, UN, Gvt. & INGOs,  Military)

- Ensure regular and appropriate communication and consultation with CARE Jordan, MERMU, CI and CARE members

- Ensure all team members comply with safety and security protocols, on the advise of the security advisor

- Development of response program strategy

- Design of operations structure

- Capacity building focus on emergency/disaster management

- Preparation of assessment report

- Act as Assessment team spokesperson for media

2. Deputy TL, Program

- Together with TL coordinate field based community consultations

- Take the lead role in liaison with CARE local partners including discussions around partnership options and support for liaison with local authorities, with the support of the TL

- Assess health and wat/san/hyg needs and program options and contribute to program strategy development and recommendations which are incorporate gender, sphere, protection and other cross cutting perspectives

- Prepare concept papers and proposals

- Capacity building focus on Information Management/Proposal development

- Support of coordination, particularly with local authorities

- Act as Assessment team spokesperson for media

3. Security Officer

- Security focal point for assessment team

- Prior to deployment assess security risks and make recommendations regarding the timing and means of entry and movement of the assessment teams in Lebanon, using appropriate criteria

- Prepare safety and security orders for the assessment mission prior to deployment which set out movement, communications, crisis management and medical emergency, evacuation protocols, equipment requirements and other necessary instructions. Ensure the orders are approved by the Team Leader prior to deployment and that all team leaders receive both a hard copy and a verbal briefing on procedures and protocols to be followed.

- During the assessment continue analysis and adapt or add to protocols as required, through the Team leader issue additional instructions as required to ensure the safety of the team. Assist the team leader in ensuring all team members comply with safety and security requirements.

- Assist ongoing mission planning, including assessment and planning for field visits, assessment of security of accommodation locations and other requirements.

- In the event of a safety and security crisis or medical emergency, assist the Team Leader in the appropriate management of the crisis and conduct appropriate incident reporting.

- Conduct security analysis to inform programming options suggested by the  assessment team

- Ensure functional telecommunication and ICT of assessment team

- Assess telecoms/ICT options for potential CARE response and develop suggested telecoms/ICT architecture and equipment plan (incl. resourcing options). Recommend to the team leader whether a telecoms expert is required in the field.

4. Logistician / Program Logistics and Team support

- With TL support representation and liaison with Government authorities

- Assess need and options for food and distribution programming

- Focal point for Logistics (infrastructure and conditions) component of assessment

- Support design of operations structure

- Start-up logistics (office, housing, transport, etc.)

- Set-up of supply chain management (SCM) systems

- Capacity building focus on SCM systems

- Assessment team logistics (accommodation, transport, etc.)

- Support start-up logistics (office, housing, transport, etc.)

- Support set-up of supply chain management systems

- Ensure logistics systems proposed consider gender implications and are appropriately designed to ensure the participation and protection of women.

6. Media and Information

- Write assessment team updates and sitreps

- Participate in appropriate coordination meetings to gather relevant information for the team and sitreps and gather relevant information from other sources to support the team and reporting

- Ensure fluid information flow between the assessment team in particular, as well as CEG and CARE Members.

- Ensure sufficient information flow to relevant CI entities (CO, RMU, CEG, COMWG)

- Produce and send appropriate information for CI communications requirements including human interest stories, talking points and supporting data

- Take photos of an adequate quality for media purposes and distribute to CARE members (documentation of humanitarian situation and CARE activities/response)

- Establish contact with international media representatives to increase CARE’s coverage in the press and draw attention to humanitarian advocacy issues

- Facilitate media requirements of CARE members including setting up interviews for CARE members and with representatives in the field, ensuring use of appropriate spokespersons within the team

- Respond to information requests from CARE members for information from the field

- Ensure spokespersons within the team are well briefed on talking points and confident in talking to the media

- Develop media component of recommendations in the assessment report/program strategy

- Act as assessment team spokesperson for media

Reporting lines:

The assessment team members are reporting to the Assessment Team Leader.

The Team Leader is reporting to the CI ERD or the designated CEG focal point.

The Team Leader will also have a dotted reporting line to the CARE CO Country Director.

Principles of a CARE response:

The following principles will guide CARE’s response:

- Driven by humanitarian considerations: CARE should base all actions primarily on humanitarian considerations. Donor, media or national member interests should be seriously considered but not drive or seriously shape CARE’s response.

- Protecting the safety of staff and partners:. Assessment, plans and operations to respond to the current crisis should factor in safety and security considerations from the outset.

- High standards of program response: CARE’s program response should adhere to SPHERE standards, humanitarian principles, and be based on sound policy analysis. Benefits-harms analysis should be incorporated into programs to ensure that programs are well thought out and any unintended harms are minimized. CARE should engage appropriately in advocacy for the needs of the Indonesian people. CARE operation should be oriented on the CI Humanitarian benchmarks.

- Solid support foundation: CAREs program support foundation is a crucial requirement to function effectively, accountable and safe under the difficult circumstances.

- Collaboration: CARE should aim to work with others in all aspects of its response in: (a) With the local people, CARE should use participatory approaches, involve local stakeholders, and aim to strengthen capacity; (b) CARE should aim to collaborate, coordinate with and learn from other humanitarian agencies; and (c) internally, CARE Members and offices should work together and jointly contribute to a collective response.

Timing:

The assessment will commence as soon as possible.  The team is expected to remain the field for approximately 10 days and in case of start-up operations some staff will potentially stay until longer term personnel are deployed to take over operations.

Report:

The report should constitute clearly prioritized response options, with a 30 day operational plan for the recommended course of action and be submitted to the CI Emergency Response Director and to the CD within 9 days of deploying to the field.

The report should contain:

- Executive summary

- Overview of needs assessment and analysis of the current humanitarian situation, including operating environment and particularly security considerations;

- Information on government response, UN agencies, donors, INGOs and LNGOs; Military

- Proposed program, including goal, objectives and overall strategy;

- Details on Key activities;

- Details on program support requirements and other logistics and resource requirements;

- Staffing schedule, incl. suggested structure (i.e. organogram)

- Overview on explored funding options

- Budget outline; and

- Key contacts

Primary Contacts in Region:

XXXX