Assessment planning checklists

Assessment preparation checklist

Plan

- Does the assessment team have a clear plan for carrying out the assessment?

Clear objectives

- Are the objectives of the assessment clear, included in its terms of reference and agreed by all team members and key stakeholders?

Team make-up

- Is there an assessment team leader?

- Does the team have the mix of technical and functional skills needed to achieve the objectives of the assessment?

- Does the team include women and men, and people with local language and cultural skills?

- Are other agencies and/or the affected community represented on the team?

Logistical support

- Has there been enough logistics and administrative planning for the team to do its job effectively and safely, e.g. transport, equipment, permits, route planning?

- Does the assessment team have reliable options for communicating (primary and secondary), e.g. phone, sat phone, radio?

- Has a preliminary safety and security analysis been completed to determine if it is safe to deploy the assessment team to the field?

Information needs

- Has the team identified the priority information needs to focus on in the assessment?

- What information do they need to meet the objectives of the assessment and conduct the analysis required?

- What information do they need to understand cross-cutting issues (e.g. gender, protection)?

Involvement of disaster-affected people

- How will the team involve disaster-affected women and men in the assessment?

- Have they told the affected community of their planned visit?

Information sources

- Who is the team going to talk to?

- What are the available sources of information?

Data collection methods

- What data collection methods will the team use?

- What skills or tools do they need to use these methods?

Guidelines and tools

- What guidelines and tools will the team use in the field to help them gather and analyse information?

Analysis frameworks

- How will the team analyse the data?

- What analysis of the context do they need to do to make useful recommendations?

- What information and tools can help with the analysis?

Recommendations

- What types of recommendations are expected of the team?

- Who are the recommendations for?

Reporting

- When will the team deliver its preliminary report and final report?

- What format will the report be in?

- Will there be a public version as well as an internal version?

Proposals and other outputs

- What other outputs (e.g. operational plans, budgets) will the team prepare?

- What proposals, plans and communications are expected of them?

Assessment basic information form

At a minimum, the assessment team should gather and analyze this basic information.

GENERAL HUMANITARIAN SITUATION

- Location and conditions of disaster area

- Impact of disaster—physical, social, economic, political, security, environmental

- Affected population—size, demographics (disaggregated by gender and age) and location

- Capacities and vulnerabilities of affected population

- Priority needs of women, men, boys and girls—food, food security and nutrition; water, sanitation and hygiene; shelter; health

- Information about context—gender roles and relations, cultural issues, conflict and power dynamics, violence, discrimination and protection issues, civil–military relations

RESPONSES TO DATE

- Affected community

- Authorities

- Local NGOs

- International NGOs

- UN agencies

- Donors

- Others—e.g. military forces

OPERATING CONDITIONS

- Security analysis

- Availability of support infrastructure—office, accommodation, telecommunications, transport

- Availability of (and damage to) logistics infrastructure—ports, roads, airports, warehousing

- Market conditions and availability of relief items locally

- Government regulations and requirements for relief operations

- Cost estimates for budget

- Availability of skilled staff