## Section-1-Program-Example
OPTIONAL - PROCUREMENT FORECAST FORM
Section - 1 : Program Unit
| Agriculture Development Project, Undawata |  |  |  |  | PN--> | CAI001 |  |  |  |  | FY -->> | CY-2010
| Name of Program / Project / Unit | [10 empty] | Updated On -->> | 2009-07-15
PROGRAM UNIT INFORMATION | [5 empty] | GEO Code | Fund Code | ESTIMATED QUANTITY REQUIRED |  |  |  |  | Do you have a Preferred Vendor? If so, please indicate name/location.
Item # | Item Description | Specs/ Model # | Quantity | Estimated Unit Cost - US $ | Total Estimated Cost - US $ |  |  | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 13
1 | Toyota Landcruiser | 13-seater LWB | 1 | 28000 | 28000 | 000 |  |  | 1 |  |  |  | Toyota, Gibraltar
2 | KSB Submersible Pumps | 380V/6" dia w/pipes-50' | 12 | 1250 | 15000 | 000 |  |  | 12 |  |  |  | NO
3 | Tractors - w/front loader | See details specs attached | 4 | 35000 | 140000 | 000 |  |  | 4 |  |  |  | CARE USA
4 | Tractors - w/o front loader | See details specs attached | 3 | 30000 | 90000 | 000 |  |  | 3 |  |  |  | CARE USA
5 | HP Printers - w/printer cable | Model Laserjet 2200D | 5 | 500 | 2500 | 000 |  | 2 | 2 | 1 |  |  | CARE USA
6 | Dell Desktop Computers | Model Inspiron D800 | 15 | 1200 | 18000 | 000 |  | 6 | 6 | 2 | 1 |  | CARE USA
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
|  |  | 40 |  | 293500 |  |  | 8 | 28 | 3 | 1
0
Note: | Please check on tab entitled "Sect-1-Guidelines-Program" for more information on this format.
| Prepared by |  | Reviewed by |  |  |  |  | Approved by / Proj. Manager
| Name: |  | Name: |  |  |  |  | Name:
| Title: |  | Title: |  |  |  |  | Title:
| Date: |  | Date: |  |  |  |  | Date:
Note on H6: This is per Donor requirements. Obtain waivers if necessary and in advance prior to commencing /finalization of the purchase of the item. Alert CARE USA Procurement Unit if procurement is restricted to the US.
Note on O6: Please provide the estimated quantity reqired by quarter.
Note on Q6: Preferred Vendor should be on the approved vendor list. If not, provide relevant information and justification to finance to include in SCALA
E X A M P L E

## Sect-1-Guidelines-Program
SECTION - 1: PROGRAM UNIT ACTIONS
GENERAL INSTRUCTIONS AND GUIDELINES
Columns | Instructions & Guidelines - Procurement Forecasting is optional and not required. If Program chooses to prepare a forecast, please follow the steps below if utilizing this form.
General | Prepare and submit this form to the Procurement Unit for each individual program, project or unit for critical items only .
The forecast of items/quantities needed is based on what is in the proposal and approved by the donor for critical items.
If this form is utilized it is recommended to revise the forecast if a particular program's activities change based on the situation, or if adjustments are dictated by donor requirements or funding.
This form has two sections:
Section 1 - deals mainly with a particular Program
Section 2 - is an update prepared by the Procurement Unit
Whenever a revised forecast is submitted to procurement, please do not forget to change the date as well - see the top right hand corner of the form.
Based on this template, the Procurement Unit can begin to review the local market and source the purchases specificed. NOTE that direct procurement activity can only begin when an authorized Purchase Request is submitted to the Procurement Unit.
Donors | It is presumed that each program or unit is aware of specific donor requirements and/or waivers if applicable. However, if further clarification is needed, log on to http://compliance.care.org. The username is: wsscare\care and the password is: abc!123. To access the site, please be sure to input the username and password correctly. For example, the above username is a back-slash (“\”) and not a forward-slash (“/”). If you have difficulty with the website, please send an e-mail request to Eric Johnson, Associate Legal Counsel & Compliance Officer - e-mail: ejohnson@care.org.
If there are special donor restrictions on procuring any of the items, alert the Procurement Unit immediately as some restrictions may increase lead time for delivery. Note that the Program or Project is responsible for obtaining any waivers directly from the donor.
USAID: Some of the major restrictions of this donor are: source and origin of the commodity, vetting vendors to be in compliance with OFAC requirements, purchasing from embargoed countries, waivers to be obtained prior to the purchase of some items (such as vehicles), etc.
ECHO: refer to Annex-4 of the Framework Partnership Agreement of ECHO for details instructions relating to procurement (accessed from http://compliance.care.org.).
You can also access Procurement specific requirements of AusAid, CIDA, DANIDA, DFID, European Aid (EU) and NORAD at http://compliance.care.org.
2 | Item Description: Provide a brief description of the item that needs to be procured.
3 | Specifications/Model #: Since the space under this column is limited, provide specifications on a separate sheet if needed. Items such as vehicles, tractors, computers, etc., require detailed specifications in order to obtain adequate pricing. If you do not have adequate specifications, please mark "Specs NAV" and request Procurement's assistance in researching specifications to meet your particular needs. Becauase CARE has set certain minimum standards with regard to IT equipment/software check with your IT personnel or seek the assistance of the IT unit in Atlanta for help with specifications.
4 | Quantity: Indicate the total quantity required in your project proposal during the current Fiscal Year. If the project is spread over a period exceeding the current FY, any item to be procured beyond the current FY period should not be indicated on this plan.
5 | Estimated Unit Cost: Based on your project budget, indicate the estimated unit cost of the item. Procurement will conduct a market analysis should advise you if the item can or cannot be purchased at that unit cost.
6 | Total Estimated Cost: This information is automatically calculated within the worksheet.
7 | Geo Code: This is the code assigned by the US Government for certain items that are restricted or that need to be purchased in the USA and should also be of US origin. The code is "000". If your project is funded by the US Government, this information will be in the TA document signed between CARE and USAID/OFDA. With regard to other donors, check the individual agreement for any such restrictions. For example, it ECHO requires purchase with the European Union, indicate "EU" under this column.
8 | Fund Code: Indicate the fund code to which the item is to be charged.
9 thru' 12 | Estimated Quantity Required: Under Columns 9 thru' 12, estimate by FY calendar quarter when you want the item delivered to your project location. This allows Procurement to appropriately plan your delivery schedule and avoid interruptions in your program. Procurement will notify you immediately if there are any projected delays in purchasing or delivery.
If your total number of items under Column 4 does not equal the total of the items indicated unders Columns 9 thru' 12, an "Error" message will show up at the bottom of Column 12.
13 | Do you have a preferred vendor?: Under this column, indicate name(s) of any vendors that you have identified or have used sucessfully in the past. The vendor will need to be appropriately screened (including a Bridger check) and the vendor must have the capacity and ability to deliver the item on time and as per specifications. For instance, if the CO has standardized on Dell computers, indicate "Dell" or the name of the dealer / representative for Dell computers at your location. Another would be the purchase of vehicles - Toyotas or Nissans or another brand. It could be dependent on what the CO has standardized as equipment.
Signatures | This forecast is optional but if prepared review and sign before routing to procurement.

## Section-1-Program-Form
OPTIONAL PROCUREMENT FORECAST FORM
Section - 1 : Program Unit
[6 empty] | PN--> | CAI001 |  |  |  |  | FY -->>
| Name of Program / Project / Unit | [10 empty] | Updated On -->>
PROGRAM UNIT INFORMATION | [5 empty] | GEO Code | Fund Code | EST. QNTY REQUIRED |  |  |  |  | Do you have a Preferred Vendor? If so, please indicate name/location.
Item # | Item Description | Specs/ Model # | Qnty | Estimated Unit Cost - US $ | Total Estimated Cost - US $ |  |  | Jul-Sep | Oct-Dec | Jan-Mar | Apr-Jun
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  | 13
1 |  |  |  |  | 0
2 |  |  |  |  | 0
3 |  |  |  |  | 0
4 |  |  |  |  | 0
5 |  |  |  |  | 0
6 |  |  |  |  | 0
7 |  |  |  |  | 0
8 |  |  |  |  | 0
9 |  |  |  |  | 0
10 |  |  |  |  | 0
11 |  |  |  |  | 0
12 |  |  |  |  | 0
13 |  |  |  |  | 0
14 |  |  |  |  | 0
15 |  |  |  |  | 0
16 |  |  |  |  | 0
17 |  |  |  |  | 0
18 |  |  |  |  | 0
19 |  |  |  |  | 0
20 |  |  |  |  | 0
|  |  | 0 |  | 0 |  |  | 0 | 0 | 0 | 0
0
Note: | Please check on tab entitled "Sect-1-Guidelines-Program" for more information on this format.
| Prepared by |  | Reviewed by |  |  |  |  | Approved by / Proj. Manager
| Name: |  | Name: |  |  |  |  | Name:
| Title: |  | Title: |  |  |  |  | Title:
| Date: |  | Date: |  |  |  |  | Date:
Note on H6: This is per Donor requirements. Obtain waivers if necessary and in advance prior to commencing /finalization of the purchase of the item. Alert CARE USA Procurement Unit if procurement is restricted to the US.
Note on O6: Please provide the estimated quantity reqired by quarter.
Note on Q6: Preferred Vendor should be on the approved vendor list. If not, provide relevant information and justification to finance to include in SCALA

## Section-2-Procurement-Example
PROCUREMENT FORECAST FORM
Section - 2 : Procurement Update
| Agriculture Development Project, Undawata |  |  |  |  | PN--> | CAI001 |  |  |  | FY -->> | CY-2010
| Name of Program / Project / Unit | [9 empty] | Updated On -->> | 2009-07-15
PROGRAM UNIT INFORMATION | [5 empty] | PROCUREMENT UNIT REVIEW
Item # | Item Description | Specs/ Model # | Qnty | Estimated Unit Cost - US $ | Total Estimated Cost - US $ | Are Specs adequate? YES/NO | Potential Vendors Located? YES/NO | Local Market Avail-ability? YES/NO | Indicate Required Lead Time | Budget Listed Adequate? YES/NO | Can item be included for Bulk Purchase? YES/NO
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 | Toyota Landcruiser | 13-seater LWB | 1 | 28000 | 28000 | YES | YES | NO | 3 mnths | YES | N/A
2 | KSB Submersible Pumps | 380V/6" dia w/pipes-50' | 12 | 1250 | 15000 | NO | YES | NO | 3 mnths | NO | N/A
3 | Tractors - w/front loader | See details specs attached | 4 | 35000 | 140000 | NO | CARE-USA | NO | 6 mnths | NO | N/A
4 | Tractors - w/o front loader | See details specs attached | 3 | 30000 | 90000 | NO | CARE-USA | NO | 6 mnths | NO | N/A
5 | HP Printers - w/printer cable | Model Laserjet 2200D | 5 | 500 | 2500 | YES | CARE-USA | NO | 2 mnths | YES | N/A
6 | Dell Desktop Computers | Model Inspiron D800 | 15 | 1200 | 18000 | YES | CARE-USA | NO | 2 mnths | YES | N/A
7 | 0 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0
11 | 0 | 0 | 0 | 0 | 0
12 | 0 | 0 | 0 | 0 | 0
13 | 0 | 0 | 0 | 0 | 0
14 | 0 | 0 | 0 | 0 | 0
15 | 0 | 0 | 0 | 0 | 0
16 | 0 | 0 | 0 | 0 | 0
17 | 0 | 0 | 0 | 0 | 0
18 | 0 | 0 | 0 | 0 | 0
|  |  | 40 |  | 293500
Note: | Please check on tab entitled "Sect-2-Guidelines-Proc Unit" for more information on this format.
| Note to Procurement Unit |  |  |  |  | 7: Updated by (Proc. Unit); 12: Reviewed by/Proc. Manager
| Upon completion of update, please distribute to the following: |  |  |  |  | 7: Name:; 12: Name:
| [a] Program Manager, ACD-Program and/or the ACD-Program Support |  |  |  |  | 7: Title:; 12: Title:
| [b] If there are other personnel who have contributed to this document, |  |  |  |  | 7: Date:; 12: Date:
copies could also be sent to such personnel.
``
Note on F6: This section is automatically updated from information on Section-1.
Note on O6: Information in this section should be updated by the Procurement Unit before approval.
E X A M P L E

## Sect-2-Guidelines-Proc Unit
SECTION 2 - PROCUREMENT UNIT ACTIONS (If Program completes section 1)
GENERAL INSTRUCTIONS & GUIDELINES
Columns | Guidelines/ Instructions for Procurement Unit- If the program unit decides to complete the forecast form then Procurement must complete section 2
General | Only the second part of this form, i.e. from Col. 7 thru' 12 requires Procurement Unit action.
Col. 1 thru 6 are automaticlaly copied from Section-1
7 | Specifications: Indicate a YES or a NO under this column. If NO, immediately request program to provide you with the clarification.
8 | Potential Vendors: Review the listing of Potential vendors indicated in Section 1. The Procurement Unit should have already have some approved vendors for major items. If the commodity that is being requested has no approved vendor, begin identifying vendors in the market place.
If the item is to be procured has a Geo Code of "000", i.e. the item should be sourced and procured in the US only, please advise the CARE-Atlanta Procurement Unit immediately via email @hqprocurement@care.org. If an item is of U.S. source and origin, you must plan for a longer lead time for shipping from the U.S.
9 | Local Availability: Survey the market and establish if the item to be procured is available locally. If not, the item will have to be procured from overseas markets within your region or through CARE-Atlanta.
10 | Lead Time: After assessing the local/overseas markets, do you think that you have adequate time to follow proper Procurement procedures and ensure the delivery within the time period stated in Section-1 (Col. 9 thru-12)? If not, indicate the approximate lead time required for the entire process to be completed, including delivery at the CO level.
If you feel that the lead time is inadequate, please advise Program immediately in writing outlining clearly why a longer lead time is necessary. Such documentation is an important aspect in the procurement cycle. While verbal advice is acceptable, it is always advisable to put this down in writing copying all concerned.
11 | Adequate Budget?: After the market survey, do you feel that the item requested could be purchased within the estimated budget amount? If not, document your findings immediately and advise all concerned immediately.
12 | Bulk Purchase: If a similar item is being ordered by more than one project in your CO, you can combine the order and take advantage of the bulk purchase discount pricing structure. If the various projects have different delivery dates for the same item, a staggered delivery schedule can be built into the contract with the vendor.
INTERNAL NOTE | Col. 13 & 14: These columns have been left blank on purpose. These columns could be used in the future for any additional item/s that you may feel necessary.

## Section-2-Procurement-Form
PROCUREMENT FORECAST FORM
Section - 2 : Procurement Update
[6 empty] | PN--> |  |  |  |  | FY -->>
| Name of Program / Project / Unit | [9 empty] | Updated On -->>
PROGRAM UNIT INFORMATION | [5 empty] | PROCUREMENT UNIT REVIEW
Item # | Item Description | Specs/ Model # | Qnty | Estimated Unit Cost - US $ | Total Estimated Cost - US $ | Are Specs adequate? YES/NO | Potential Vendors Located? YES/NO | Local Market Avail-ability? YES/NO | Indicate Required Lead Time | Budget Listed Adequate? YES/NO | Can item be included for Bulk Purchase? YES/NO
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
1 |  |  | 0 | 0 | 0
2 |  |  | 0 | 0 | 0
3 |  |  | 0 | 0 | 0
4 |  |  | 0 | 0 | 0
5 |  |  | 0 | 0 | 0
6 |  |  | 0 | 0 | 0
7 |  |  | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0
9 | 0 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0
11 | 0 | 0 | 0 | 0 | 0
12 | 0 | 0 | 0 | 0 | 0
13 | 0 | 0 | 0 | 0 | 0
14 | 0 | 0 | 0 | 0 | 0
15 | 0 | 0 | 0 | 0 | 0
16 | 0 | 0 | 0 | 0 | 0
17 | 0 | 0 | 0 | 0 | 0
18 | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  | 0
Note: | Please check on tab entitled "Sect-2-Guidelines-Proc Unit" for more information on this format.
| Note to Procurement Unit |  |  |  |  | 7: Updated by (Proc. Unit); 12: Reviewed by/Proc. Manager
| Upon completion of update, please distribute to the following: |  |  |  |  | 7: Name:; 12: Name:
| [a] Program Manager, ACD-Program and/or the ACD-Program Support |  |  |  |  | 7: Title:; 12: Title:
| [b] If there are other personnel who have contributed to this document, |  |  |  |  | 7: Date:; 12: Date:
copies could also be sent to such personnel.
``
Note on F6: This section is automatically updated from information on Section-1.
Note on O6: Information in this section should be updated by the Procurement Unit before approval.