|  | EUROPEAN COMMISSION DIRECTORATE-GENERAL FOR HUMANITARIAN AID - ECHO Agreement |
| --- | --- |

# SINGLE FORM FOR HUMANITARIAN AID ACTIONS

## GENERAL INFORMATION

    - Name of Humanitarian Organisation/Country of registration: CARE International UK

    - Title of the Action:   Post Flood Livelihoods Early Recovery & Rehabilitation Programme for Poor and Marginalized People in Bangladesh

    - Area of intervention (country, region, localities):

| Districts | Upazillas | Unions |
| --- | --- | --- |
| Sirajganj | Chauhali | Khaskaulia |
|  | Sirajganj Sadar | Khoksabari |
|  |  | Chongachi |
|  | Shahazadpur | Parjana |
| Netrokona | Kalmakanda | Rangshati |
|  |  | Langura |
|  |  | Najirpur |
| Jamalpur | Dewanganj | Dandhara |
|  | Bakshiganj | Dhanwakamalpur |
|  |  | Battagore |

    - Start date of the Action: 1st March 2008

- If the Action has already started explain the reason that justifies this situation (urgent Action or other reason): N/A

    - Duration of the Action in months: 12 (twelve) months

    - Start date for eligibility of expenditure: 1st March 2008
Please explain if this date differs from submission initial proposal (see 1.10)

In the initial proposal the starting date was proposed from December 01, 2007. CARE Bangladesh has been implementing early recovery activities for the monsoon flood victims since mid-October 2007 and completed the ECHO funded flood response in early December 2007. Some of the activities funded by different donors such as agriculture recovery, Cash for Work and short term livelihood recovery will be completed by 15th Feb. 2008.

Following the Cyclone Sidr that ripped through the South-west of Bangladesh on 15th December 2007, many of the development interventions including flood response were hampered as many of the organisations including CARE extended humanitarian assistance to the cyclone affected people.  Since there was no feedback from ECHO, CARE did not start the operation. ECHO requested CARE to re-submit the flood response proposal in meeting held in Dhaka on January 17, 2008. Thus CARE proposed the above mentioned date for operation start date.

    - Requested funding modalities for this agreement
100% financing					X
Co-financing						
Multi-donor (for International Organisations)	 
In case of 100% financing: justify the request	:

CARE Bangladesh mobilised a total of USD 2.25 million for the monsoon flood response at emergency and recovery phase. Since the Cyclone Sidr hit the coast of Bangladesh CARE immediately diverted resources to emergency life saving activities. As an organisation CARE does not have its own sources of funding. Thus 100% of this proposed Post Flood Livelihoods Early Recovery & Rehabilitation Programme for Poor and Marginalised People in Bangladesh is requested for ECHO funding.

    - Urgent action	Yes 		No 
If yes:	Primary emergency	  
 		Emergency decision	  	
 		Other			   X	Please justify: Ad hoc decision

    - Control mechanism to be applied: A 		P X

    - Proposal and reports
Initial proposal			X		date:	23-11-07
Revised proposal N°.3		X		date:	20-02-08
ECHO reference A/…				date:	dd-mm-yy

- Intermediate report					date:	dd-mm-yy

- Final report						date	dd-mm-yy

- List the supplementary agreements and exchange of letters after signature of the Agreement up to intermediate report stage

- List the supplementary agreements and exchange of letters after submission of the Intermediate report up to final report stage

## NEEDS ASSESSMENT

    - Date(s) of assessment; methodology and sources of information used; organisation/person(s) responsible for the assessment

a)	In October 2007 CARE conducted a household assessment survey among 400 households in 8 upazilas, under 6 districts, including Siranganj, Netrokona and Jamalpur. Four of the flood response partners namely MMS, POPI, SAP and SKS were involved in conducting the assessment.

b)	Findings of field monitoring and observations in implementing the ECHO supported earlier flood response. Between September and November 2007, CARE implemented a humanitarian assistance programme for immediate flood response and recovery, operating in 11 flood affected districts and reaching 230,819 families.

b) 	Disaster Emergency Response Group (DER) draft report on post flood damage and needs assessment published as of 27 September 2007.

c)	Between 31st July and 1st August 2007, CARE conducted Upazilla-wise Rapid Assessments in 85 Upazillas to collect initial information about levels of damage, devastation and the current needs of the flood vulnerable people.

d)	A qualitative assessment focusing the needs of women and children was conducted between 6th and 8th August 2007.

e)	CARE conducted a Flood Response Lessons Learnt workshop in February 2008 involving all 9 partners. The findings of this will be taken into consideration in the implementation of the project.

### Methodology :

### Primary data were collected directly from the field through rapid assessment, focused group discussion and key informants interview at union level. CARE involved four local implementing partners (SKS, MMS, SAP and POPI) in the assessment. Methods used in the qualitative assessment were as follows:

- Structured questionnaire survey

- Key informants interview

- Focused Group Discussions (FGD) with the women of the affected communities

- Discussions with women members of Union Parishads (elected local government)

- Discussions with the women members of Union Parishad Disaster Management Committees (UDMC)

- Discussions with the members of EKATA (CARE’s ongoing women’s empowerment programme employing REFLECT methods with women’s groups)

### Secondary data review.

Sources of information:

- Needs Assessment Report

- DER (Disaster Emergency Response) group's coordination information

- Situation report from Disaster Management Information Centre (DMIC) of Disaster Management Bureau (DMB), Ministry of Food and Disaster Management

- Partner NGOs situation reports

- NIRAPAD's situation reports

- WFP's poverty map

- Flood forecast and warning centre

    - Problem statement and stakeholder analysis

- Bangladesh regularly experiences a wide variety of natural disasters. It’s geographical and geological position makes it one of the most hazard-prone countries in the world. In addition, in recent years, due to climate change and environmental degradation, the frequency and intensity of natural disasters in Bangladesh has increased.

- In 2007 the floods occurred in Bangladesh in two spells. The first of which occurred in July and continued for three weeks, affecting 39 districts. The second spell started in mid September and inundated 23 districts, including seven new districts, not previously affected. The floods have increased the vulnerability and poverty of poor and marginalised people.

- The impacts on people’s lives and livelihoods from the floods have been devastating. According to the Disaster Management Information Center of the Disaster Management Bureau, Ministry of Food and Disaster Management, around 13.34 million people (2.9 million households) have been affected by floods in 2007. Field crops have been washed away and a large number of the flood affected poor and marginalised families lost their houses and household assets. According to a preliminary report of the Ministry of Agriculture (MoA), standing crops, jute, vegetables and seedbeds worth USD 87 million on around 110,000 hectares of land have been affected. The impact of the crop damage has resulted in huge risks to the lives and livelihoods for the poor and marginalised farmers. Unemployment has been created as most depend on daily labour in agricultural activities during the pre and post harvest.

- A total of 84,321 houses (according to government statistics) have been totally destroyed by the floods while another one million houses were partially damaged. This has resulted in many flood-affected people (including women and children) being displaced and living in insecure housing. This is a big concern for ongoing winter and next rainy season.

- According to DG, DPE a total of 3,783 primary schools were affected by the floods, of which 47 were fully damaged and 1,487 were partially damaged. 242 schools were used as flood shelters during the floods.

Stakeholder Analysis:

- In the three proposed project districts, a total of 1,799,820 have been affected by the 2007 floods, of which 711,222 are extreme poor.

- Damage to crops has posed huge risks to the lives and livelihoods of poor and marginalised farmers. Unemployment has been created as most depend on daily labour in agricultural activities during pre and post harvest.  As high as 80-90% of people are suffering from a loss of income due to the disruption of their usual income opportunities in agri-labour and small- scale commercial activities. There is a prime need for employment creation as flood affected families are not in a position to kick start income generating activities.

- Damage to houses has resulted in many people becoming displaced and living in insecure makeshift structures on the roadside, open spaces and other inhumane situations.

- People are practicing open defecation as the floods have damaged sanitation facilities. Without the reconstruction of sanitation facilities, further environmental and health hazards will develop. Diarrhoea and other diseases will cause the poor and marginalised the loss of health and income and in some cases loss of lives.

- 70-80% government and public tube wells were submerged and many are not functioning. Access to safe water is limited and women and children have to spend considerable time collecting safe drinking water. This limits their productive time for household work, income generation and education. Tube-well installation and plinth raising is needed to facilitate access to safe drinking water and future flood risk reduction.

- Many of the non-registered primary schools have been damaged. Renovations of the schools are needed to resume classes. The drop out rate will increase in these community schools as children cannot attend school in damaged buildings. Moreover, many of the children will not attend due to a lack of education materials and clothing as their parents do not have resources to purchase these.

- Housing reconstruction is needed to provide secure shelters for flood displaced people. People also need employment opportunities. Cash for work in repairing of earthen rural roads, school renovations and platform raising, tube-well and water-seal latrine installation and platform raising are needed to create employment opportunities.

### Summarise findings of the assessment (include full report in annex, if relevant) and link these to the Action

- According to a preliminary report of the Ministry of Agriculture (MoA), standing crops, jute, vegetables and seedbeds worth USD 87 million on about 110,000 hectares of land have so far been affected.

- A total of 84,321 houses (according to government statistics) have been totally destroyed by the flood while another one million houses were partially damaged.

- 80-90% people are suffering from loss of income due to the disruption of their usual income opportunities

- 21% of respondents said that their crops were fully damaged. This significantly reduced agricultural labour. Many of the respondents mentioned that they are hardly able to earn Tk. 50 during and post the flood situation.

- 79% of respondents have only around 10 decimals of land.

- 18% of respondents houses are fully damaged, 37% partially and 31% moderately.

- Around 47% of the respondents have no latrine while 29% of the existing latrines were fully damaged by the flood.

- 70-80% of tube wells were submerged and many of them are not functioning. 50% of the targeted poor do not have any tube wells

- About 24% of the respondents said their water sources were fully damaged. 50% do not have any tube wells.

- About 13% of the respondents have sold their household assets to survive during and after the floods. 63% sold assets to purchase food for their families during and after the floods.

- 47 primary schools were fully damaged and 1,487 partially damaged. 242 schools were used as flood shelters during the flood.

- Post flood recovery and rehabilitation required was as follows (i) shelter e.g. house repairs, water and sanitation (37% prioritised), (ii) recovery of capital which has been consumed and/or damaged during flood and options to earn (34% prioritised).

- Significant numbers of respondents from affected families reiterated the demand for school renovation and support for their school going children.

- Health, hygiene and nutrition recovery support is also required.

- If changes in needs assessment at intermediate report stage, please explain

- If changes in needs assessment after intermediate report, please explain

## 3.       HUMANITARIAN ORGANISATION IN THE AREA OF INTERVENTION

  - Humanitarian Organisation's presence in the area of intervention: brief overview of strategy and current or recent activities in the country

Responding to humanitarian emergencies is an essential part of CARE’s work to fight poverty and injustice and we recognise that emergencies are a cause and effect of both. CARE helps people cope with crises through disaster risk reduction, emergency relief, preparedness and post-crisis recovery. CARE International recognised the current situation in Bangladesh as a humanitarian crisis and launched a consolidated appeal for funds to support the flood affected people in Bangladesh.

CARE has been operating in Bangladesh since 1955, and has had projects in housing, nutrition, irrigation, credit, health training assistance and agricultural development.  Current program areas include food security, agriculture and natural resources development, institutional strengthening, health, water and sanitation and rural/urban infrastructure.

CARE has responded to all national emergencies, including cyclones and floods, with funding support from institutional and private donors.  CARE undertook a large relief operation (food, shelter, water and sanitation) followed by long term rehabilitation and mitigation activities after the devastating 1991 cyclone that took the lives of 150,000 people in the coastal areas of Chittagong, Noakhali, Barisal and Khulna.

Since the beginning of the 2007 floods, CARE Bangladesh had been active in providing relief and rehabilitation assistance to flood affected victims.  A USD 2.25 million program has been implemented includes food and non food item distribution, medical support, cash for work and agriculture early recovery support.

  - Actions currently on-going and funding requests submitted to other donors (including other EC services) in the same area of intervention - indicate how overlap and double funding would be avoided

| Programme | Sector | Location | Donor | Status |
| --- | --- | --- | --- | --- |
| Bangladesh Monsoon Flood 2007 Early Recovery Programme | Agriculture and Livelihood | Kurigram, Gaibandha, Jamalpur, Netrokona, Serajgonj and Sunamgonj District | CARE USA Norwegian MoFA | On-going, will be completed by 15 February 2008 |
| SHOUHARDO (Strengthening Household Ability to Respond to Development Ability) | Food Security, Disaster Risk Reduction, Empowerment, Livelihood, Health & Nutrition | Char areas of Tista-Brahmaputra-Jamuna Basin, North-East Haor area and South-East Coastal area. Total 18 districts. | USAID Title II | Long term Development program (on going) |

Strategies to avoid duplication and overlapping :

- Separate management, staff, monitoring and accounts for the proposed project.

- The project will not target the same villages and beneficiaries where the existing projects are on-going. Different villages and beneficiaries will be targeted to avoid duplication and or overlapping.

- The project will also maintain regular coordination with CARE's ongoing projects as well as other NGOs to avoid duplication of efforts. In addition, CARE will maintain regular coordination and sharing meeting with the ECHO local office in Dhaka.

- CARE will maintain coordination with its partners, NGOs, and UDMCs. Through the SHOUHARDO CARE has already developed working relationships with local NGOs, UDMCs and local government bodies that will facilitate smooth operation of the project.

- Preference will be given to the village/working area outside SHOUHARDO.

- Report on other Actions carried out by the Humanitarian Organisation or its Implementing Partners in the same period in that area of intervention and how risks for double funding were avoided

## 4.         OPERATIONAL FRAMEWORK

  - Exact location of the Action (include map of project location)

| Districts | Upazillas | Unions |
| --- | --- | --- |
| Sirajganj | Chauhali | Khaskaulia |
|  | Sirajganj Sadar | Khoksabari |
|  |  | Chongachi |
|  | Shahazadpur | Parjana |
| Netrokona | Kalmakanda | Rangshati |
|  |  | Langura |
|  |  | Najirpur |
| Jamalpur | Dewanganj | Dandhara |
|  | Bakshiganj | Dhanwakamalpur |
|  |  | Battagore |

  - Beneficiaries

    - Total number of direct beneficiaries:

12,750 flood affected poor and marginalised people and 9,000 school going children of extreme poor families.

    - Status of the beneficiaries (multiple options possible)
 IDPs	  Refugees Returnees 	X local population	
 Others (e.g. for Grant Facility, thematic funding, etc.)

    - Specificities of beneficiaries (please elaborate, refer to groups as appropriate, e.g. unaccompanied minors, disabled, children, ex-combatants…)

The beneficiaries of the proposed project are the flood affected poor and marginalised people of three worst hit districts of Bangladesh. Their livelihoods were almost entirely have been exhausted by severe floods.  Without external assistance they are unable to recover from the huge loss (in the form of severe damage to standing crops, loss of livestock and damages to houses, tube wells for drinking water and hygiene latrines) they suffered and restore their livelihoods.   Although there has been support from the government and other agencies to overcome the emergency situation caused by the floods, these efforts have not been adequate to restore the losses incurred by the poor and marginalised people. Many have lost households’ assets and do not have adequate resources to meet their daily food and other requirements. CARE’s assessment of the targeted beneficiaries found that as a result of the floods, there are no/limited jobs for agricultural labourers  affected wage labourers  are currently unable to earn a daily wage of even Tk. 50 (approximately half a EURO).

The targeted beneficiaries are poor and marginalised individuals who depend on selling labour for agriculture and non-farm sector.  Between 80 and 90% of them are suffering from a loss of income due to the disruption of their usual income opportunities in agriculture and other small-scale income opportunities. The agrarian rural economy is unable to provide jobs for them and the recent price hikes (caused by rising inflation) of essential commodities have put intense pressure on the lives and livelihoods of potential beneficiaries.  In order to meet their immediate demand for food and survival needs potential beneficiaries have already used up whatever small savings they had, sold household assets, took loans from mahajons (local money lenders) at high rates of interests and purchased goods on credit. Some of them started selling labour in advance at wage rates substantially below the rates of normal periods.  The targeted beneficiaries' houses are fully or partially damaged and they cannot simply afford   repairs and reconstruction needed without external support.

The project targeted the poor and marginalised those who don't have secured shelter and access to water and sanitation. This posed women and children in a vulnerable situation and many of them have to spend considerable time in fetching water.

The project targeted primary school going children of the poor and marginalised families, many of their parents will not be able to bear the educational costs for their children. Children face difficulties in finding clothes in which to go to school. Dropout rate will increase.

    - Beneficiary identification mechanisms and criteria

Beneficiaries will be selected through a participatory mapping undertaken by CARE and PNGOs. Action specific beneficiaries will be selected using the following criteria:

Cash for Work

- Families living in makeshift houses

- Displaced, landless or unemployed families with no work

- Poor families with pregnant/lactating mothers and children under five years of age

- Poor families with many dependents.

- Families not registered by any other agency for CFW and/or rehabilitation programmes

House construction and Water Seal Latrines

- Flood displaced extremely poor people living in khas/leased land or with their own piece of land

- Poor families whose houses were damaged by last flood

- Poor families with pregnant/lactating mothers and/or numerous minor children

- Poor families with many dependents.

- Families not registered by any other agency for rehabilitation programmes

    - Describe to what extent and how the beneficiaries were involved in the design of the Action

- CARE and its partner NGOs have been working in the target area for a long time and have undertaken community consultations to develop community driven approaches for disaster risk reduction DP mainstreaming.

- Beneficiaries were involved in the needs assessment. Focused group discussions with the affected community and discussions with Union Parishad and UDMC members were undertaken to identify needs.

- The project will be implemented through the involvement of community groups, Union Parishads and UDMCs. Problem identification will be further confirmed in the initial phase of the action, to fine-tune the activities and interventions.

- At the project inception phase (2-6 weeks) CARE, along with partner NGOs will undertake a further, more in-depth consultation with the beneficiaries and local stakeholders. The purpose of the consultation will be to fit the proposed activities to the local context.

- Beneficiaries will be involved in a participatory monitoring and evaluation process.

    - Other potential beneficiaries (indirect, "catchment", etc.)

According to government estimates, around 10 million people are affected by flooding in 39 districts. The total population in the proposed three flood-affected project districts is around seven million, of which 2.7 million are extreme poor. A total of 1.7 million people are affected by floods in the proposed three project districts.

The DP mainstreaming activities designed by this project will benefit both the flood affected and non-flood affected catchment populations.

    - Beneficiaries per sector:

| Sector | Number of beneficiaries |
| --- | --- |
| Food security | 5,000 families |
| Water & Sanitation | 12,750 people |
| Rural Water Sources | 12,750 people and 19,000 students |
| Non food items | 9, 000 students |
| Permanent Shelter | 12,750 people |
| Educational facilities | 9,000 students |
| Disaster Preparedness & Mitigation | 12,750 direct beneficiaries / 7 million catchment population |

- In case of changes, please explain

- In case of changes, please explain

- Estimate per type of beneficiaries 
 	female:	… %,  	male:	… % (total= 100%)
 	infants (< 5y):	… %,	children (< 18 y): … %, 	elderly: … %

  - Objectives, Results and Activities

#### Overview: Log-frame (max. 3 pages)

| Title of the Action | Post Flood Livelihoods Early Recovery & Rehabilitation Programme for Poor and Marginalised People in Bangladesh |
| --- | --- |
| Principal Objective | To support flood affected poor and marginalised people in Bangladesh in recovering their shelter and livelihoods. |

|  | Intervention Logic | Objectively Verifiable Indicators | Sources of Verification | Risks and Assumptions |
| --- | --- | --- | --- | --- |
| Specific Objective | Provide post-flood recovery and rehabilitation support (cash for work, housing re-construction/repairs, access to water supply and sanitation, repair and renovation of non-registered primary schools and educational materials and clothes) with a focus on long-term disaster risk reduction. | - Short term employment opportunities created for at least 5,000 poor people to survive during and beyond the lean period - 2,550 water seal latrines installed at household and community levels - 146 tube wells installed in communities and schools - 1,500 houses repaired - 1,050 houses reconstructed. - 45 community primary schools renovated - 9,000 children from poor and marginalised families have educational materials and clothing to continue schooling - Community knowledge and awareness on flood preparedness and WATSAN increased | - Project progress and completion reports - Project interim and completion reports - Field visit and monitoring reports - Case studies and photographs - Media reports - Community FGDs | - No further disaster occurs and hampers project intervention. - Political situation remains stable - Local GOB authorities and communities extended their cooperation and support. - There is no major price hike or excessive inflation and/or scarcity of the required commodities in the market |
| Results | 1. Poor and marginalised people will have employment opportunities for at least 60 days and livelihood security to survive during and beyond the lean period. | - 5,000 poor and marginalised enrolled under CFW for at least 60 days - 5,000 of poor and marginalised families will have better income during and beyond lean period | - Master roll - Interim, pre final and final reports - Case studies - FGDs - Media reports - Photographs |  |
|  | 2. Poor and marginalised people have access to water-seal latrines and their sanitation situation improved | - 2,550 water seal latrines installed - 12,750 rural poor people have access to water seal latrines - Family and community support system developed for management of latrines | - Interim, pre final and final report - Case studies - FGDs - Media report - Photographs - Handover document - Meeting minutes |  |
|  | 3. Poor and marginalised people have access to safe drinking water and adequate sanitation. | - 146 tube wells installed - 12,750 people and 19,000 students have access to safe drinking water | - Interim, pre final and final report - Case studies - FGDs - Media report - Photographs - Handover document - Meeting minutes |  |
|  | 4. Displaced flood affected poor people have adequate shelter to live with dignity. | - 1,500 houses repaired - 1,050 houses reconstructed - 12,750 flood displaced people find better shelter - 2,550 of families have flood resistant houses | - Interim, pre final and final report - Case studies - FGDs - Media report - Photographs - Handover document - Meting minutes |  |
|  | 5. Community primary schools are renovated. Children of poor and marginalised families have educational materials and clothes to continue education. | - 45 community primary schools are renovated - 9,000 children have better classroom environments - 9,000 children of poor and marginalised families have educational materials and clothes to continue schooling | - List of schools - Physical verification of schools - Master roll of students |  |
|  | 6. Increased disaster preparedness (DP) awareness at the local level | - 10 local youth clubs/groups activated on DP - 150 youths (at least 20% female) receive equipment and training on search and rescue (SAR) and first aid - 10 events on DP/DRR orientation organised - 10 simulations on flood, SAR & first aid organised - 50 events on community based WATSAN orientation organised - 50 community based resource persons trained on tube raising and maintenance - 2,550 families receive wood and fruit (e.g. bananas, papayas, flood resistant trees) saplings and orientation on homestead plantation - 2 IEC materials on DP developed/reprinted and disseminated among target beneficiaries - Lessons learned document published and shared among disaster practitioners, policy makers and donors | - Interim, pre final and final report - Case studies - FGDs - Media report - Photographs - Handover document - Workshop/training report - Meeting minutes - Event report |  |
| Activities | - Enroll 5,000 poor and marginalised flood affected people into CFW for at least 60 days each. [EUR 225,158 (budget line 01.01.03)] 2.1. Install 2,550 of water seal latrines. Three rings, one slab, one bamboo pole, bamboo fencing and CI roofs will be provided to 2,550 families. [EUR 191,384 (budget line 01.02.01)] 2.2. 50 orientation sessions will be arranged for the beneficiaries, in order to raise their awareness about the safety and effective use of water seal latrines. Special care will be given for the maintenance of the water seals. 3.1. Install 146 tube wells [EUR 11,688 (budget line 01.02.02)] 3.2. 50 orientation sessions will be arranged for the beneficiaries to raise their awareness about the use of safer water and special care for the maintenance of the tube wells, as these are their social assets. 4.1 Repair 1,500 partially damaged houses [EUR 60,042 (budget line 01.07.01)] 4.2 Re-construct 1,050 fully damaged houses [EUR 183,879 (budget line 01.07.01)] 5.1 Renovate 45 flood affected community primary schools [EUR 13,903; (Budget line 01.07.02) 5.2 Distribute educational materials and clothes amongst 9,000 school children [EUR 45,032 Budget line 01.06.05] 6.0 Mainstreaming Disaster Preparedness [EUR 43,841 (budget line 01.08.80)] Facilitation and coordination [EUR 4,003; (Budget line 01.08.08) 6.1 Activate 10 local youth clubs/groups on DP mainstreaming 6.2 Provide training and equipment on search and rescue and first aid to 150 youth, of which at least 20% will be female 6.3 Organise 10 events on DP/DRR orientation 6.4 Organise 10 simulations on flood SAR and first aid 6.5 Organise 50 events on community based WATSAN orientation 6.6 Provide hands on training to 50 poor and marginalised people on water seal latrine and tube well installation and maintenance 6.7 Provide wood and fruit (e.g. bananas, papayas, flood resistant trees) saplings and orientation for homestead plantation to 2,550 families 6.8 Developed/reprint 2 IEC materials on DP and disseminate among targeted beneficiaries 6.9 Publish lessons learned document and share among disaster practitioners, policy makers and donors. |  |  |  |
|  |  |  |  | Pre-conditions - Communities accept the structural and preparedness measures - Coordination established amongst partners, local government bodies and GOB line agencies - UP and UDMC members contribute to project activities - CARE and partner NGOs recruit and/or deploy staff in a timely manner - Donors mobilise fund in a timely manner |

#### More detailed information per result

| At proposal stage |  |  |
| --- | --- | --- |
| Result #1 : Poor and marginalised people will have employment opportunities for at least 60 days and livelihood security to survive during and beyond the post-flood lean period. |  | Total amount: 225,158 EUR |
| Beneficiaries (status + number): 5,000 flood affected poor and marginalized families | Sector: Food Security Related sub-sector Food for Work |  |
| Indicators for this result: - 5,000 poor and marginalized enrolled under CFW for at least 60 days - 5,000 of poor and marginalized families will have better income during and beyond lean period |  |  |
| Activities related to the result: - Conduct FGD and assessment to identify and enroll 5,000 flood affected poor and marginalized families for CFW. - Identify DRR schemes and form community level PIC (Project implementation committee) - Regular payment to beneficiaries. - Monitoring working environment and work progress. - Documentation & visibility | Means and related costs: - Fund for CFW; [EUR 225,158 (Budget line 01.01.03)] - Project Staff - Vehicle, conveyance and transport. - Logistics and management. Means 2, 3 & 4 is common for all Results. Total cost of those is 184,524 EUR, which is 23.8% Goods and Services Delivery Cost. |  |
| Intermediate report |  | Total amount: …….…... EUR |
| Update on indicators: … | Update6 on beneficiaries (status + number): … |  |
| Update6 on activities: … | Update6 on means and related costs: … |  |
| Final report |  | Total amount: …….…... EUR |
| Indicators for achieved result: ... | Final state on beneficiaries (status + number): … |  |
| Activities accomplished: …. | Finally committed means and related costs: … |  |

| At proposal stage |  |  |
| --- | --- | --- |
| Result #2 : Poor and marginalised people have access to water-seal latrines and their sanitation situation improved |  | Total amount: 191,384 EUR |
| Beneficiaries (status + number) : 12,750 rural poor people have access to water seal latrines | Sector: Water & Sanitation Related sub-sector : Waste disposal & latrine |  |
| Indicators for this result: - 2,550 water seal latrines (WSL) installed - 12,750 rural poor people have access to water seal latrines - Family and community support system developed for management of latrines. |  |  |
| Activities related to the result: - Conduct FGD and assessment to identify communities and enroll 2,550 flood affected poor and marginalized families for WSL support. - Procure and/or produce rings, slab, bamboo pole, bamboo fencing and CI roofs for 2,550 WSL. - Install 2,550 WSL - Undertake community awareness activities on hygiene promotion. 50 orientation sessions will be arranged for the beneficiaries, in order to raise their awareness about the safety and effective use of WSL. Special care will be given for the maintenance of the water seals - Monitoring work progress and effectiveness. - Documentation and visibility. | Means and related costs: - Fund for WSL installation. [EUR 191,384 (Budget line 01.02.01)] - Project Staff - Vehicle, conveyance and transport. - Logistics and management. Means 2, 3 & 4 is common for all Results. Total cost of those is EUR 184,524 which is 23.8% of Goods and Services Delivery Cost. |  |
| Intermediate report |  | Total amount: …….…... EUR |
| Update on indicators: … | Update on beneficiaries (status + number): … |  |
| Update on activities: … | Update on means and related costs: … |  |
| Final report |  | Total amount: …….…... EUR |
| Indicators for achieved result: ... | Final state on beneficiaries (status + number): … |  |
| Activities accomplished: …. | Finally committed means and related costs: … |  |

| At proposal stage |  |  |
| --- | --- | --- |
| Result #3 : Poor and marginalised people have access to safe drinking water and adequate sanitation. |  | Total amount: 11,688 EUR |
| Beneficiaries (status + number) : 12,750 rural poor people and 19,000 students have access to safe drinking water | Sector: Water & Sanitation Related sub-sector : Rural Water Sources |  |
| Indicators for this result: - 146 tube wells installed - 12,750 people and 19,000 students have access to safe drinking water |  |  |
| Activities related to the result: - Conduct FGD and assessment to identify communities and schools for tube well installation. - Procure and install 146 tube wells. - Test Arsenic contamination in the tube well water. - 50 orientation sessions will be arranged for the beneficiaries to raise their awareness about the use of safer water and special care for the maintenance of the tube wells, as these are their social assets. - Monitoring work progress and effectiveness. - Documentation and visibility. | Means and related costs: - Fund for Tube wells installation. [EUR 11,688 (Budget line 01.02.02)] - Project Staff - Vehicle , conveyance and transport. - Logistics and management. Means 2, 3 & 4 is common for all Results. Total cost of those is 184,524 EUR, which is 23.8% of Goods and Services Delivery Cost. |  |
| Intermediate report |  | Total amount: …….…... EUR |
| Update on indicators: … | Update on beneficiaries (status + number): … |  |
| Update on activities: … | Update on means and related costs: … |  |
| Final report |  | Total amount: …….…... EUR |
| Indicators for achieved result: ... | Final state on beneficiaries (status + number): … |  |
| Activities accomplished: …. | Finally committed means and related costs: … |  |

| At proposal stage |  |  |
| --- | --- | --- |
| Result #4 : Displaced flood affected poor people have adequate shelter to live with dignity. |  | Total amount: 243,921 EUR |
| Beneficiaries (status + number) : 12,750 flood displaced people find better shelter resistant to future floods. | Sector: Rehabilitation/continuum Related sub-sector : Permanent shelter |  |
| Indicators for this result: - 1,500 houses repaired - 1,050 houses reconstructed - 12,750 flood displaced people find better shelter - 2,550 of families have flood resistant houses |  |  |
| Activities related to the result: - Conduct FGD and assessment to identify 2,550 flood affected poor and marginalized families for house reconstruction and repairing support. - Procure and/or produce house reconstruction and repairing material. - Repair 1,500 partially damaged houses - Re-construct 1,050 fully damaged houses - Monitoring work progress and effectiveness. - Documentation and visibility. | Means and related costs: - Funds for house reconstruction and repairing. [EUR 243,921 (Budget line 01.07.01)] - Project Staff - Vehicle , conveyance and transport. - Logistics and management. Means 2, 3 & 4 is common for all Results. Total cost of those is 184,524 EUR which is 23.8% of Goods and Services Delivery Cost. |  |
| Intermediate report |  | Total amount: …….…... EUR |
| Update on indicators: … | Update on beneficiaries (status + number): … |  |
| Update on activities: … | Update on means and related costs: … |  |
| Final report |  | Total amount: …….…... EUR |
| Indicators for achieved result: ... | Final state on beneficiaries (status + number): … |  |
| Activities accomplished: …. | Finally committed means and related costs: … |  |

| At proposal stage |  |  |
| --- | --- | --- |
| Result #5 : Community primary schools are renovated. Children of poor and marginalised families have educational materials and clothes to continue education.. |  | Total amount: 58,541 EUR |
| Beneficiaries (status + number) : 9,000 children of poor and marginalized families have educational materials and clothes to continue schooling. | Sector: Rehabilitation/continuum Related sub-sector : Education facilities [EUR 13,509; (Budget line 01.07.02)] Sector: Non-food items Related sub-sector : Education items [EUR 45,032 Budget line 01.06.05] |  |
| Indicators for this result: - 45 community primary schools are renovated - 9,000 children have better classroom environment - 9,000 children of poor and marginalized families have educational materials and clothes to continue schooling |  |  |
| Activities related to the result: - Conduct FGD and assessment to identify 45 community primary schools and 9,000 students for education facilities support. - Procure and/or produce school renovation materials. - Procure education material (will be finalized in discussion with children) and clothes. - Renovate 45 flood affected community primary schools - Distribute educational materials and clothes amongst 9,000 school children. - Monitoring work progress and effectiveness. - Documentation and visibility. | Means and related costs: - Funds for education facilities — school renovation [EUR 13,509; (Budget line 01.07.02)]; education material and clothing for students [EUR 45,032 Budget line 01.06.05]. - Project Staff - Vehicle, conveyance and transport. - Logistics and management. Means 2, 3 & 4 is common for all Results. Total cost of those is 184,524 EUR which is 23.8% of Goods and Services Delivery Cost. |  |
| Intermediate report |  | Total amount: …….…... EUR |
| Update on indicators: … | Update on beneficiaries (status + number): … |  |
| Update on activities: … | Update on means and related costs: … |  |
| Final report |  | Total amount: …….…... EUR |
| Indicators for achieved result: ... | Final state on beneficiaries (status + number): … |  |
| Activities accomplished: …. | Finally committed means and related costs: … |  |

| At proposal stage |  |  |
| --- | --- | --- |
| Result #6 : Increased disaster preparedness (DP) awareness at the local level. |  | Total amount: 47,844 EUR |
| Beneficiaries (status + number) : 12,750 direct beneficiaries and 7 million catchments population vulnerable to regular flood disaster. | Sector: Disaster Preparedness and Mitigation Related sub-sector : i) Facilitation and coordination [EUR 4,003; (Budget line 01.08.08)] ii) Local capacity building/training [EUR 43,841 Budget line 01.08.80] |  |
| Indicators for this result: - 10 local youth clubs/groups activated around DP - 150 youths (at least 20% female) receive equipment and training on search and rescue (SAR) and first aid - 10 events on DP/DRR orientation organized - 10 simulations on flood SAR and first aid organized - 50 events on community based WATSAN orientation organized - 50 community based resource persons trained on tube raising and maintenance - 2,550 families receive wood and fruit (e.g. bananas, papayas, flood resistant trees) saplings and orientation on homestead plantation - 2 IEC materials on DP developed/reprinted and disseminated among target beneficiaries - Lessons learned document published and shared among disaster practitioners, policy makers and donors |  |  |
| Activities related to the result: - Conduct FGD and assessment to identify youth clubs/groups, and youths. - Conducts events/trainings on DP. - Procure wood and fruit (e.g. bananas, papayas, flood resistant trees) saplings and distribute those to beneficiaries received house repairing and reconstruction support. - Develop 2 IEC materials on DP. - Organize lesson learn workshop. - Organize dissemination seminars/events. - Monitoring work progress and effectiveness. - Documentation and visibility. | Means and related costs: - Funds for facilitation and coordination [EUR 4,003; (Budget line 01.08.08)]; local capacity building/training [EUR 43,841 Budget line 01.08.80]. - Project Staff - Vehicle , conveyance and transport. - Logistics and management. Means 2, 3 & 4 is common for all Results. Total cost of those is 184,524 EUR, which is 23.8% of Goods and Services Delivery Cost. |  |
| Intermediate report |  | Total amount: …….…... EUR |
| Update on indicators: … | Update on beneficiaries (status + number): … |  |
| Update on activities: … | Update on means and related costs: … |  |
| Final report |  | Total amount: …….…... EUR |
| Indicators for achieved result: ... | Final state on beneficiaries (status + number): … |  |
| Activities accomplished: …. | Finally committed means and related costs: … |  |

| Other costs | Initial amount | Intermediate report |  | Final Committed |
| --- | --- | --- | --- | --- |
|  |  | Budgeted | Committed |  |
| Total other costs |  |  |  |  |

  - Work plan (e.g. annex Gantt chart) – Attached as Annex 2

  - Revised work plan, if changed after proposal

  - Final work plan, if changed after Intermediate report

  - Monitoring, evaluation, audit and other studies

#### Monitoring of activities (explain how, by whom)

Participatory monitoring of progress and results will be an ongoing process throughout the project period. The monitoring system will involve beneficiaries as well as local stakeholders to develop a sense of ownership and commitment. Rigorous data will be collected to measure progress, address problems, record experiences, and disseminate findings. The project will orient local partners in the collection and analysis of information. Project and partner staff will also conduct regular meetings with UDMC, local NGOs and GOB authorities to address implementation challenges and to coordinate effectively. A Monitoring and Documentation Coordinator will be responsible for providing strategic support at all stages of the project on information.

Qualitative data will be collected through key informant analyses and focus group discussions. Selected case studies will substantiate and give depth to the operation. The Monitoring and Documentation Coordinator will report to the Emergency Response Coordinator on a weekly basis. During monitoring if s/he observes any critical problems that are affecting the operation, s/he will report to the Emergency Response Coordinator immediately to take necessary measures. Major objectives of operation monitoring are to:

i)	collect information on the operation on a monthly basis and report on a quarterly basis.

ii)	help staff make decisions to improve and/or terminate response efforts

iii)	ensure accountability of key players involved in the response

iv)	make the operation more effective

Means of information collection:

- Formatted data collection

- Discussions with beneficiaries

- Discussions with UP Chairman/Members/UDMC members

- Observations

- Review Master-roll

The project will undertake periodic monitoring and recording of the progress of the activities against the set indicators. Project staff, including the Emergency Response Coordinator and the Humanitarian Assistance Coordinator, will conduct regular monitoring visits to address implementation challenges. In addition, CARE’s Assistant Country Director will make visits to the project areas to oversee progress against project plans and ensure quality control.

Project reports will be reviewed for both quality and clarity by both programme and financial staff at CARE International UK.

#### Tick the box if one of the following studies will be undertaken:
 an external evaluation during the Action
X an external evaluation after the Action
 an external audit during the Action
X an external audit after the Action
X  an internal evaluation or internal audit related to the Action

#### Other studies:   please elaborate:

#### (please remember that for external evaluations, audits and studies financed by the Commission the Terms of Reference have to be agreed by DG ECHO before launching the selection procedure)

## CROSS-CUTTING ISSUES

- 5.1   Describe the expected level of sustainability and/or connectedness

The operation will build on the success of the previous project experiences of CARE and PNGOs - to assist vulnerable communities to improve their human condition and social position. A similar USAID funded programme is being implemented by CARE – SHOUHARDO. Attention will be given to ensure the proposed project does not overlap with the above mentioned projects and similar projects of other organisations, but rather builds on the lessons learned.

The project will promote sustainability through ensuring appropriate members of the community are trained in the operation and maintenance of the tube wells and latrines. Activating local youth clubs and capacity development of the youth will contribute towards evolving a local support structure in future disaster response. The plinth rising of hoses, tube wells, latrines, schools and markets will help target populations to survive during future floods.

The DP mainstreaming activities that have been planned under this project will result in increased knowledge and awareness among communities to take the lead in DRR activities. Targeted coordination and consultation with local institutions, UP, civil society stakeholders and local GOB institutions will influence their ability to plan and coordinate future DRR activities.

The involvement of UPs and UDMCs in project implementation will also have a positive impact on the sustainability of this project.

- 5.2	  Continuum strategy (Linking Relief, Rehabilitation and Development)

CARE’s programme strategies have been broadened to encompass rights based approaches with a focus on the underlying causes of poverty. CARE works in partnership with communities, local partners and local government institutions to amplify the voices of the poor and the marginalised in ways that influence public opinion, development practice, and policies at all levels. Improving the lives and livelihoods of poor and marginalised people living in disaster prone, vulnerable areas is one impact vision of CARE.

In a recent programming shift, CARE’s disaster management approach has changed from relief to community based disaster preparedness. Currently SHOUHARDO and FRRAS projects are undertaking community based disaster management activities in the proposed project areas. CARE’s five-year SHOUHARDO (Strengthening Household Ability to Respond to Development Opportunities) Programme is working in the same region. The basic rationale for the proposed project is that the poorest Bangladeshi households and communities frequently suffer development setbacks in the face of annual local natural disasters leading to the loss of lives and productive assets. These communities may take several years to recover, only for the next disaster to happen. The intent of the disaster risk mitigation activities is thus to help vulnerable populations to anticipate and cope in advance with the reality of natural disasters, as a regular part of ongoing development activities.

CARE is working to build the capacity of local elected bodies in understanding disaster risk reduction and contingency planning for emergency response. The involvement UP and UDMC members at various stage of the project will deepen our understanding about the particular vulnerabilities of people living in disaster prone areas.

- 5.3     Mainstreaming (e.g. Disaster Risk Reduction, Human rights,          Gender, Environmental impacts, others to be specified)

The proposed project supports a fundamental humanitarian principle of the International Covenant on Economic, Social and Cultural rights of the UN Charter, and the Universal Declaration of Human rights, namely the right to life with dignity. This includes the right to an adequate standard of living, adequate food, clothing and housing and the continuous improvement of living conditions, which should be enjoyed by all citizens.

Likewise, the project promotes gender equity and child rights and seeks to influence power structures at the household and local levels. The project design takes into account the contemporary role of women in Bangladeshi society and their responsibilities within the household. Intervention strategies were developed based upon gender consultations related to women’s interests, needs and priorities, especially in remote rural villages. By allocating power/ownership over provided resources with women, their contribution to household livelihood security will be more valued and will help to promote the equitable participation of women in household decision-making. In addition, the strategy of targeting women contributes to overcome barriers to women’s participation in activities outside of the household.

The project will undertake various approaches to ensure the active involvement of women, in terms of decision-making in design, maintenance and management of tube wells, latrines and the ownership of houses. Women will benefit greatly through reduced time spent in the collection of water and improved sanitation facilities.

- In case of changes or problems to be addressed, please explain

- In case of changes or problems to be addressed, please explain

## FIELD COORDINATION

- 6.1	Field co-ordination (indicate the Humanitarian Organisation's participation in coordination mechanisms with other relevant stakeholders, e.g. clusters, NGOs, UN agencies, others to be specified as well as the links with the Consolidated Appeal Process, when relevant)

- 6.2 National and local authorities (relations established, authorisations, coordination)

At the national level, CARE Bangladesh is a member of different government, non-government and donor coordinating bodies including “Disaster and Emergency Response (DER)”. CARE Bangladesh participates in these forums for the enhanced coordination of activities, resources and information. CARE Bangladesh has en established coordination mechanism amongst all regional field offices, partner offices and the GOB. The exchange of information and learning will be undertaken through this mechanism.

To provide commodities support to the targeted areas in an efficient/timely manner and to avoid potential duplications, CARE Bangladesh will maintain a coordination and networking relationship with the DER, Disaster Management Bureau (DMB), and Network for Information, Response and Preparedness Activities on Disaster (NIRAPAD), Disaster Forum, Federation of NGOs in Bangladesh, etc. CARE will coordinate with GOB officials, and use the current good working relations to maximise coordination and impact.

CARE and the proposed implementing partners made coordination with other agencies in the proposed operation areas. The targeted unions have been selected in consultation with partners and in coordination with other implementing agencies to minimise duplication and overlapping.

CARE’s project coordination and management system includes standard procedures for quality control for all its projects/programmes. One key aspect of this procedure is the establishment of a project management committee. In the proposed project, CARE will establish a project committee consisting of members from the project, senior management personnel from both CARE and the PNGOs. The committee will meet every three months to oversee the performance of the project. The project will also maintain regular coordination with CARE's ongoing projects, as well as other NGOs, to avoid duplication of efforts. In addition, CARE will attend regular coordination and sharing meetings with ECHO and its partners in Bangladesh to exchange knowledge and experiences.

CARE will place its Field Supervisors at the PNGO's offices to establish effective coordination and partnerships, as well as to maintain linkages and communication with all relevant stakeholders such as UP, NGOs, local administrations etc.

The project will be complemented by CARE's ongoing projects in the targeted areas. Hence, CARE will maintain coordination with its partners, NGOs, and UDMCs. Through SHOUHARDO CARE has already developed working relationships with local NGOs, UDMCs and local government bodies that will allow the smooth operation of the proposed project.

- 6.3 Co-ordination with DG ECHO (indicate the Humanitarian Organisation's contacts with DG ECHO and its technical assistants in the field)

CARE has successfully completed the Emergency Flood Response Project (Ref: ECHO/-SA/BUD/2007/02003) with funding support from ECHO.

Currently implementing "Humanitarian Relief Assistance for Vulnerable People affected by cyclone 'SIDR' with funding support from ECHO (please ECHO/BGD/BUD/2007/03002)

CARE also regularly participated in the partners coordination meeting in Bangladesh. In addition, CARE International UK also maintaining regular coordination with ECHO in Brussels.

- In case of changes or co-ordination problems, please explain

- In case of changes or co-ordination problems, please explain

## IMPLEMENTING PARTNERS

- 7.1 Name and address of implementing partner(s)

Manab Mukti Sangstha (MMS)

Vill. Khas Barashimul

P.O. Banggabandhu Bridge (west sub)

C/O. The City Bank

Dis. Sirajganj

Email: hb_mms@yahoo.com

South Asia Partnership (SAP) Bangladesh

H # 63, Block – Ka

Cooperative Society Ltd.

Phn.: 88-02-8112103, 8114697

Mob: 01711530990

Email: sapbdesh@citechco.net

People’s Oriented Program Implementation (POPI)

5/11-A, Block – E, Lalmatia, Dhaka – 1207

Phn.: 88-02-9121049, 9137769

Email: popi@bdmail.net

- 7.2  Status of implementing partners (e.g. NGO, local authorities, etc.) and their role

CARE has a long track record of partnership with the above three local organisations. They have been implementing SHOUHARDO programme in partnership with CARE since January 2006. All of the partners were involved in CARE's emergency flood response. SAP has been involved in the implementation of the emergency flood response funded by ECHO.

- 7.3 Type of relationship with implementing partner(s) and the expected reporting by the implementing partner

CARE forged partnerships for implementing developmental and /or relief programmes with the proposed partner organisations. Each of the proposed three project partners have implemented/are currently implementing emergency flood response initiatives in partnership with CARE. The partners were involved in the assessment of flood damage and in identifying the situation of vulnerable people. The project team will work in close collaboration with the partners in beneficiaries' selection, distribution of relief goods and coordination with other agencies (GO-NGO). CARE will closely monitor the operation and its internal auditor will oversee the procurement and financial operations.

- In case of changes, please explain

- In case of changes, please explain

## SECURITY AND CONTINGENCY MEASURES

- 8.1 Contingency measures (Plan B/ mitigating actions to be taken if risks and assumptions spelled out in the log-frame materialised)

| Assumptions and Risks | Probability | Actions to mitigate and or minimise |
| --- | --- | --- |
| No further disaster occurs and hampers project intervention. | High | Observe field situation, consult ECHO and make necessary changes or adjustments in operation |
| Political situation remains stable | Low | Observe the situation and if instable situation arises consult ECHO |
| Local GOB authorities and communities extended their cooperation and support. | Low | Coordination, advocacy and lobbying with government |
| There is no major price hike or excessive inflation and/or scarcity of the required commodities in the market | Medium | Monitor the market, consult ECHO and make necessary changes or adjustment in operation where required |

- 8.2 Security considerations

- 8.2.1 Security situation in the field, describe briefly

Bangladesh is currently under a state of emergency. Demonstrations, political activity, and hartals (nationwide strikes) are banned during the state of emergency and the situation seems calm. However the security situation in Bangladesh is fluid and uncertain, it could deteriorate quickly. Spontaneous demonstrations take place in Bangladesh from time to time in response to world events or local developments. Protests involving workers from the large garment-manufacturing industry are not uncommon in Dhaka and other industrial cities.

There is a general threat from terrorism. Attacks cannot be ruled out and could be indiscriminate, including in places frequented by expatriates and foreign travelers.

However, risk for implementing humanitarian assistance or development projects is very low. There is no political and or local pressure that creates obstacles in implementing humanitarian assistance or development projects.

- 8.2.2 Has a specific security protocol for this Action been established?
Yes		No		Standard procedures	X
If yes please elaborate:

- 8.2.3 Are field staff and expatriates informed of and trained in these procedures?
Yes X		No 	

- In case of changes or problems to be addressed, please explain

- In case of changes or problems to be addressed, please explain

## COMMUNICATION, VISIBILITY AND INFORMATION ACTIVITIES

- 9.1 Planned communication activities (in field and/or in Europe)

CARE will make deliberate attempts to communicate with all the stakeholders including the European audience about the project, its implementation progress and impact. CARE will provide information and data on the project, including number of recipients of relief goods and services and photographs on CARE (www.carebd.org) and DER websites, including those of European CI members.

CARE will engage local and national media expert to develop human interest stories and articles to be published in the national and international media. From time to time CARE will send out press releases to local, regional and international media. Making use of its existing communication channels it will keep all stakeholders including the government, relevant donors and other agencies (e.g. local and international NGOs) informed and updated about the proposed operation. The lessons learnt of the project will circulated widely to different stakeholders acknowledging the contribution of ECHO. Print and electronic media will be fed with information and data on the operation on a regular basis. Tools for information dissemination will include briefings, information pack, press visits on site. CARE newsletters will include stories from the operation and existing opportunities for reaching European audience in disseminating information and data will be capitalised on.

Visibility plan includes putting ECHO's logo on all documents and reports prepared under the proposed operation and ECHO's stickers on materials as deemed appropriate. Partners offices from which the operation will be carried out will have sign board with ECHO's logo placed on appropriate places. ECHOs' contribution will be acknowledged in correspondence with all institutional actors concerned. Efforts will be made to inform the beneficiaries about the source of funding.

In addition, CARE will engage international media experts and fellows of different media organisations such as Panos London to feature the project interventions, and how the project is contributing to flood and climate change adaptation.  The features will be posted on CARE Bangladesh and CARE UK website. CARE will share regular press release along with the features to different knowledge portals such as Livelihoods Connects www.livelihoods.org Development Gateway www.developmentgateway.org, www.reliefweb.int  and www.alertnet.org . Furthermore, the successfully funded, project would feature in our monthly e-bulletin, an electronic newsletter distributed to 20,000 CARE supporters, and in the quarterly newsletter which receives a circulation of almost 25,000 with acknowledgement of ECHO support. Finally, CARE UK will undertake initiatives for news coverage in UK.

Throughout the implementation process and in all project activities and publications, CARE will ensure that ECHO’s support is duly recognised. CARE will ensure the visibility of ECHO through various initiatives, including:

  - CARE will hold an official opening ceremony and organise learning/sharing workshops to inform a broader audience about the intervention. Local and national media will be invited, together with representatives of union parishads, community representatives, and other relevant stakeholders, which will raise the visibility of ECHO and its contribution to the project. CARE will ensure that ECHO is provided with full credit for the funding. Local authorities, communities and beneficiaries will be informed about the support given by ECHO

  - The ECHO logo will be incorporated in all the information and communication materials that the project will produce and use. All of these materials will acknowledge the support provided by ECHO, as appropriate in local languages

  - During meetings with communities and relevant stakeholders (government and non government), ECHO’s contribution to this project will be duly recognised

  - Where and when appropriate, the project will produce t-shirts, caps, bags, etc which include ECHO’s logo

  - CARE will organise learning/sharing workshops to inform a broader audience about the intervention. Local and national media will be invited, together with representatives of union parishads, community representatives, and other relevant stakeholders, which will raise the visibility of ECHO and its contribution to the project. CARE will ensure that ECHO is provided with full credit for the funding. Local authorities, communities and beneficiaries will be informed about the support given by ECHO

  - CARE will closely coordinate with ECHO’s local representatives to ensure strong, appropriate national and international media coverage of the project and its impact on vulnerable households and institutions.

- 9.2 	Visibility on durable equipment, major supplies, and at project locations

The ECHO logo will be incorporated in all the information, communication and training materials that the project will produce and use. The commodities and materials that will be distributed to the community will include ECHO’s logo. Similarly, where and when appropriate, the project will produce t-shirts, caps, bags, etc. with ECHO logo. All of these materials will acknowledge the support provided by ECHO, as appropriate in local languages

- 9.3	Planned publication activities

- In case of changes, please explain

- Report on the relevant activities

## HUMAN RESOURCES

Indicate global figures per function and status

| Function | Status | Number of staff | Number of man/month in project | Comments (such as % time allocation,…) |
| --- | --- | --- | --- | --- |
| - Donor contact (operation) point for the project - Thematic/DRR issue related advise and guidance - Oversees overall monitoring, planning, development, implementation and review of the project - Leads liaison, communication, advocacy and lobbying at strategic and policy level - Leads media, communications and visibility | National Staff | 1 (one) | 4.8 person months | 40% time; Emergency Response Coordinator |
| - Overall implementation of project activities - Oversees project activities and ensures project achieves its targets in a timely manner - Assists project staff in procurement and delivery of commodities - Ensures compliance with ECHO rules and regulations, framework partnership agreement, partnership with PNGOs and sub-contractual agreements with service providers - Coordination and linkages with ECHO and its partners - Undertakes coordination and advocacy work at national level - Execution and management of contracts, including donor reporting | National Staff | 1 (one) | 12 person months | 100% time; Emergency Response Manager |
| - Ensures projects have very good systems for monitoring and evaluating the progress and results of the project - Develops and executes monitoring and evaluation plans of the project - Helps in mapping, research and final evaluations, as well as regular monitoring and project reporting - Data management, analysis and quality assurance of gathered data - Technical assistance and capacity building for staff on M&E | National Staff | 1 (one) | 12 person months | 100% time Monitoring & Documentation Coordinator |
| - Strategic leadership and guidance - Oversees overall planning, development, implementation and review of the project - Support liaison, communication, advocacy and lobbying at strategic and policy level - Leads and/or support media, communications and visibility | International Staff | 1 (one) | 1.5 person months | 10% shared time; Assistant Country Director |
| - Planning and implementation of project activities - Lead needs assessment at the field level - Monitor and reports on operation and delivery - Work with partners in planning activities - Ensure standards and compliance - Ensure proper use of resources - Maintain liaison with other related stakeholders as per project need - Documentation and contribution to reporting | National Staff | 3 (three) | 36 person months | 100% time; Field Supervisor |
| - Assists with fund management and procurement in accordance with ECHO guidelines - Ensures timely support to project staff and partners - Assists project staff in fixing logistic support such IT support, travel arrangement, etc | National Staff | 1 (one) | 12 person months | 100% time; Finance & Admin Assistant |
| - Overall implementation of project activities at field level - At field level, oversee project activities and ensure project achieves its targets in a timely manner - Assist partner procurement and delivery of commodities - Ensure compliance with ECHO rules and regulations, framework partnership agreement, partnership etc. at PNGO level - Coordination and linkages with field organisers and field supervisors - Undertake coordination and visibility work at local/field level | PNGO Staff | 3 (three) | 36 person-month | 100% time; Project Manager PNGO |
| - Facilitate the beneficiaries' selection and community planning process - Identify appropriate participants for different community events - Assist project team in identification of appropriate methodology in distribution of commodities - Facilitate community consultations and planning - Implement targeted interventions at community level - Facilitate handover process of the hardware facilities | PNGO Staff | 9 (nine) | 108 person- month | 100% time; Programme Organiser PNGO |
| - Pre and post survey of scheme. - Scheme Preparation: Design and layout of the scheme. - Wage measurement and Cost calculation - Progress Monitoring and reviewing the scheme - Maintain scheme document and prepare reports | PNG Staff | 3 (three) | 36 person months | 100% time Community engineer |
| - Preparation of project budget and look after fund management in accordance with ECHO guidelines - Oversee financial management and audit requirements - Conduct regular monitoring of project expenditure trends in accordance with approved budget - Ensure financial support to project team for smooth implementation of project activities - Timely financial reporting on the project | PNGO staff | 3 (three) | 19.5 person-months | 50% shared time; Accountants PNGO |
| - Ensure following procurement policy and procedures - Ensure proper financial management - Assist partners in proper financial monitoring - Ensure field logistical and project support - Internal audit | Shared National Staff | 8 (eight) | 12 person-months | 10% shared time; finance, admin, procurement and logistic support staff |
| - Planning and implementation of project activities - Supervise and technical assistance to project staff - Ensure proper use of resources - Maintain liaison with relevant stakeholders as per project need | PNGO Staff | 3 (three) | 4.5 person months | 10% of shared time: PNGO Executive Director and/or Senior Management |

- In case of changes, please explain

- In case of changes, please explain

## FINANCIAL OVERVIEW

| Eligible cost of Action | Initial budget | Intermediate report |  | Final committed | Funding of Action | Initial | Final state |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Budget | Committed |  |  |  |  |
| Personnel costs | 117,229 |  |  |  | Direct revenue from Action |  |  |
| Low value equipment allowance | 735 |  |  |  | Contribution by applicant |  |  |
| Equipment partially charged costs |  |  |  |  | Contribution by other donors |  |  |
| Equipment fully charged costs | 4,203 |  |  |  | Contribution requested from ECHO | 1,047,071 |  |
| Consumables & goods costs | 774,533 |  |  |  | % of total funding: 100% |  |  |
| Sub-contracting costs |  |  |  |  |  |  |  |
| Communication, visibility, information | 10,007 |  |  |  |  |  |  |
| Logistics and running costs | 66,360 |  |  |  |  |  |  |
| Other costs (FD 4 Audit & evaluation) | 5,504 |  |  |  |  |  |  |
| Subtotal direct eligible costs |  |  |  |  |  |  |  |
| Indirect costs (max. 7%) | 68,500 |  |  |  |  |  |  |
| Total Costs | 1,047,071 |  |  |  | Total Funding |  |  |

- In case of other donors, please identify the donors and the amount provided

## ADMINISTRATIVE INFORMATION

### 12.1 ECHO FPA number, (if applicable) FPA 03/017

- 12.2 Name and title of legal representative signing the Agreement

Geoffrey Dennis – Chief Executive Officer

- 12.3 Name, telephone, e-mail and title of the person(s) to be mentioned in Article 7 of the Agreement

Kate Akhtar – Emergency Programme Officer

Akhtar@careinternational.org

+44 (0)207 9334 9314

- 12.4 Name, telephone, fax and e-mail of the representative in the area of intervention

Stav Zotalis - Assistant Country Director

CARE Bangladesh

Tel: + 880-2-8114207, 9112315 (Ext. 213) Fax: + 880-2- 8114183

Email: stav@carebangladesh.org

- 12.5 Bank account 
Name of bank: Barclays Bank Plc
Address of branch: Level 28, 1 Churchill Place, London, E14 5HP, UK 
Precise denomination of the account holder: CARE International UK
Full account number (including bank codes):

Account no: 68522600 Sort code: 20-82-94

- IBAN account code, (or BIC country code if the IBAN code does not apply): IBAN GB77 BARC 2082 9468 5226 00 13

## CONCLUSIONS AND HUMANITARIAN ORGANISATION'S COMMENTS

Two consecutive floods have caused huge damage to crops, household assets, houses and social and community structures in the proposed three districts of Bangladesh. The losses and destruction caused by the floods are so severe that   many poor and marginalised people in rural communities are unable to recover and restore their normal lives without external assistance.  The proposed areas of operation are highly disaster prone and among the worst hit districts.  The proposed interventions will not only help them in their efforts to recover from the shock and rebuild their shelter and maintain livelihoods but also strengthen their capacities to become more resilient to economic and social vulnerabilities.

CARE has been implementing humanitarian assistance programmes with support from various institutional and foundation donors, including ECHO for long. This response is to assist the flood-affected communities to cope with their sufferings and struggle they are undergoing.  The rehabilitation programme will help the targeted poor and marginalised to start a new life in improving their human conditions, as well as building community resilience.

CARE considers rehabilitation support to be critical and is therefore seeking continued support from ECHO for this response.

At proposal stage fill the numbered paragraphs. For the intermediate report, modify only key data in the numbered paragraphs (strikethrough) and fill out the paragraphs I. For the final report, modify only key data in the numbered paragraphs (strikethrough) and fill out the paragraphs F.

This table will be annex I of the signed Agreement. It has to be a concise overview of the different elements of the Action. Any changes made to the log-frame at intermediate report or final report stage will be done using strikethroughs.

Per result identified in the log-frame, the table will be progressively completed at proposal, intermediate report and final report stage. As the log-frame has to be concise, more detailed information necessary for a good understanding of the proposal/ report will be gathered here.

The guidelines will contain a table of sub-sectors per sector.

The main means and costs have to be identified in order to understand how the results will be reached and the activities implemented (see guidelines for more detail).

Update to be provided on progress as well as on changes made to the proposal, including their justification

The last table groups the costs that have not been dedicated to one specific result (support costs, feasibility studies, audits etc. as explained in the guidelines). The total of the total amounts mentioned per result and in this table will correspond to the subtotal direct eligible costs in the table section 11.

Sustainability and connectedness are similar concepts used to ensure that activities are carried out in a context that takes longer-term and interconnected problems into account.

Expat, local staff, staff of the implementing partner,…

This table will constitute annex II of the signed Agreement

The partner can use another representation of costs as long as at least personnel costs and the costs on information, communication and visibility can be distinguished.