Partner: CARE Österreich			Implementation period: 01/09/07 – 31/12/08

Operation contract:	                                                 		Amount requested: Euro 200,000

Country: Nepal			Date of this logical framework: 26/08/2007

|  | Intervention Logic | Objectively Verifiable Indicators | Sources of Verification | Risks and Assumptions |
| --- | --- | --- | --- | --- |
| Principal Objective | To provide post-flood rehabilitation support to the victims of flooding in Dhanusha, Mahottari, Sarlahi, Banke, Bardia and Kailali districts of Nepal. |  |  |  |
| Specific Objective | To provide post-flood rehabilitation support (housing construction materials, access to clean drinking water, and support to rehabilitate/install tube wells) to 625 flood affected families in Dhanusha, Mahottari, Sarlahi, Banke, Bardia and Kailali districts of Nepal. | - At least 625 poor and most marginalized households will get to repair their houses through provided materials (such as bamboo, roofing materials etc). - At least 625 households will have access to clean drinking water through the support provided for rehabilitation/installation of 130 tube wells. - 16 damaged schools toilets will be supported through rehabilitation/ construction. | - Field visit reports - Interim and final reports - School management committee records - Participatory community- evaluation report | - The emergency situation does not pose direct threat to the lives of project staff and partners. - Staff and community groups are able to implement and monitor activities safely. |
| Results | R.1. Reconstruction of the damaged houses/school toilets of the flood victims. | - At least 625 poor and most marginalized households will get to repair their houses through provided materials (such as bamboo, roofing materials etc). - 16 damaged schools toilets will be supported through rehabilitation/ construction. | - Field visit reports - Interim and final reports - School management committee records - Participatory community- evaluation report |  |
|  | R.2. Access to clean drinking water. | - At least 625 households will have access to clean drinking water through the support provided for rehabilitation/installation of 130 tube wells. | - Field visit reports - Interim and final reports - Participatory community- evaluation report |  |
| Activities | Activity for Result 1 - Provide Support for rehabilitation /construction of community housing. - Provide Support for rehabilitation /construction of school toilets. Activity for Result 2 - Provide support for rehabilitation/installation of 130 tube wells benefitting | Means - Staff, construction materials (bamboo, roofing materials). - Community laborers, local materials (sand, stones, aggregate, timber, etc.) | Costs The total budget requested from ECHO for the operation is estimated at a cost of Euro 200,000. |  |
|  |  |  |  | Pre-conditions The emergency situation does not deteriorate to the extent that the life of the project staff is under direct threat. |