|  | EUROPEAN COMMISSION HUMANITARIAN AID OFFICE (ECHO) grant agreement |
| --- | --- |

# SINGLE FORM FOR HUMANITARIAN AID OPERATIONS

## 1.	GENERAL INFORMATION

### 1.1.	Name of humanitarian organisation: 	CARE International Deutschland e.V.

### 1.2. 	FPA number (if applicable): 			3-016

### 1.3.	Purpose of the submission

1.3.1.	Proposal

New proposal				date:	24-09-2007

Revised proposal 		X	date:	11-10-2007

1.3.2.	Interim narrative report			date:	dd-mm-yy

1.3.3.	Preliminary final report			date:	dd-mm-yy

1.3.4.	Final report					date	dd-mm-yy

### 1.4.	Grant agreement number		ECHO/

### 1.5.	Implementing rules applicable to this agreement

Grant, 100% financing		X

Grant, co-financing			

### 1.6.	Framework of this submission

Primary emergency decision	

Emergency decision 			

Ad hoc decision			

Global plan decision			X

DIPECHO				

Other, please specify			

### 1.7	Executive summary of operation

  - Title of the operation

“Emergency Relief to Internally Displaced Persons (IDPs) and host communities in conflict affected areas, Sri Lanka“

  - Country(ies) and location(s) of implementation

Following the deteriorating security situation and the subsequent displacement of thousands of families in Mannar district the proposed intervention will be implemented in the areas of the northwestern district under control of the government and to a greater extent those under the control of the LTTE. CARE will assist the displaced families and their host communities and address the most pressing needs in close coordination with all relevant public authorities and international and local agencies. At this point in time, Manthai West DS division (LTTE controlled) and Nanattan DS division (Government controlled) and Mannar DS division (Government controlled) have been identified as the areas with the highest number of displacement and the direst needs for immediate assistance. However, the areas of intervention might change as the people may move further away from where the fighting takes place. Thus, the proposed intervention might shift to other DS divisions of Mannar District or adjacent districts as Killinochi and Mullaitivu.

| Manthai West DS Division (LTTE controlled) | Nanattan DS Division (Government controlled) | Mannar DS Division (Government controlled) |
| --- | --- | --- |
| Villages | Villages | Villages |
| 1. Illuppakadavai | 1. Kovvankulam | 1. Keeri |
| 2. Paliaru | 2. Mooddakkadai | 2. Thottavely |
| 3. Vellankulam | 3. Pallankottai | 3. Ollathoduva |
| 4. Koori | 4. Valkkaippattankandal |  |
| 5. Athimottai | 5. Kattakadu |  |
| 6. Periyamadhu | 6. Ponthivukandal |  |

Should the security situation in Mannar deteriorate to an extent that CARE can not remain operational, CARE would work with the ECHO representatives in Colombo to implement planned or alternative activities in an alternative location in the north or east of the country.  Due to the extreme fluidity of the current situation, the exact area will be specified only when the scenario occurs and the subsequent decision will be based mainly on the needs of the IDPs and host families and the security threats prevailing in possible intervention areas.

  - Start date of the operation:	15 October 2007

  - Duration in months:			8 Months

4.5.1. Total number of direct beneficiaries:

| Target Area | Villages | IDP families | Host families | Total No. of persons |
| --- | --- | --- | --- | --- |
| Manthai West | 6 | 1,169 | 200 | 5,476 |
| Nanattan | 6 | 300 | 300 | 2,400 |
| Mannar Town | 3 | 140** | 100 | 960 |
| TOTAL | 15 | 1,609* | 600*** | 8,836**** |

*Please note that the IDP numbers provided by the GA are somewhat higher than the numbers mentioned in this table. The above quoted figure has been provided by UN OCHA after an assessment mission conducted on 17th September 2007. Additionally, displacement is ongoing, new families continue to arrive which makes data inaccurate.

**Please not that the IDPs in the three selected villages are currently being relocated from the welfare camps in Murunkan and are expected to arrive at the time of the proposal writing

***The exact number of host families which will be supported can not be specified as yet, but the water activities will also be of benefit to numerous host families as well as the emergency preparedness activities

**** The average family has four members.

Please note that the number of beneficiaries is already disaggregated. At this point it can not be exactly specified how many beneficiaries benefit from more than one project component. All the people currently residing in the project area will benefit from the hygiene training, the emergency preparedness trainings and the improved access to water.

(4.5.2.) Identify the status and give details of the beneficiaries

CARE will target with the proposed intervention six villages in Manthai West DS division, six villages in Nanattan DS division and three villages in Mannar DS division. The rational for targeting these villages is the number of recently displaced IDPs, the vulnerability of the people and the assistance received so far. Since the relief effort is currently ongoing, the locations may change in case the villages will be assisted by other agencies or in case of further population movement. The majority of the IDPs are currently staying in common buildings, with host families or in small gatherings out in the open, seeking shelter under trees or tarpaulin sheets. Most pressing needs are food, shelter, safe water and a range of NFRIs.

Approximately 1,609 IDP families will directly benefit from the provision of safe water. Depending on the respective context, the resident population will also benefit from the water provision. Moreover, the hygiene promotion as well as the awareness raising and prevention campaign against endemic diseases will target the IDP and host population in the selected villages. 370 IDP families will be provided with temporary shelter facilities. The same number will be provided with the most essential NFRIs identified for an eight month period. For the clothing needs CARE will coordinate with other specialised agencies for an adequate coverage. The number of IDP families benefiting from the NFRI component is most likely to increase as NFRI assistance is ongoing since the escalation of conflict in the intervention area but as yet patchy and on an ad hoc basis. Therefore, CARE will address NFRI needs wherever gaps have been identified. Hence, it is anticipated that the entire package is not required in all cases.

Special attention will have to be given to particular vulnerable parts of the IDP population such as pregnant women, lactating women, female headed households, mentally and physically disabled persons and unaccompanied children and elderly. A rapid assessment in Manthai West comprising more than the selected villages has shown that the above mentioned vulnerable groups are amongst the IDP population in a considerable number.

    - Specific objective

To improve living conditions of IDPs and host communities in conflict affected areas, Sri Lanka

    - Indicators and sources of verification

Indicators:

- 330 IDP families have received essential NFRIs

- 30 vulnerable host families have received essential NFRIs

- 1,169 IDP families have access to safe water and improved awareness of hygiene and sanitation issues

- 287 IDP families’ temporary shelter needs are met.

- 15 communities have been trained in EPP/DRR

- CARE response meets Sphere common standards and incorporates best practise in HAP feedback mechanisms

Sources of Verification

- Final project report

- Baseline survey/assessments at project start

- Project Monitoring and evaluation report

- Official documents from local authorities

### 4.8.	Results and Indicators

(4.8.1.) Expected result #1

#### Increased access to essential NFRI for target IDP and host families

#### Indicators:

- 350 IDP families have sufficient personal hygiene items for an eight month period

- 330 IDP families have access to cooking and eating utensils

- 30 vulnerable host families have sufficient essential NFRIs

- 287 IDP families have sufficient tools and equipment for maintenance and safe use of their shelters (e.g. mosquito nets)

- 150 IDP families have sufficient infant NFRIs for 8 months

- Monthly (or every 2 months) distributions take place in a manner that ensures active participation and appropriate targeting

Sources of Verification

- Final project report

- Baseline survey/assessments at project start

- Project Monitoring and evaluation report

- Official documents from local authorities

(4.8.2.) Expected result #2

#### Increased access to, use and awareness of safe water and hygiene issues

#### Indicators:

- 2 Water bowsers delivering safe drinking water to 12 IDP’s and vulnerable host communities (estimated 90,000 litres / day) for 8 months period

- 60 Water storage points (2,000ltr.) constructed in vulnerable IDP and host communities.

- Rehabilitation possibilities of existing water sources explored and carried out when feasible

- 1 bowser for three month period delivering according to the need

- 15 health and hygiene campaigns, posters and meetings organised.

Sources of Verification

- Final project report

- Baseline survey/assessments at project start

- Project Monitoring and evaluation report

- Official documents from local authorities

(4.8.3.) Expected result #3

#### Increased access to shelter facilities

#### Indicators:

- 287 IDP families have received temporary shelter items.

- 287 temporary shelters are located in hazard free environments

Sources of Verification

- Final project report

- Baseline survey/assessments at project start

- Project Monitoring and evaluation report

- Official documents from local authorities

(4.8.4.) Expected result #4

Communities have increased awareness and capacity to deal with impact of conflict

##### Indicators:

- 15 trainings and 15 visits to build knowledge and awareness of preparedness issues.

Sources of Verification

CARE monitoring reports

Please refer also to the logical framework attached as annex 1.

  - Total budget of the operation: 		EUR  250,000

  - Contribution requested from EC: 	EUR  250,000

(11.5.)  Eligibility date of expenditure:		15 October 2007

## 2.	NEEDS ASSESSMENT

### 2.1.	Date(s) of assessment

CARE conducted a rapid assessment on 15th August in the “LTTE controlled areas” of Manthai West and Madhu. Additionally, CARE is responding to the displacement in Nanattan DS division since the 1st of September. Seven out of the 13 villages that are facing an influx of IDPs as a result of the military operations in Musalai are working villages of the former ECHO funded project.  In these villages CARE is gathering relevant data on a daily basis and in close coordination with other agencies, public authorities and the established Village Emergency Preparedness Committees.

Complementary information has been provided by the consortium of humanitarian agencies in Mannar whch conducted an assessment from 7th to 9th September in Nanattan DS division. On 8th September UNHCR also shared their findings from a rapid assessment conducted in Nanattan and on the 17th September the UN partner organisations carried out an assessment in Manthai West which was also shared with all agencies in the Vanni on the 19th September.

Another assessment had been carried out by the ICRC in Manthai West. The findings have been shared in the coordination meetings in Killinochi.

Since the situation is changing on a daily basis, the respective DS, the Mannar GA and the LTTE authorities are providing frequent updates on the population movement as well. However, all the figures provided need to be dealt with cautiously as they sometimes differ considerably from one source to the other.

### 2.2.	Methodology and sources of information used

This proposal is to a large degree based on the findings of three assessments, carried out in Manthai West: The ICRC assessment, the UN OCHA assessment and CARE’s rapid assessment. Differing methodologies were applied to collect the data such as standardised assessment formats taking into account all sectors and more specific questionnaires focusing on certain focal areas (ICRC assessment focuses on Shelter, Water and Protection only). The UN OCHA assessment was conducted by the UN agencies and a number INGOs in eight GN divisions of Manthai West. More than 350 people have been interviewed during the data collection. Periyamadhu, one of CARE’s selected villages has been left out for security reasons since accessibility from Killinochi is restricted.

In the course of CARE’s rapid assessment, senior project staff together with the safety and security advisor conducted interviews with IDP and host families and held meetings with the public authorities in Manthai West.

Moreover, the Government Agent (GA) of Mannar District provides weekly updates of the current location and the number of IDPs. During the assessments considerable inconsistencies between those numbers and the reality on the ground became noticeable. As the GA is fuelled with IDP information by the Gramma Niledhari (GN) and the District Secretary (DS), CARE used as information source the data available at the lower government level so the degree of reliance increased.

Additionally, relevant data were gathered on a daily basis in the Government controlled areas of Mannar District as the CARE Mannar team was leading the emergency response to the displacement in its focal villages.

### 2.3.	Organisation/person(s) responsible for the assessment

Overall responsibility:

Nick Osborne

Country Director

CARE International in Sri Lanka

Operational responsibility:

Sally Austin – Assistant Country Director Programme

F A Cader – Programme Director

### 2.4.	Problem statement and stakeholder analysis

Sri Lanka has seen since April 2006 a resumption of the more than two decades old conflict between the Sri Lankan Government and the rebel Liberation Tigers of Tamil Eelam (LTTE) affecting millions of people in terms of displacement, damage and destruction of property and infrastructure. More than 5,000 people have been killed and thousands more suffered injuries and isolation. The direct conflict takes place mainly in the North and East of the island where the LTTE controls significant parts of the territory. In 2006 and 2007 the fighting mainly concentrated on the East of the country as the SLA tried to drive the LTTE out of the areas they held in Batticaloa and Trincomalee. The military confrontations in the East have calmed down after the SLA captured most of the main LTTE strongholds. However, the fighting has now moved further to the North along the Forward Defense Lines (FDL) which separates the Vanni (LTTE controlled area), from the Government controlled areas.

The Mannar District is located on the West coast of Sri Lanka. It is a border district where control is divided between the Sri Lankan Government (GoSL) and the Liberation Tigers of Tamil Eelam (LTTE). There are regulated checkpoints between the two zones that act as a border crossing with strict control over movement of goods and persons. Furthermore, even in the South of Mannar District in Musalai DS division, there are clusters in which the LTTE is operating and which are since the beginning of September subject to SLA military operations aimed at the eviction of the LTTE from these areas.

The military operations in Musalai which began on 1st September 2007 caused the displacement of approximately 1,323 families (4,635 persons). The majority of the displaced are now staying with host communities in Nanattan DS division but Mannar island also faces an influx of IDPs. Even though it was announced that the people have to vacate their homes only for a couple of days, there is still no sign that the affected population can go back any time in the near future. In fact, it has been announced that the Sri Lankan Government plans to set up police stations and naval and/or army bases in the captured area and would thus allow the people to return only after this process has been finished. While the UN agencies and the ICRC have taken on the responsibility for the IDPs which are currently accommodated in welfare camps that are guarded by the SLA, the international NGOs present in Mannar and organised in the interagency coordination body provide initial emergency relief to the IDPs staying with friends, relatives or on common land in the communities. In addition to the people which have been displaced due to the fighting in Musalai, there is an increasing number of people leaving their homesteads over night seeking safety in neighbouring villages as the tensions along the FDL increases.

Throughout the first nine months of 2007 people living in the LTTE controlled part of Mannar district (Madhu, Manthai West) were leaving their homesteads, seeking for sanctuary within the district as an upsurge in skirmishes, shelling and military manoeuvres alongside the FDL made life insecure in many areas and created an atmosphere of fear amongst the people, many of them with a long history of displacement. As the fighting intensified with the onset of heavy government shelling over the past weeks, the people moved further to the North towards Killinochi and Mullaitivu District with the vast majority of the people still residing in Manthai West. According to the figures shared by the DS Manthai West on 18th September, 2048 families (approx. 7915 persons) have been recently displaced within Manthai West DS division. The assistance to the IDPs residing in Mannar “LTTE controlled areas” is hampered by the security situation and the recent closure of the Uyilankulam entry/exit point after the ICRC withdrew its staff on 3rd September 2007. However, even though the most important gate in Mannar is currently closed CARE have received approval from the Government authorities to transport essential items to Manthai West and Madhu.

In regard to those areas of the Mannar District that are under the control of the LTTE, two different scenarios seem most likely to occur during the proposed time of intervention which will also affect the situation in the Government controlled territory. In case the SLA tries to advance into the LTTE area, the FDL will most likely shift which will cause further displacement, leaving people being caught in the crossfire on both sides. As seen in the recent past, an advancing army will also cause displacement in already “cleared” areas as supply routes will be “secured”. Therefore, on both sides a considerable number of IDPs will be in dire need of immediate assistance. People residing currently in Manthai West will try to move further to the North away from the fighting, Mannar town and Nanattan would most likely face further influx of IDPs on the government controlled side of Mannar. If this scenario evolved, CARE would respond with its Mannar team in those areas that are accessible from the Government controlled side. The CARE offices in Killinochi and Malawi would take on the responsibility to respond from within Vanni to the displacement in Manthai West and Madhu.

In case there will be sporadic fighting without any major push by the SLA into the LTTE controlled areas of the Mannar district, it is expected that the Uyilankulam E/E point will be opened at least temporary be it with ICRC presence or without. If this scenario occurred, CARE would respond with its Mannar team from the Government controlled area to the displacement in Manthai West crossing the Uyilankulam E/E point, bringing in required goods and items with the necessary permission by the GA Mannar. For the eventuality of a sudden border closure, CARE will set up a safe house in collaboration with another international agency equipped with communication facilities, sleeping berths, food rations and basic medical items. Since the needs for assistance are considered higher in the Mannar “LTTE controlled areas” the main focus of the intervention would be Manthai West whilst CARE would nonetheless keep responding to the displacement in the Government controlled part of Mannar, mainly in Nanattan and Mannar town as these are the places with the highest numbers of recently displaced IDPs in the “GoSL controlled” areas.

Generally, every activity carried out in Mannar has to be sensitive to the particular context in the region. Of main importance in Mannar because of its fluctuating population numbers are the ethnic composition and the several types of disputes over land issues that in the past caused occasionally intercommunal violence. Even though Mannar is not densely populated, the land that can be used is fairly limited. Also, it needs to be taken into account that the recently displaced add to a high number of displaced families living in Mannar “GoSL and LTTE controlledreas” for already many years.. Furthermore, the long history of war and displacement has disrupted the livelihoods of the stable population in Mannar and even the recovery efforts in the post-CFA period were limited and have created competition for those limited resources between the communities. Therefore, every relief activity has to consider the needs of the most vulnerable in host communities as well, in order to avoid tensions between groups.

CARE will coordinate with all stakeholders in Mannar. Institutionalised coordination meetings are in place with international and local NGOs present in Mannar (Consortium of Humanitarian Agencies (CHA). The UN agencies chair the frequent interagency meetings which at this point in time focus very much on the welfare camp situation. Additionally, all humanitarian assistance is being coordinated with the Mannar Government Agent (GA). Material transport into the “LTTE controlledareas” needs prior approval by the GA and liaison with the Security Forces Commander in the Vanni. Additionally, the church and particularly the Mannar Bishop play an important role in Mannar District and need to be involved into the relief efforts to the displaced.

The response in Manthai West needs to be coordinated with the LTTE authorities as well which will be done with the local representative but also with the Killinochi PDS through the CARE office in Killinochi. The agencies based in Killinochi will be informed and coordinated with through the regularly scheduled coordination meetings.

### 2.5.	Findings of the assessment

The assessments in Nanattan DS division and Mannar town DS division revealed that the majority of the IDPs are staying with host communities. Those families that are accommodated in SLA controlled camp-like arrangements are being assisted by the ICRC and the UN agencies with the support of some INGOs. WFP is providing dry food rations to all registered and screened displaced from Musalai. The GA in Mannar has published that as of the 15th September 4,316 IDPs have arrived in Nanattan due to the onset of fighting in Musalai DS division. 319 IDPs are staying in Mannar town, but the number will increase as the people residing in Nanattan schools will be relocated to Mannar town in order to reopen the school facilities again.

The most urgent needs have been identified as temporary shelter, Water and temporary Sanitation facilities and Non-food relief items as towels, buckets, cooking utensils, mats, lanterns etc. but also hygiene and infant kits. All different kind of arrangements can be found in the host communities: people staying in common places, people staying on land provided by the church authorities, people staying with host families (one host family is hosting up to 10 IDP families). Since the displacement will last for a yet unknown time span, it is essential to provide temporary shelter that can withstand the rainy season which is just about to start. Rapid assessments have shown that IDPs prefer to stay in shelters that are constructed with cadjan rather than tarpaulin as the common tarpaulin tents are not adequate for the hot weather. In the Government controlled areas of Mannar, cadjan is easily available and thus would be used for temporary shelter in the proposed intervention. The scarcity of potable water and the lack of latrines are general problems in the area but is now becoming a serious hazard for the health of the people in an increasingly overcrowded environment.

The situation in Manthai West is currently more fluid as the IDPs are continuously moving towards the North arriving in places as Kovilulam, Athimoodi, Pali Aru, Vellankulam etc.  According to the Manthai DS 2048 families are displaced in Manthai West, most of them staying out in the open, using trees or plastic sheets as cover. Others have taken refuge in communal buildings as schools or churches. Only very few are staying with host families on their plot of land, the vast majority are gathering in communal places and in some places greatly outnumbering the resident population, which is different from the situation in Gosl areas of Mannar.  In coordination meetings of the Killinochi based agencies, it has been stressed that only one third of the shelter needs can be met and that a common effort is urgently required to address the basic shelter needs of all the IDPs currently displaced in Manthai West.

Due to the security situation, the restriction on transport and the poor road conditions, assistance is reaching these people only slowly. Huge problems have been identified with the water supply as most of the wells contain saline water that can be used only for cleaning purposes. The set up of water tanks and water bowsering have also been identified as a priority in Manthai West. Wells that are used pose health risks to the people, as they are in bad conditions and require cleaning and repair works. Even though some agencies (ZOA, WV) have already started bowsering in some villages, the need is much higher. Moreover, it has been observed that sanitary facilities in almost all IDP locations are not available which perpetuate the health risks the IDPs are facing. Diseases like diarrhoea can easily spread and combined with the lack of available medical care, becomes a serious threat mainly to children.

As described above, the lack of adequate basic shelter structures makes its provision to the affected IDPs a priority. Different to Nanattan and Mannar town, cajan is very scarce in Manthai West but can be purchased in Mullaitivu and therefore used as shelter material. The upcoming rainy season makes the shelter provision an urgent requirement. Moreover, all assessments have shown that sanitary items, mosquito nets and kitchen utensils are urgently required to alleviate the suffering and meet the most basic needs.

In discussions the IDPs currently displaced in Manthai West stressed that many of them had already moved several times in the last months. As soon as the situation deteriorated to an extent that they felt unsafe they moved some miles to a village out of shelling range and stayed there, still having the opportunity to return occasionally to collect assets or work on the paddy fields. Generally, the majority of the IDPs moved nearer to the coast and then further to the North as the security situation worsened and rumours of continued fighting spread out. There is also a likelihood that after the end of the harvesting season, there will be a further movement to the North.

## 3.	HUMANITARIAN ORGANISATION'S STRATEGY

### 3.1.	Partner's strategy in country and/or region(s) of operation

###### Brief History

CARE International has been operating throughout Sri Lanka since 1950. At that time and for the next three decades CARE in Sri Lanka focused on food related programmes and maternal and child health issues to respond to the most immediate and basic needs of the communities. During the 1980s, CARE’s programme was diversified in response to the changing needs of the country and the organisation’s wider objective of poverty alleviation. Projects focused mainly on the areas of Agriculture and Natural Resources Management and Small Economic Activity Development. The second focus of CARE’s work was Relief and Rehabilitation activities in response to the needs arising through the protracted civil war. Since the second half of the 1990s, CARE’s projects have been aiming at improving Household Livelihood Security of families affected by the on-going conflict, plantation workers, small-scale farmers and other rural poor.

### General intervention strategy

Each CARE programme and project embodies six fundamental principles:

- Promote Empowerment - We stand in solidarity with poor and marginalised people, and support their efforts to take control of their own lives and fulfil their rights, responsibilities and aspirations.  We ensure that key participants and organisations representing affected people are partners in the design, implementation, monitoring and evaluation of our programmes.

- Work with Partners - We work with others to maximise the impact of our programs, building alliances and partnerships with those who offer complementary approaches, are able to adopt effective programming approaches on a larger scale, and/or who have responsibility to fulfil rights and reduce poverty through policy change and enforcement.

- Ensure Accountability and Promote Responsibility - We seek ways to be held accountable to poor and marginalised people whose rights are denied.  We identify individuals and institutions with an obligation toward poor and marginalised people, and support and encourage their efforts to fulfil their responsibilities.

- Address Discrimination - In our programs and offices we address discrimination and the denial of rights based on sex, race, nationality, ethnicity, class, religion, age, physical ability, caste, opinion or sexual orientation.

- Promote Non-violent Resolution of Conflicts - We promote just and non-violent means for preventing and resolving conflicts at all levels, noting that such conflicts contribute to poverty and the denial of rights.

- Seek Sustainable Results – As we address underlying causes of poverty and rights denial, we develop and use approaches that ensure our programmes result in lasting and fundamental improvements in the lives of the poor and marginalised with whom we work.

### Current activities

Building sustainable rural livelihoods

Projects under this programme assist rural households in securing their livelihoods and improving living conditions through integrated approaches covering the full spectrum of agriculture-related activities, from pre-production planning to the introduction of adequate post-harvest technologies and the support in marketing of products. Project interventions emphasise on linking farmers to appropriate extension and information services and strengthening the capacity of local representative structures in order to improve service provision to households.

The Plantation Programme

For centuries, workers on plantations, such as the vast tea estates, have been marginalised, exploited and have been denied adequate integration into the society of Sri Lanka. CARE’s projects operating in this sector work towards building an atmosphere of trust and co-operation and to open and enforce channels of communication between residents and management, enabling both parties to jointly define their problems as well as potential solutions.

##### The North and East - Conflict affected areas

In response to the immense suffering and the overwhelming needs of both the families directly affected by the civil war, such as Internally Displaced Persons (IDPs), as well as the communities hosting IDPs and suffering from the unstable political situation, CARE has been giving special attention to its programme in the Northern and Eastern part of the country during the past decade. Projects under this programme always aim at addressing needs along the whole continuum from relief to rehabilitation and finally development activities. Activities support families in re-building their livelihoods and strengthening the capacity of government actors, and NGOs as well as Community Based Organisations (CBOs) to better address communities’ needs.

The Tsunami Response

CARE’s Tsunami response strategy was designed as a long term intervention mainly focusing on the reconstruction of houses, the rehabilitation of livelihoods and capacity building. CARE is even two years after the Tsunami struck the coast of Sri Lanka, active in rehabilitation and development projects for the affected population in the South, East and the North of Sri Lanka. In the framework of the Tsunami response also neighbouring communities affected by the conflict and living in chronic poverty receive assistance in rebuilding their lives.

CARE International Deutschland has been supporting the implementation of projects in Sri Lanka continuously since 1997. The European Commission, the German Ministry for Economic Co-operation and Development as well as the German Federal Foreign Office projects supported or are currently supporting the implementation of projects in the field of relief and rehabilitation in conflict affected areas as well as such aimed at the improvement of rural livelihood.

ECHO has been supporting CARE’s activities in the conflict affected areas of Sri Lanka since April 2003.

### 3.2.	Link between operation, the findings of the assessment and the problem
statement

With the proposed intervention, CARE will address the main problems identified in the assessment:

1. Non Food Relief Items (NFRIs)

CARE plans to distribute different NFRI kits, the composition will be decided upon the needs in the intervention area and in close coordination with other agencies providing assistance to ensure complementarities and avoid duplication. According to the findings of the assessments, it has been planned to provide four different NFRI sets. The first one will contain more durable items as bed sheets, plastic mats, towels, mosquito nets etc. The second set will include hygiene items that need to be replaced after a certain time as they are consumables such as tooth paste, sanitary napkins, soap etc. The third set will address the special needs of infants. A fourth set will be addressing the needs of the most vulnerable of the host families, supporting them with buckets, kitchen utensils etc.

The distribution will focus on these areas having the greatest need, currently identified as being in Manthai West, but as elaborated before, this could change depending on a whole range of factors: development of the conflict, assistance provided by other agencies, access and security issues. Since the hand out of items is always accompanied by security problems, rigid procedures will be put in place to provide the utmost safety to the CARE staff. Monitoring of the distribution will be tight so that abuse of the assistance will be avoided.

2. Water and Sanitation

The assessment has revealed that in the LTTE controlled areas as well as in the Government controlled areas of the Mannar District, there is scarcity of potable water due to the salinity of most water sources. Therefore, CARE is planning to provide water tanks and organise water bowsers to refill the tanks. Even though it is clear that this can be only a temporary solution, it accommodates the urgency of the assistance as well as the volatile and fluid environment.

- Latrines: As already outlined above, the resident population as well as the IDP population do not have access to latrines. It is considered essential that whenever temporary shelter is provided it is accompanied by the set up of latrines. Especially if more than one family is staying in one place. However, CARE had to make strategic choices in the framework of the proposal at hand and decided not to include the construction of temporary toilets mainly because of the restricted resources. This however does not mean that CARE’s target villages will not be provided with sanitary facilities in fact the emergency response in Mannar District is and will be a combined effort of all agencies which complement each others resources and capacities.

3. Temporary Shelter

In the framework of the proposed intervention, CARE is also planning to address the needs for temporary shelter prevalent in the target area as outlined above. In close coordination with the public authorities, other agencies, host communities and IDPs, cadjan shelters will be provided to the IDPs in the Government as well as LTTE controlled areas on the land of the host families or common land.

4. Emergency Preparedness Training

Since CARE strives for a strengthening of local coping mechanisms to external shocks, and taking into account that the first response is always done without any outside assistance, it is planned to conduct Emergency Preparedness Trainings for CBOs and other local organizations to better plan for the eventuality of an emergency situation. In the framework of the last ECHO funded project, these trainings and the set up of emergency preparedness committees proved to be very effective as they were able to respond immediately to the displacement that took place at the beginning of September.

### 3.3	Is/are there similar operation(s) in the country/region?

If yes, explain the measures foreseen to avoid overlap/duplication

Since CARE is currently implementing in the Mannar District an ECHO funded project (project ended on 31st August 2007 and is currently being wrapped up) CARE is familiar with all the stakeholders in Mannar District and is taking part in the formal coordination body for NGOs established by the GA which takes place on a weekly basis. All assistance provided in the Mannar District has to be reported to the GA. Additionally, UNHCR is chairing an interagency meeting which is held on a daily basis, updating and coordinating the assistance provided mainly in welfare camps. The Consortium of humanitarian agencies (CHA) is chairing weekly meetings of all local and international agencies in Mannar District, coordinating the assistance provided to IDPs accommodated in host communities.

Moreover, coordination meetings take place in Killinochi of the agencies based in the LTTE controlled areas. The CARE team in Mannar thus closely coordinates and liaises with its Killinochi office.

Several agencies are involved into emergency relief activities in Mannar District. During the first weeks of September 2007, individual villages were allocated to certain agencies which were then in charge for organizing the response to the needs in their respective focal areas. Every agency had to coordinate its assistance with the agency that had taken on the responsibility for the respective area. Thus, the highest degree of complementarity could be achieved and gaps easily identified. Furthermore in the last years close relationships with all NGOs working in that area have been established.

### 3.4.	Previous humanitarian operations with EC grants in the country/ region

Immediate relief assistance for tsunami affected communities in Mullaitivu and Kilinochchi districts

This ECHO funded project was implemented to provide immediate and short-term relief assistance to families and individuals displaced by the Tsunami in Mullaitivu and Kilinochchi districts in order to cover their immediate needs.

Relief Assistance for Mullaitivu District, Wanni Region

The successor project to “Relief Assistance for Wanni Region” it also aims at sustainably improving the health and nutritional status of resettling/internally displaced and host families.

Relief Assistance for Wanni Region

This intervention served to rebuild livelihoods and effect sustainable improvements in the lives of resettling families in the Wanni region. Working in 80 instead of 30 villages, as originally envisaged, the intervention helped to sustainably improve the health and nutritional status of needy communities through the construction and rehabilitation of wells, the construction of latrines, as well as the provision of agriculture and fishing inputs.

RAPID I and II

The overall objective of the projects “Rehabilitation Assistance for Internally Displaced – RAPID I” and “Rehabilitation Assistance for Internally Displaced – RAPID II” funded by the European Commission and implemented in Sri Lanka between 01/98-01/99 and 11/99-03/02, respectively, was to assist IDPs living in 5 districts, which were controlled by the government, but nevertheless heavily affected by the civil war. Through the project’s activities, vulnerable women and children were especially targeted. RAPID II and I substantially improved the delivery of services to IDPs in a range of sectors through government agencies, NGOs and grassroots CBOs. Both projects consistently followed participatory approaches in order to increase the communities’ active participation in developing micro-projects from design through implementation up to post-project maintenance. Based on needs identified by the individual organisations, capacity building for the above-mentioned service providers was specifically targeted to the areas of participatory needs assessments, Design, Monitoring and Evaluation (DME), as well as reporting and financial management. During RAPID I, CARE partnered with 34 organisations for 71 micro-projects, while during RAPID II a total of 83 partner organisations implemented 150 micro projects assisting over 10.000 households.

“AFIDACAH”

The primary goal of the EC Funded “Assistance For Internally Displaced and Conflict Affected Households” (AFIDACAH) Project was to extend feasible support to the IDPs and other vulnerable groups affected by the civil war in Sri Lanka. The twenty-year-long civil war has resulted in cumulative loss of more than 80,000 lives and the displacement of 1.5 million people in Sri Lanka. In addition, the civil war has caused enormous damage to the infrastructure as well as the social, economic and cultural fabric of the Northern and Eastern provinces.

“Rehabilitation Support to Tsunami Victims in Mullaitivu District, Wanni Region, Sri Lanka“

The project was designed in contribution to recovery and rehabilitation of tsunami affected population in the Mullaitivu district.

“Aid to uprooted people (UPWARD)”

With this project CARE seeks to substantially contribute to the project’s overall objective, namely to ensure that uprooted people in five conflict affected districts of Sri Lanka are successfully reintegrated and their livelihoods and human rights secured. Approx. 47,250 direct beneficiaries in 9,450 households, among them many female headed, are expected to directly benefit from the project. Especially the support for institutional development of Community Based Organisations (CBOs) will empower whole communities, so that the whole communities in the DS divisions CARE will work in will indirectly benefit from the project. Recognising the multidimensional nature of reintegration, hardware assistance to increase access to safe water and sanitation facilities and support for agricultural and off-farm income generation activities will be coupled with capacity building and the implementation of peace-building and reconciliation initiatives to set the bases for long-term peaceful development.

“Support to Internally Displaced Persons (IDPs) and host families in Mannar District, Sri Lanka”

CARE implemented in the first eight months of 2007 an ECHO funded project in the Government controlled areas of the Mannar District aimed at the improvement of living conditions of both IDPs and host families affected by the recent deterioration of the conflict. Main components of the intervention were livelihood activities, provision of access to safe water and sanitation facilities, training on crucial health issues as well as establishing Village Emergency Preparedness Committees. The now proposed intervention will draw on the lessons learnt and experiences of the prior ECHO funded project.

### 3.5.	Have you discussed this proposal with ECHO's technical assistance office in 
the country/region of operation?

Yes X		No 

Comments:

CARE maintains frequent communication with the ECHO representatives in Colombo and in Brussels.

## 4.	OPERATIONAL FRAMEWORK

  - Title of the operation

“Emergency Relief to Internally Displaced Persons (IDPs) and host communities in conflict affected areas, Sri Lanka“

  - Country(ies) and location(s) of implementation

Following the deteriorating security situation and the subsequent displacement of thousands of families in Mannar district the proposed intervention will be implemented in the areas of the northwestern district under control of the government and to a greater extent those under the control of the LTTE. CARE will assist the displaced families and their host communities and address the most pressing needs in close coordination with all relevant public authorities and international and local agencies. At this point in time, Manthai West DS division (LTTE controlled) and Nanattan DS division (Government controlled) and Mannar DS division (Government controlled) have been identified as the areas with the highest number of displacement and the direst needs for immediate assistance. However, the areas of intervention might change as the people may move further away from where the fighting takes place. Thus, the proposed intervention might shift to other DS divisions of Mannar District or adjacent districts as Killinochi and Mullaitivu.

| Manthai West DS Division (LTTE controlled) | Nanattan DS Division (Government controlled) | Mannar DS Division (Government controlled) |
| --- | --- | --- |
| Villages | Villages | Villages |
| 1. Illuppakadavai | 1. Kovvankulam | 1. Keeri |
| 2. Paliaru | 2. Mooddakkadai | 2. Thottavely |
| 3. Vellankulam | 3. Pallankottai | 3. Ollathoduva |
| 4. Koori | 4. Valkkaippattankandal |  |
| 5. Athimottai | 5. Kattakadu |  |
| 6. Periyamadhu | 6. Ponthivukandal |  |

Should the security situation in Mannar deteriorate to an extent that CARE can not remain operational, CARE would work with the ECHO representatives in Colombo to implement planned or alternative activities in an alternative location in the north or east of the country.  Due to the extreme fluidity of the current situation, the exact area will be specified only when the scenario occurs and the subsequent decision will be based mainly on the needs of the IDPs and host families and the security threats prevailing in possible intervention areas.

  - Start date of the operation:	15 October 2007

  - Duration in months:			8 Months

4.5.      Beneficiaries

4.5.1.   Total number of direct beneficiaries:

| Target Area | Villages | IDP families | Host families | Total No. of persons |
| --- | --- | --- | --- | --- |
| Manthai West | 6 | 1,169 | 200 | 5,476 |
| Nanattan | 6 | 300 | 300 | 2,400 |
| Mannar Town | 3 | 140** | 100 | 960 |
| TOTAL | 15 | 1,609* | 600*** | 8,836**** |

*Please note that the IDP numbers provided by the GA are somewhat higher than the numbers mentioned in this table. The above quoted figure has been provided by UN OCHA after an assessment mission conducted on 17th September 2007. Additionally, displacement is ongoing, new families continue to arrive which makes data inaccurate.

**Please not that the IDPs in the three selected villages are currently being relocated from the welfare camps in Murunkan and are expected to arrive at the time of the proposal writing

***The exact number of host families which will be supported can not be specified as yet, but the water activities will also be of benefit to numerous host families as well as the emergency preparedness activities

**** The average family has four members

Please note that the number of beneficiaries is already disaggregated. At this point it can not be exactly specified how many beneficiaries benefit from more than one project component. All the people currently residing in the project area will benefit from the hygiene training, the emergency preparedness trainings and the improved access to safe water.

4.5.2.   Identify the status and give details of the beneficiaries

CARE will target with the proposed intervention six villages in Manthai West DS division, six villages in Nanattan DS division and three villages in Mannar DS division. The rational for targeting these villages is the number of recently displaced IDPs, the vulnerability of the people and the assistance received so far. Since the relief effort is currently ongoing, the locations may change in case the villages will be assisted by other agencies or in case of further population movement. The majority of the IDPs are currently staying in common buildings, with host families or in small gatherings out in the open, seeking shelter under trees or tarpaulin sheets. Most pressing needs are food, shelter, safe water and a range of NFRIs.

Approximately 1,169 IDP families will directly benefit from the provision of safe water. Depending on the respective context, the resident population will also benefit from the water provision. Moreover, the hygiene promotion as well as the awareness raising and prevention campaign against endemic diseases will target the IDP and host population in the selected villages. 370 IDP families will be provided with temporary shelter facilities. The same number will be provided with the most essential NFRIs identified for an eight month period. For the clothing needs CARE will coordinate with other specialised agencies for an adequate coverage. The number of IDP families benefiting from the NFRI component is most likely to increase as NFRI assistance is ongoing since the escalation of conflict in the intervention area but as yet patchy and on an ad hoc basis. Therefore, CARE will address NFRI needs wherever gaps have been identified. Hence, it is anticipated that the entire package is not required in all cases.

Special attention will have to be given to particular vulnerable parts of the IDP population such as pregnant women, lactating women, female headed households, mentally and physically disabled persons and unaccompanied children and elderly. A rapid assessment in Manthai West comprising more than the selected villages has shown that the above mentioned vulnerable groups are amongst the IDP population in a considerable number.

    - "Catchment" population

The overall population will partly benefit from the provision of water facilities and hygiene training as well as the emergency preparedness activities.

    - What are the identification mechanisms and criteria?

Beneficiaries will be those who are recently displaced because of the deteriorated security situation. Lists from the GN and DS indicating the number and location of IDPs will be verified by the CARE team. The level of vulnerability will be taken into consideration e.g. female headed households, disabled, elderly, number of children and so forth. The overall number of family members as well as the resources to their disposal will be taken into account as well. Some host families might be selected according to their degree of vulnerability. As we have gathered abundant experience on working with partners in the area, we have decided to work through CBOs where feasible but to monitor closely in order to ensure that the most vulnerable will benefit from our intervention. Moreover, the beneficiaries will have the opportunity to complain if there is any kind of bias in favour of the more powerful and affluent. Even though there is no procedure formalized yet, three venues for complaining will be established: 1. Committees for addressing the complaints will be established on different levels of the project. 2. Complaints box will be attached to a village information board. 3 Complaint telephone numbers will be provided. Any person, household, group or organization and project staff and counterparts can complain against CARE, the project, CARE staff, counterpart staff from the government and project suppliers involved in this intervention.

    - To what extent and how were the beneficiaries involved in the design of 
the operation?

In order to strengthen the existing social structures, CARE interviewed the villagers and also consulted with community leaders and district authorities as already outlined under paragraph 2.2. and also included the IDP families. The strategies and priorities proposed for this operation have been discussed at length with all relevant partners and beneficiaries to ensure a maximum adequacy and feasibility.

4.5.6.	Sectors of activity

- Sector 1:	Provision of NFRIs

One time Distribution of a set of NFRIs comprising durable items such as bed sheets, towels, plastic mats, family mosquito nets, plastic buckets etc. to 330 IDP families

Two monthly distributions of NFRI kits containing essential hygiene items such as soap, sanitary napkins, and tooth paste etc. to 350 IDP families over an 8 month period

Two monthly distributions of special infant NFRI kits to 150 IDP families over an 8 month period

One time distribution of essential NFRI items to ca. 30 vulnerable host families

These activities will be carried out in consultation with other agencies in order ensure maximum benefits to the target families.

- Sector 2:	Water

Hiring of 2 Water bowsers to deliver safe drinking water to 12 IDP’s and vulnerable host communities (estimated 90,000 litres / day) for 8 months period

Wherever feasible, existing water sources are cleaned and/or repaired

Construction of 60 Water storage points (2,000ltr.) in vulnerable IDP and host communities.

15 health and hygiene campaigns, posters and meetings organised.

- Sector 3:	Temporary Shelter

Provision of temporary shelter to 287 IDP families

- Sector 4: Emergency Preparedness

15 trainings and 15 visits to build knowledge and awareness of preparedness issues.

4.5.7.	Give the following information for each sector

- Total number of direct beneficiaries:	1,169 IDP families and host families

- Types of beneficiaries and number of beneficiaries per type

1. NFRIs – 330 IDP families and 30 host families

2. Water – 1,169 IDP and additional host families, training on hygiene may cover additional families

3. Shelter – 287 IDP families will be provided with temporary shelter

4. Emergency preparedness – 1,169 IDP families and additional host families

  - Principal objective

To ensure IDPs and conflict affected communities in Northern Sri Lanka are receiving adequate and integrated humanitarian assistance.

    - Specific objective

To improve living conditions of IDPs and host communities in conflict affected areas, Sri Lanka

    - Indicators and sources of verification

Indicators:

- 330 IDP families and 30 host families have received essential NFRI items.

- 1,169 IDP families have access to safe water and improved awareness of hygiene and sanitation issues

- 287 IDP families’ temporary shelter needs are met.

- 15 communities have been trained in EPP/DRR

- CARE response meets Sphere common standards and incorporates best practise in HAP feedback mechanisms

Sources of Verification

- Final project report

- Baseline survey/assessments at project start

- Project Monitoring and evaluation report

- Official documents from local authorities

### 4.8.	Results and Indicators

4.8.1. Expected result #1

#### Increased access to essential NFRI for target IDP and host families

#### Indicators:

- 350 IDP families have sufficient personal hygiene items for an eight month period

- 330 IDP families have access to cooking and eating utensils

- 30 vulnerable host families have sufficient essential NFRIs

- 287 IDP families have sufficient tools and equipment for maintenance and safe use of their shelters (e.g. mosquito nets)

- 330 IDP families have sufficient infant NFRIs for 8 months

- Monthly (or every 2 months) distributions take place in a manner that ensures active participation and appropriate targeting

Sources of Verification

- Final project report

- Baseline survey/assessments at project start

- Project Monitoring and evaluation report

- Official documents from local authorities

4.8.2. Expected result #2

#### Increased access to, use and awareness of safe water and hygiene issues

#### Indicators:

- 2 Water bowsers delivering safe drinking water to 12 IDP’s and vulnerable host communities (estimated 90,000 litres / day) for 8 months period

- 60 Water storage points (2,000ltr.) constructed in vulnerable IDP and host communities.

- Rehabilitation possibilities of existing water sources explored and carried out when feasible

- 1 bowser for three month period delivering according to the need

- 15 health and hygiene campaigns, posters and meetings organised.

Sources of Verification

- Final project report

- Baseline survey/assessments at project start

- Project Monitoring and evaluation report

- Official documents from local authorities

4.8.3. Expected result #3

#### Increased access to shelter facilities

#### Indicators:

- 287 IDP families have received temporary shelter items.

- 287 temporary shelters are located in hazard free environments

Sources of Verification

- Final project report

- Baseline survey/assessments at project start

- Project Monitoring and evaluation report

- Official documents from local authorities

4.8.4. Expected result #4

Communities have increased awareness and capacity to deal with impact of conflict

##### Indicators:

- 15 trainings and 15 visits to build knowledge and awareness of preparedness issues.

Sources of Verification

CARE monitoring reports

#### 4.9.	Activities

4.9.1. Distribution of Non Food Relief Items (NFRIs)

CARE is planning to distribute four different NFRI kits in Manthai West (LTTE controlled), Nanattan DS division and Mannar DS division.  The overall amount allocated for NFRIs is 21,000 EUR and it has been estimated that the NFRI needs (except for clothing) of 330 IDP families can be met for an eight months period. It has been planned that a package containing more durable items such as mosquito nets, towels, mats, bed sheets, buckets, kitchen utensils will be distributed once at the beginning of the project. 10,900 EUR have been allocated for that package. The hygiene kit will be distributed every two months as it contains consumables that are envisaged to be exhausted after two months. Four distributions will be carried out for which 8,000 EUR are allocated. An infant kit will be distributed in the same way to 150 IDP families (estimated cost 2,100 EUR). For planning purpose the reach out has been based on the assumption that the target groups did not receive any NFRI assistance as yet. The rapid assessments however have shown that NFRIs have been provided already by different agencies though by far not covering all the needs. Therefore, CARE will compile the NFRI kits according to the actual needs and address the gaps in NFRI assistance. Thus it is anticipated that the number of IDP families benefiting from the NFRI distribution will increase.

It is foreseen to provide NFRIs mainly to the IDPs in Manthai West as the need is considered to be higher. However, the items will be distributed strictly according to the existing needs and will also take into consideration the most vulnerable families in the host communities (but the ratio will be no less than 1 (host family) to 10 (IDP families)), thus the distribution might also cover villages in Nanattan DS division and Mannar DS division.

- NFRI needs assessment

- Purchase, transport, storage

- One time distribution of durable NFRI kits

- 2-Monthly distribution for eight months of NFRI kits that contain consumables

4.9.2. Water

According to the findings of the rapid assessments in Manthai West in all but one location there is not sufficient potable water available to the IDP families. Manthai West is generally an area that is facing water shortage and salinity of water sources. With the influx of IDPs into the areas, additional provision of potable water becomes crucial. Depending on the local context and available water sources (e.g. saline water can be used for washing and cleaning), an average of 5 water tanks per village will be provided. The distance of the target group to the nearest water tank shall not be more than 500m. If no other water source (saline) is available the tank shall provide a minimum of 15 litres the day per person using the tank. If other sources are available, the water provided shall not be less than 7 litres the day. Sufficient tabs (preferable not attached to the reservoir) will decrease the time needed for filling containers and some training will be provided in maintenance and minor repairs as well as awareness in case the tanks are supposed to cover only the need for potable water. The tanks will be refilled by hired bowsers on a daily basis for eight months. 12,000 EUR have been allocated for the purchase of 60 tanks with a capacity of 2,000 or 1,000 litres depending on the circumstances. For the bowsering 18,200 EUR have been allocated, covering the daily refilling of 6 project villages in Manthai West. Depending on the existing gaps and available resources, CARE may provide the bowsering service also in the government controlled areas of the Mannar District.

In some areas of Manthai West, the cleaning and repair of existing water sources may be an option that will be considered as it is a more sustainable solution going beyond the implementation period. Even some of the wells that will be used as water sources for the bowsering might need some minor repair and cleaning.

As mentioned before, water storage will require periodic maintenance by the community (at least every two weeks).  Water quality monitoring is crucial and chlorination (this will require consent, approval from authorities and awareness from community as this is a public health issue. This will further require technical specialist and need proper training of operators from the community) or the promotion of water boiling may be required and will be part of the planned hygiene promotion.

A water quality monitoring system will be developed taking into account the area, size of the community, water source and water quality. Sources of water quality deterioration could be at the well, the storage tank and eventually at the household level thus all three possible places of contamination will be part of the monitoring system. The community will take part in the water quality monitoring for sustainability and awareness purposes (water user committees).

Hygiene promotion will be carried out directly by CARE or in close coordination with other agencies engaged in Water and Sanitation. As woman and children are those family members who are responsible for the water collection, they will be specifically targeted for the hygiene promotion. Water and sanitation issues but also general health risks predominant in the area (as Chikungunya, Malaria and Dengue) and how to minimize the vulnerability will be part of the training.

- Needs assessment

- Site identification for tank installment

- Purchase of required material

- If applicable, repair and cleaning of existing water sources

- Installation of water tanks

- Hiring of water bowser

- Training on maintenance

- establish water user committees for maintenance and proper monitoring

- hygiene promotion activities

4.9.3. Temporary Shelter

As the assessment has shown that there is a great need for shelter facilities, it is planned to provide 287 IDP families with cajan shelters. Unlike the tarpaulin tents, the cajan shelters are supposed to last much longer and provide better thermal conditions. Moreover, the beneficiaries are familiar with the cajans and have particularly asked for those. In Manthai West cajan has to be brought in from Mullaitivu whereas in Nanattan and Mannar DS division cajan is easily available. Depending on the local context shelter will be provided on land allocated by the authorities or on the land of the host families. 57,400 EUR have been allocated for temporary shelter. The provision of shelter is very urgent as the rainy season is up to start very soon which will cause huge hardship for those people that are currently staying out in the open or under trees without any protection.

- Shelter needs assessment

- Site identification and preparation

- Purchase and transport of material

- Set up of temporary shelters

4.9.4. Emergency Preparedness Training

Drawing on the experiences of the prior ECHO funded project in Mannar District, CARE is planning to further improve the functioning of the Emergency Preparedness Committees which have been established already and which took on the responsibility to respond first to the latest displacement in their respective communities. Additionally, it has been planned to provide some training to CBOs in Manthai West in preparing plans for the case of an emergency.

- Identification of appropriate partners

- Training and awareness on emergency preparedness planning

- Strengthening of the coordination mechanisms

Others

- Data collection and establishment of a list of beneficiaries

- Participation in coordination bodies on national as well as district level

- Reconfirmation of collected data and consolidation of data with other organizations operational in the are

- Submission of final report

#### Work plan

| ACTIVITIES | Oct '07 | Nov '07 | Dec '07 | Jan ‘08 | Feb '08 | Mar '08 | Apr '08 | May'08 | June ‘08 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sector 1: NFRIs |  |  |  |  |  |  |  |  |  |
| NFRI needs assessment | X |  |  | X |  |  | X |  |  |
| NFRI purchase | X |  |  | X |  |  | X |  |  |
| NFRI distribution government controlled areas | X | X | X | X | X | X | X | X |  |
| NFRI distribution in LTTE controlled areas | X | X | X | X | X | X | X | X |  |
| Sector 2: Water and Sanitation |  |  |  |  |  |  |  |  |  |
| Identification of water sources needing rehabilitation | X |  |  | X |  |  | X |  |  |
| Rehabilitation of water sources if possible (Cleaning, repairing of wells) | X | X |  | X | X |  | X | X |  |
| Provision and set up of water tanks | X | X |  | X | X |  | X | X |  |
| Water bowsering | X | X | X | X | X | X | X | X |  |
| Background study regarding water table, nearest water sources, agreement on the location with beneficiaries | X | X |  |  |  |  |  |  |  |
| Sector 3: Temporary Shelter |  |  |  |  |  |  |  |  |  |
| Site identification and beneficiary consultation | X | X |  |  |  |  |  |  |  |
| Construction of temporary shelter | X | X | X |  |  |  |  |  |  |
| Sector 4: EPP training |  |  |  |  |  |  |  |  |  |
| Partner selection | X | X |  |  |  |  |  |  |  |
| Training on EPP issues |  | X | X | X | X | X | X |  |  |
| Others |  |  |  |  |  |  |  |  |  |
| Establish a coordinating Mechanism with other agencies | x | x | x |  |  |  |  |  |  |
| Data collection and establishment of a list of beneficiaries | x | x |  |  |  |  |  |  |  |
| Reconfirmation of collected data and consolidation of data with other organizations operational in the area | x | X |  |  |  |  |  |  |  |
| Staff Training / prep. project implementation planning- in Detail | x |  |  | x |  |  | x |  |  |
| Establishing community committees / Preparation of Community Emergency preparedness plan |  | x | x | x | x | x | x | x |  |
| Preparation of donor reports |  |  |  | x |  | x |  | x | x |

#### 4.11.  Monitoring, evaluation and external audit

4.11.1. Monitoring

As in all of CARE’s projects, monitoring and evaluation will be a critical and integral part of the operation. Data concerning the identified indicators will regularly be collected by the project staff. The intervention’s progress will periodically be reviewed hence possible bottlenecks can be identified at an early stage and adjusting measures can be undertaken to ensure that the results of the operation will be achieved. CARE will report to ECHO as per ECHO’s reporting requirements.

A Programme Officer of CARE International Deutschland has been seconded to CARE Sri Lanka. He will closely monitor the project and provide assistance whenever necessary.

4.11.2. Evaluation

- Is an evaluation foreseen during the operation?

Yes 		No X

- Is an evaluation foreseen after the operation?

Yes  		No X

4.11.3. External audit

- Is an audit foreseen during the operation?

Yes 		No X

- Is an audit foreseen after the operation?

Yes  		No X

## 5.	RISKS AND ASSUMPTIONS

### 5.1.	Pre-conditions

### 5.2.	Assumptions and risk assessment profile

### Please refer to the attached logical framework.

### 5.3.	Security

    - Situation in the field

## The situation on the ground is very volatile as the Mannar District is partly under the control of the LTTE. Isolated incidents of killings, claymore and grenade attacks, abductions and disappearances occur on regular basis in the government controlled areas. Violence is expected to increase as the government tries to force the LTTE out of the area.  A particular flashpoint for violence remains the territory between LTTE and government controlled areas. The LTTE controlled areas are subject to aerial bombing and artillery attacks by the Sri Lankan Army.

## At least one non-state paramilitary group aside from the LTTE is known to be active in Mannar.

    - Have you established a specific security protocol for this operation?

Yes	X	No		Standard procedures	

CARE has taken measures to increase its communications capability to support activities in Mannar district.

A “safe house’ has been arranged in the uncleared areas to allow staff to seek safety in the event that the FDL closes suddenly and they are unable to return safely to Mannar town. The safe house has back up communications that will allow staff to establish contact with base and there are food, water, and first aid supplies readily available. Medical assistance is available at a nearby clinic and for more serious cases MSF Spain has staff at Periyamadu hospital.

5.3.3.	Have you a specific plan for security-related and medical evacuations 
for this operation?

Yes	X 	No	

If yes please elaborate:

Medical and security evacuations can be carried out either through the FDL to Mannar or via Malawi (where CARE has an emergency sub office) to Killinochchi. The government and the LTTE facilitate crossing the FDL for emergency medical reasons.

5.3.4.	Are your field staff and expatriates informed of and trained in these 
procedures?

Yes X		No 	

## 6.	RESOURCES REQUIRED

### 6.1. 	Total budget (point 11.1.)

€ 250,000

### Human resources

6.2.1.	Staff included in Title 1: “Goods and services delivered to the beneficiaries”

Expatriate Staff

No expatriate staff has been foreseen for this position.

Local Staff

A local operations manager will assume the overall responsibility for the implementation of the proposed operation. He will furthermore co-ordinate project activities with the interventions of other organisations as well as with the relevant public authorities. He will be responsible for the networking with partnering institutions, and ensure proper reporting and accounting in collaboration with the financial staff of the CARE Colombo office.

Four Project Co-ordinators will be employed in the project. One of them has in-depth field experience in water and sanitation programming.

Four Project Officers and two Project Assistants will liaise with the local communities and villages, organise labour, and oversee field activities.

6.2.2.	Staff included in Title 2: “Support costs”

Expatriate Staff

The Country Director, the Assistant Country Director Programme, the Assistant Country Director Programme support as well as the financial controller will be charged each 2% as they provide crucial support to all projects run by CARE Sri Lanka.

Local Staff

One administration assistant, one finance officer, one information coordinator (M&E), one procurement assistant, five drivers (due to the security protocols), one custodian and two guards will be required for the operation. Furthermore, a minor percentage of the support staff in the Colombo headquarters will be charged to the project as it provides essential service to the projects and therefore a share has to be covered by all projects run at the same time.

### 6.3.	Material resources

    - Equipment needed. Describe the procedure to be followed for the procurement of equipment. N/A

6.3.2.	Goods to be purchased. Describe the procedure to be followed for the awarding of contracts.

No durable goods will be purchased in the framework of this operation.

| Item | Total amount in EURO | Procurement procedure |
| --- | --- | --- |
| Bed sheets |  |  |
| Towel |  |  |
| Plastic mats |  |  |
| Family mosquito nets |  |  |
| Baby mosquito nets |  |  |
| Plastic buckets |  |  |
| Kitchen utensils |  |  |
| Plastic file |  |  |
| Back pack |  |  |
| Water container |  |  |
| Rubber slippers |  |  |
| Lantern |  |  |
| Laundry soap |  |  |
| Bathing soap |  |  |
| Tooth paste |  |  |
| Sanitary napkins |  |  |
| Baby soap |  |  |
| Baby powder |  |  |
| Total NFRIs | 21,000 | If all items can be purchased together: Negotiated procedure. In case the total value of the contract is less than 5,000 EUR then single quote |
| 9’ Timber Post | 6,730 | Single Quote |
| 12’ Timber Rafter | 6,416.67 | Single Quote |
| 12’ Timber Bean | 5,833.33 | Single Quote |
| Reapers (Varichu) | 1,963.14 | Single Quote |
| Cadjan | 12,620.19 | Single Quote |
| Wire nails | 336.54 | Single Quote |
| Gravel and Clay (flooring) | 10,096.15 | Negotiated Procedure |
| Clay (block) | 4,262.82 | Single Quote |
| Coir rope | 925.48 | Single Quote |
| Rubber coir | 302.88 | Single Quote |
| Erku | 336.54 | Single Quote |
| Skilled work | 3,365 | Single Quote |
| Unskilled work | 7,852 | Single Quote |
| Total for cadjan shelter (including transport) | Ca. 57,400 |  |
| Water tanks | 12,000 | Negotiated procedure |

CARE kindly asks for the permission to purchase the timber post, the timber rafter, the timber bean and the cadjan on the basis of a single quote. The reasons for this request are the urgency of the shelter provision (before the rainy season starts), the restrictions on material transport into the LTTE controlled areas and the lack of local vendors.

Kindly note that the estimation is an average indication and that there will be considerable deviation according to the area. Activities in the LTTE controlled area will be more expensive.

Estimated cost per basic NFRI kit: Euro 30

Estimated cost per hygiene NFRI kit: Euro 7

Estimated cost per infant NFRI kit:  Euro 3.5

Estimated cost per water tank (including base and transport): Euro 200

Estimated cost per water bowser: Euro 1,000 (for one month period)

Estimated cost per cadjan shelter (including transport): Euro 205

The procurement of materials will be undertaken by CARE. CARE will identify suppliers for each of these activities to facilitate timely procurement and achieve reasonable prices for materials and inputs. CARE’s internal procurement guidelines fully comply with ECHO’s procurement stipulations.

CARE kindly asks for derogation to the rule of origin and nationality for the procurement of equipment, goods and services.

6.3.3.	If the operation requires the purchase of medicines and/or medical equipment: Do you have standard procedures for the purchase, handling and storage of these medicines/equipment? N/A

Yes 		No 

Please specify:

## 7.	PERSPECTIVES OF THE HUMANITARIAN ORGANISATION IN TERMS OF 
LINKING RELIEF, REHABILITATION AND DEVELOPMENT

### 7.1.	This (or similar) operation is under way since 2000

### Describe the expected level of sustainability – various elements of the programme seek to improve living conditions and awareness for IDPs – this should ensure support also for their future.  Some effort will be invested into the establishment of proper coordination channels and bodies between Mannar and Killinochi.

### Continuum strategy – this proposal is self contained and all elements will be completed within the time frame.  However in the current context within Sri Lanka and the high level of displacement and potential displacement concern is that similar assistance programmes will be required in future to respond to the deteriorating situation.

## 8.	MAINSTREAMING

#### Human Rights

CARE has made a deliberate and explicit effort to focus on people realising their human rights by standing in solidarity with them. It does so by exposing the root causes of vulnerability and marginalisation and expanding its range of responses. CARE strives at empowering people, who are denied their rights, and at supporting their efforts to take control over their lives.

Gender

Gender plays an important role in CARE’s existing programs implemented in the proposed project area at present. Equal contribution as well as equal pay is promoted within these programs. The needs as expressed by males and females are taken into account and an emphasis exists on acknowledging and understanding the contribution of women to income and activities within the household.

#### Environment

#### Environmental considerations will be assessed in co-operation and co-ordination with the local authorities and government departments.

## 9.	VISIBILITY PLAN AND COMMUNICATION STRATEGY

In order to ensure an ongoing high quality in terms of visibility and communication, CARE aims for the following activities:

- CARE will publish project specific press releases in Germany highlighting the identity of the donor

- CARE International Deutschland will provide information about the project on its website www.care.de as well as establish a link to the ECHO website

- The project will be included into other forms of public information campaigns

- CARE will inform the Sri Lankan public about the project and the identity of the donor with press releases or other appropriate channels (e.g. press visit, sponsored radio talks etc.)

- Explanation to all local organisations and beneficiaries about the donor’s identity and European background.

## 10.	FIELD COORDINATION AND LOCAL IMPLEMENTING PARTNERS

### 10.1.	National and local authorities

### GA and Interagency meetings at Manner level, IASC meetings, IDP meetings, CHA and other meetings at Colombo level.

### 10.2.	Field co-ordination

### Through the above GA and interagency meetings at Manner level and by ensuring community participation in decision making. Since part of the target area is under LTTE control (Manthai West), CARE also coordinates with the relevant authorities (PDS Killinochi, PDS Manthai West)

### 10.3.	Implementing partner(s)

10.3.1.  Name and address of implementing partner(s)

CARE International in Sri Lanka

Gregory’s Road 7A, Colombo 07

Sri Lanka

10.3.2.  Role of implementing partner(s) in this operation

CARE International in Sri Lanka is responsible for the implementation of project activities, following appropriate contractual and financial procedures, and reporting to CARE International Deutschland. CARE International in Sri Lanka´s role also includes co-ordination with national and local level stakeholders, as well as the ECHO delegation in Colombo, Sri Lanka.

10.3.3.  Type of relationship with implementing partner(s)

CARE International Deutschland is a member of CARE International. CARE International consists of 12 individual CARE member organisations in Europe, North America, Australia, Japan and Thailand with CARE country offices in more than 70 countries.

Roles and responsibilities of CARE International in Sri Lanka and CARE International Deutschland are defined in project-specific implementation agreements (IPIA).

10.3.4.  History of previous collaboration with implementing partner(s)

CARE Deutschland has been supporting the implementation of projects implemented by CARE International in Sri Lanka continuously since 1997. With the support of the European Commission and the German Ministry for Economic Co-operation and Development as well as the German Federal Foreign Office projects in support of rural livelihoods as well as in the realm of relief and rehabilitation in conflict affected areas have been and are currently being implemented.

10.3.5. Name and title of the person(s) authorised to represent the implementing partner(s) with regard to this operation

Nick Osborne, Country Director CARE Sri Lanka

### 10.4.     Contractor(s) and procedure envisaged for the award of contracts

CARE International in Sri Lanka has a well developed vendor list, covering Sri Lankan, regional and international suppliers. Contracts will be awarded in adherence to ECHO’s procurement regulations.

CARE kindly asks for derogation to the rule of origin as well as the rule of nationality.

10.4.1.  Name and address of contractor(s)

Some work may be contracted out to appropriate local contractors e.g. the water bowsering.

10.4.2.  Role of contractor(s) in implementing this operation

Contractors may carry out some work on the basis of clearly defined scopes of work.

10.4.3.  Describe the procedure followed for the selection of contractor(s)

CARE will ensure that ECHO’s procurement regulations will be fully adhered to for the selection of contractors.

## 11.	FINANCIAL INFORMATION

### 11.1.	Total budget of the operation:					€ 250,000

### 11.2.	Contribution requested from European Community: 		€ 250,000

Percentage of the total amount:					100%

### 11.3.	Co-financing:

11.3.1.	Indicate your own contribution:			N/A

Contributions by other donors: 			N/A

Name:							N/A

Justification for co-financing:

### 11.4.	Pre-financing requested from European Community:	  € 125,000

Percentage of the total EC contribution:			50%

### 11.5.	Eligibility of expenditures, date:		1 October 2007

(4.3.) Start date of the operation:		1 October 2007

11.5.1. If the operation has already started explain the reason that justifies that situation:

- Primary emergency operation	

- Emergency operation			

- Other					

Please elaborate:

11.5.2. If the eligibility date of expenditure precedes the start date of the operation please justify this request

## 12.	ADMINISTRATIVE INFORMATION

### 12.1.	Humanitarian organisation’s official name, address, phone/fax n°

CARE International Deutschland e.V.

Dreizehnmorgenweg 6

53175 Bonn

Tel.: +49 228 97563-0

Fax: +49 228 975 63 51

### 12.2.	ECHO FPA number:	3-016

### 12.3.	Name and title of legal representative

Dr. Wolfgang Jamann

National Director

### 12.4.	Name, telephone, fax and e-mail of desk officer at HQ

Axel Rottlaender

Programme Officer Relief

Phone:	+49 228 9 75 63 47

Fax:		+49 228 9 75 63 51

Email:	rottlaender@care.de

### 12.5.	Name, telephone, fax and e-mail of the representative in the country of operation

Nick Osborne

Country Director

Phone: +94 11 266 2905 7

Fax: +94 11 269 3168

Email: nick@care.lk

### 12.6.	Bank account

- Name of bank: 		Deutsche Bank AG

- Address of branch: 	Kaiserplatz 5-9

53113 Bonn

- Precise denomination of the account holder: CARE Deutschland e.V.

- Full account number (including bank codes):

Bank Code: 	380 700 59

Account No.:	051012308

- IBAN account code, (or BIC country code if the IBAN code does not apply):

### IBAN code: DE36 3807 0059 0051 0123 08

## CONCLUSIONS AND PARTNER'S COMMENTS

Within the current security context in Sri Lanka support for marginalised IDP’s remains critical.   Mannar district particularly is a somewhat neglected area regarding outside assistance.  In general it is only the IDP welfare camps that receive support whilst the IDP’s who chose to remain outside relief camps (often for security reasons) are left behind almost without any help.  The host families also that offer support receive no assistance.  This inequitable distribution is causing tensions between the resident population and the IDPs living in the camps. Moreover, it is not taking into account the huge number of IDPs staying with host families.

CARE through this project aims to support the IDP’s and also improve the capacity and understanding within the host communities to support further IDP movements should they occur.   Clearly within the current context the possibility of this is high.