Emergency distribution of medicines in the Gaza Strip

Introduction

CARE in the Health sector in the occupied Palestinian territory

CARE West Bank & Gaza (CARE WBG) has been working in the occupied Palestinian territory (oPt) since 1948.

Since the start of the second Intifada (September 2000), CARE strives to improve the Palestinian population’s access to health services. Indeed, the on-going Israeli-Palestinian conflict and movement restrictions imposed to the Palestinian population by Israeli authorities in the oPt strongly hinder the Palestinians’ access to basic health care.

Since 2001, CARE implements health projects in the oPt with funds from the European Commission’s Directorate General for Humanitarian Aid (ECHO).

Currently, CARE is carrying out a project that started on the 1st of September 2007 and will end on August 31st 2008. The ECHO-funded project is tailored to facilitate access to basic health care to isolated communities in the West Bank. As such, through mobile teams, approximately 96 villages are provided with basic health care provision, which otherwise they would not receive due to the stringent movement restrictions (Wall, road blocks, checkpoints, etc.) imposed by the Israeli authorities. In addition, the project supports NGO clinics and hospitals in Gaza through the distribution of pharmaceuticals, disposables and medical equipment.

Within this project, CARE also strengthens the capacity of health professionals in both West Bank and Gaza through training on Rational Use of Medication (RUM) in partnership with Birzeit University. Finally, the capacity of health educators (from clinics and hospitals supported by the project) is also strengthened through training on topics including, but not limited to, communication skills, mother and child health care, nutrition, first aid, hygiene awareness, parasitic infections and management of chronic diseases.

Thus, since 2001, CARE has a long-term commitment towards the Palestinian population in terms of access to health services, as well as a strong expertise on this matter thanks to a highly qualified staff.

In August and September 2006, CARE France has carried out an emergency delivery of medicines in the oPt with the financial support of the Paris Municipality and the French Ministry of Foreign Affairs. Between June and September 2007, CARE carried out a similar intervention with funding from the French Ministry of Foreign Affairs.

Current health situation in the Gaza Strip

During the implementation of its ECHO funded project, CARE has witnessed the strong degradation of the health situation in the Gaza Strip and identified the urgent need to support the Central Drug Store (CDS) in Gaza with an emergency distribution of medicines.

In the Gaza Strip, the situation of the Palestinian population is continuously deteriorating. After Hamas took over the Gaza Strip in June 2007, the Israeli authorities imposed a stringent isolation policy – restricting people’s access to and from Gaza and curbing access of all non-humanitarian supplies. This isolation policy, along with a lack of effective coordination between the Palestinian Authority in Ramallah and the Hamas authorities in Gaza has resulted in shortages of spare parts for critical health and water and sanitation installations, medical and relief items, food, materials for humanitarian projects and raw materials for Gaza’s commerce and industry.

Consequently, the health care provision is on a steady decline, resulting in serious shortages of pharmaceuticals and the breakdown of essential medical equipment (laboratory, x-ray, echo machines, etc) with the inability to repair these. In the same way, the frequency of electricity and fuel cuts are seriously impacting all hospital services, and it is most critically felt in intensive care units, operation theatres and emergency rooms.

The most recent development was the Israeli decision on 17th January 2008 to completely close off the Gaza Strip, which included the passage for all goods and fuel. As a result no basic commodities were allowed to enter including medical supplies and fuel required to operate the Gaza power plant. The hospitals in Gaza have been already operating on a minimal level; however, the cut-off of fuel has made it ever more challenging to continue even emergency services. According to WHO report, two hospitals were forced to stop activities in all their departments except for emergency cases and the intensive care units during the hours of the cut. Similarly, the Gaza CDS is facing serious shortages on essential medical supplies. As of the 22nd of January, the World Health Organization and the International Committee of the Red Cross have been allowed to send medical items into Gaza; however the need for assistance remains valid.

Indeed, through a rapid assessment conducted since the beginning of January, CARE has identified the urgent need to support the CDS in Gaza. The information collected reveals that 104 pharmaceuticals are at 0-1 month stock, and 61 pharmaceuticals are with less than three month stock (please refer to the attached lists in Annex 1 – Gaza CDS Needs). This variety of medications is used against acute illnesses such as infections, eye diseases, chronic diseases like diabetes, heart diseases and blood hyper tension, emergency cases like poisoning, viral infections and oncology treatment, etc.

Therefore, as shown above, there is an urgent need to support the Gaza Central Drug Store through the provision of medicines that are currently depleting.

In order to respond to this urgent need within the framework of CARE’s health project funded by ECHO and avoid a further deterioration of the health situation in the Gaza Strip, CARE requests financial support from the French Ministry of Foreign Affairs in order to deliver medicines to the Gaza CDS. This intervention will allow the access of the Palestinian population to basic health care services, which is a basic human right, as well as the treatment of the above mentioned diseases that strike the Palestinian population.

Description of the intervention

Global objective

Ensure an immediate aid and support to health facilities in the Gaza Strip, which urgently need assistance, through the procurement of medicines.

Specific objective

Mitigate the shortages of basic medicines faced by the Central Drug Store in the Gaza Strip.

Locations

The Ministry of Health (MoH) Hospitals and Primary Health Care Centers (PHC) in 5 Governorates in the Gaza Strip: North Gaza, Gaza, Deir-al-Balah, Khan Yunis, Rafah.

The facilities that the proposed intervention plans to support are the following:

| Governorate | Number of MoH Primary Health Care Centers (PHC) | Number of MoH Hospitals | Name of MoH Hospitals |
| --- | --- | --- | --- |
| North Gaza | 10 | 2 | - Kamal Udwan - Beit Hanoun |
| Gaza | 15 | 2 | - Shifa - Gaza Ophthalmic - Gaza Pediatrics |
| Deir Al Balah | 15 |  |  |
| Khan Younis | 12 | 2 | - Gaza European - Nasser |
| Rafah | 4 | 1 | -Abu Yusef Al Najjar |
| TOTAL | 56 | 7 |  |

Note: The above mentioned facilities represent the whole structure of the Ministry of Health within the Gaza Strip. The above list of facilities is tentative, and may change during the course of the project, on the basis of Hospitals’ and PHC’s needs and CARE’s continuous coordination with other actors of the health sector in the Gaza Strip.

Catchment population

- Palestinians in need of basic and emergency health care;

- The Central Drug Store, MoH Hospitals and Primary Health Care Centers in the Gaza Strip.

Number of beneficiaries

Approximately 70,000 direct beneficiaries will have access to proper medical treatment through the provisions of medicines to the MoH Hospitals and PHC in the Gaza Strip.

This number of beneficiaries is an estimation based on the average caseload of patients per above mentioned facility in the Gaza Strip and on the expected number of items to be delivered through this intervention.

Activities

Activity 1: Assessment and identification of the Gaza Central Drug Store’s needs in terms of medicines

In January 2008, CARE has conducted a rapid assessment in the Gaza Strip that pointed out the urgent need to provide the CDS with medicines. CARE has consulted with the Manager of the Gaza CDS in order to assess shortages and needs in terms of medicines.

According to this assessment, it appears that 104 pharmaceuticals are currently at 0-1 month stock, and that 61 pharmaceuticals are with less than 3 month stock. Lists of these medicines are attached in Annex 1 – Gaza CDS Needs.

During this initial assessment, CARE has coordinated its intervention with other actors of the health sector in the Gaza Strip, such as Médecins du Monde (MDM), the World Health Organization (WHO), etc, who also plan to support the Gaza CDS through procurement of medicines in the near future. In addition, CARE is also in the process of providing pharmaceuticals to the CDS through its ECHO-funded project.

Therefore, CARE currently keeps and will keep coordinating continuously, within the organization itself as well as with the other actors, in order to ensure that assistance is not duplicated.

Through this intervention, CARE plans to provide 15 items (for a total quantity of 212,210 units) out of the 104 that are currently at 0-1 month stock and the 61 that are with less than 3 month stock.

The stock of medicines provided by CARE will cover 4 months consumption.

A list of the 15 items, with the planned quantities, is attached to this document in Annex 2 – List Medicines MoFA.

Please note that this list is indicative and may vary in the course of the project, depending on availability of items, expected delivery time, and continuous coordination within CARE itself and between CARE and other actors of the health sector in the Gaza Strip. Upon project approval from the French Ministry of Foreign Affairs, CARE will conduct another rapid assessment in order to ensure full coordination with other on-going interventions and revise, if necessary, the list of pharmaceuticals to be procured to the CDS.

Activity 2: Procurement process

Given the emergency of the situation and the necessity to procure the medicines to the CDS as quickly as possible, CARE has already launched the tendering process in order to identify potential vendors soonest, as well as unit costs and time of delivery.

Therefore, CARE is already fully prepared for this intervention, and once the grant agreement is signed with the French Ministry of Foreign Affairs, will be able to purchase the medicines immediately, and thus ensure rapid delivery.

The procurement process will be done according to CARE’s internal procedures. The products will be purchased locally to ensure cost-effective and timely delivery, and to support the Palestinian private sector’s development.

The local pharmaceutical companies that CARE works with for the procurement of medicines are located in the oPt, mainly in Ramallah, which facilitates the delivery to CARE’s warehouses. If the medicines cannot be produced on the local market, CARE will purchase them through local agents of international pharmaceutical companies.

The local pharmaceutical companies submitting an offer are requested to submit their ISO 9000 and 14000 certification statuses. These certifications ensure the quality of services provided by the vendors and that the latter respect regulations and environmental standards. To note is that, currently, four local pharmaceutical companies are certified Good Manufacturing Practice (GMP), which means that these companies are recognized worldwide for their control and management of manufacturing and quality control testing of pharmaceutical products.

Once the medicines are purchased from the local pharmaceutical companies and/or agents, the latter will deliver them to CARE’s warehouses in Ramallah and/or Gaza.

Activity 3: Reception and storage of delivered pharmaceuticals

Upon their delivery by the contractors, the pharmaceuticals will be stored in the quarantine zone of CARE’s warehouses in Ramallah and/or Gaza.

CARE’s pharmacists will then randomly select samples of the delivered medicines and sent them to the laboratory of Birzeit University for testing. Through this process, CARE will ensure that the purchased pharmaceuticals are in line with the quality standards defined by the World Health Organization and the Palestinian Ministry of Health, as well as with the current ISO and GMP certifications, and will ensure that the delivered products are not damaged, are safe and effective. This testing process is charged to the project, for a total value of €1,000.

After checking the conformity of the medicines, the latter will be transferred from the quarantine zone to the warehouses’ distribution zone for repacking and delivery.

Activity 4: Delivery of medicines to the Gaza Central Drug Store

All purchased medicines will be delivered to the CDS in Gaza, from CARE’s warehouses in Ramallah and/or Gaza. A delivery plan will be put in place in coordination with the CDS.

To transport the medicines from CARE’s warehouses to the Gaza CDS, CARE will contract a local transportation company. For the past 5 years, CARE has worked with the same transportation company to conduct its delivery of medicines. During this period, CARE has distributed nearly €15 million worth of pharmaceutical products without encountering any problem during delivery.

The transportation cost will reach approximately €10,000, which has been charged to the project. This high cost is due to the fact that most of the medicines will have to be delivered from Ramallah to Gaza (most local pharmaceutical companies/agents are located in Ramallah), and the passage of the Gaza Strip’s crossing points will entail the unloading and reloading of trucks on both sides of the border.

The medicines’ transportation will be monitored through the Generic Inventory Management System (GIMS) used by CARE West Bank & Gaza. This system will permit to follow all products from their departure from CARE’s warehouses to their arrival at the Central Drug Store in the Gaza Strip, by type, value and donor.

In addition, CARE’s health teams will follow and monitor the delivery of medicines to ensure their proper arrival at the CDS.

All delivered boxes of medicines will bear a label clearly stating that the product is donated by CARE with the support of the French Republic, with apparent CARE and French Republic logos.

Expected results and indicators

Result: Gaza Central Drug Store provided with essential pharmaceuticals in the course of the project.

Indicators:

- At least 12 identified pharmaceuticals delivered to the CDS.

- Quantities received will cover 4 months consumption.

Human resources required for the project

- Project Manager: S/he is responsible and coordinates the assessment. S/he will overview the project activities and will ensure their proper implementation on the ground.

- Procurement Officer: S/he will be supervising the purchase of the medicines. S/he will be reviewing, finalizing and approving the contracts and payments for vendors prepared by the project assistant. S/he will ensure that all procurement procedures are followed.

- Assistant Logistician: S/he will overview and monitor the delivery of the products to CARE’s warehouses and their distribution to the CDS. S/he will coordinate the transport of medicines to CARE’s warehouses, ensure that the products are well received and stored within CARE’s warehouses, and will ensure their proper delivery to the CDS in the Gaza Strip.

- Gaza warehouse temporary employee(s): They will be in charge of receiving the medicines in CARE’s warehouse, of their transfer from one zone of the warehouse to the other, and will be in charge of packaging and loading the medicines.

- Project Assistant: S/he will be working closely with the procurement officer. S/he will prepare the necessary documents (contracts with vendors, payment requests for vendors, etc.) and send them to the procurement officer for review and approval. S/he will also ensure proper filing of project documents.

- Accountant: S/he will be in charge of the financial monitoring of the project.

Material resources for the project

Part of the rent of CARE’s Ramallah and Gaza warehouses are charged to the project. Similarly, part of CARE’s Jerusalem and Ramallah offices running costs have been charged to the project.

Coordination of the intervention

In order to avoid overlapping and identify un-covered needs, CARE works in coordination with all UN agencies, especially the World Health Organization, the World Bank, as well as with other humanitarian agencies working in the health sector: ECHO, international NGOs (International Committee of the Red Cross, etc.), French NGOs (Médecins Sans Frontières, Médecins du Monde, etc.), and local NGOs (Palestinian Medical Relief Society, Health Work Committee, etc.). This coordination is done through monthly and/ or crisis meetings, during which on-going projects and health emergencies striking the Palestinian population, and the means to efficiently respond are discussed. CARE is highly proactive in this coordination: CARE regularly initiates contact with these partners and holds bilateral meetings with NGOs.

As mentioned previously, CARE is currently coordinating this intervention, both internally and with other actors who plan to support the Gaza CDS through procurement of medicines (MDM, WHO, etc.), in order to avoid overlap of interventions. This coordination will continue during the implementation of the project.

Monitoring planned for the intervention

Initial Assessment

An assessment of the Gaza Central Drug Store, and its needs, has been conducted in January 2008. CARE’s team also visited the CDS to ensure that products to be delivered were indeed out of stock or close to be.

Monitoring of the project

CARE has in place and will use, for this intervention, a global monitoring system, that comprises a monitoring of the storage and of the use of the medicines.

This monitoring system will be used to ensure that the donor’s and CARE’s standards are respected for the management of the distributed products and according to good governance principles and the Humanitarian Charter.

CARE’s team on the ground will ensure oversight of the operation and of its impact. CARE will follow up with the CDS to ensure proper delivery of medicines to the latter, and will follow up with the MoH Hospitals and PHC to make sure that medicines delivered through this project are available within the health facilities.

Duration of the intervention: 4 months.

Visibility

- A press release will be published locally and in France to launch this distribution. The press release will state the origin of funding.

- The distributed boxes of medicines will bear labels with the following statement in Arabic and French: “CARE distributes medicines to the Palestinian population with the support of the French government”, with CARE and French Republic logos.

Visibility costs (mainly stickers) have been charged to the project.