Things need for submission:

- food security assessment (annex 1)

- beneficiary numbers?

- budget

- budget notes

I.  PROPOSAL SUMMARY

Request for a New Award

| Headquarters: | Country Office: |
| --- | --- |
| CARE International CARE International in Tajikistan Bob Bell Louis Alexander Director, Food Security Unit Country Director/Program 151 Ellis Street 25 Bekhzod Street Atlanta Georgia, 30303 Dushanbe, Tajikistan Tel: 404-681-2552 Tel: (992-91) 901-2273 Fax: 404-589-2626 Tel: (992-372) 21-17-78 e-mail: bellr@care.org e-mail: louis@care.tajnet.com | CARE Tajikistan Louis Alexander Country Director/Program 25 Bekhzod Street Dushanbe, Tajikistan Tel: (992-91) 901-2273 Tel: (992-372) 21-17-78 e-mail: louis@care.tj |

Country/Region: 	Jilikul and Yovon districts in Khatlon region, Vakhdat and Varzob districts in Regions of Republican Subordination and Dushanbe, capital city of Tajikistan

Submission Date: 	February 19, 2008

Program Title: 	CARE Tajikistan  Emergency Response for Children and Families Affected by the Tajikistan Winter Emergency

Program Duration: 	one month

Proposed Start Date: 	February  25, 2008

Proposal includes the following categories of restricted goods:

| Restricted Goods | Check box if applicable |
| --- | --- |
| Agricultural commodities | N/A |
| Vehicles not manufactured in the U.S. | N/A |
| Pharmaceuticals – Human and Veterinary | N/A |
| Pesticides | N/A |
| Fertilizer | N/A |
| Used equipment | N/A |
| USG-owned excess property | N/A |

Dollar Amount Requested from OFDA	$377,910

Dollar Amount from Other Sources	$_______

Dollar Amount of In-Kind Contributions	$_______

Total Dollar Amount of Program	$377,910

Program Goal:

Total Number of Individuals Affected in the Targeted Area: 75400

Total Number of Beneficiaries Targeted (Individuals): 18400

Total Number of IDP Beneficiaries Targeted (Individuals): n/a

| Sector: |  | Economy and Market Systems |
| --- | --- | --- |
| Objective: |  | To improve food security of extremely vulnerable population through provision of cash. |
| Dollar Amount Requested: |  | $ 123,338 |
| No. of beneficiaries targeted: |  | 16100 |
| No. of IDP targeted: |  | n/a |
| Geographic Area(s): |  | Jilikul and Yovon districts in Khatlon region, Varzob, Shahrinav, Hissor and Faizobod districts in Regions of Republican Subordination |
| Sub-Sector: |  | Economic Recovery |
| Indicator (A): |  | - Amount of cash distributed per beneficiary |

| Sector: |  | Logistics/Relief Commodities |
| --- | --- | --- |
| Objective: |  | To improve access to fuel, heating and other essential equipment and supplies for vulnerable population to counterbalance winter and energy crisis |
| Dollar Amount Requested: |  | $ 254,572 |
| No. of beneficiaries targeted: |  | 14,400 |
| No. of IDP targeted: |  | n/a |
| Geographic Area(s): |  | Jilikul and Yovon districts in Khatlon region, Vakhdat and Varzob districts in Regions of Republican Subordination, and Dushanbe, Tajikistan |
| Sub-Sector: |  | Non-Food Items (NFIs) |
| Indicator (A): |  | Number of beneficiaries receiving NFIs |
| Indicator (B): |  | Number of NFIs per beneficiary by NFI type |

Cross-Cutting Themes (CCT)

| Name of CCT | Relevant Sector and Sub Sector | Indicators |
| --- | --- | --- |
| Children | All | - No. of children assisted |

Justification

  - Problem Statement

- Extreme winter temperatures, depleting food and fuel stocks, probable, prolonged blackouts at the national level beginning mid-February, and limited access to water is pushing the entire population of Tajikistan (estimated at 7 million people) into humanitarian crisis.  While the current energy crisis and impending power outages are primarily affecting urban populations, a series of economic and environmental shocks over the last few years have left rural populations with few remaining coping strategies for mitigating their increased level of food insecurity

- As most rural areas have electricity less than 1 hour a day, and limited to no access to gas for heat or water (due to frozen and cracked water mains), the impact on households has been profound.  Households surveyed by Save the Children report that their fuel supplies have been exhausted and that several or all of the family members have either fallen ill or have died over the last few months.  The decrease or elimination of electrical, gas and water services has also negatively impacted health and education service delivery.

  - Needs Assessment Summary

Rural populations of Tajikistan live in poverty with limited coping strategies, dependant on agricultural production of food for household consumption. While the energy crisis and freezing winter temperatures are negatively affecting urban populations as well, due to higher food and fuel prices and decreased availability of potable water, of greater concern is the heightened level of food insecurity that is being experienced by rural populations.  Some specific evidence (collected by Save the Children in Baljuvon and Khovaling Districts of Khatlon Region at the end of January 2008) of the increased levels of food insecurity in rural areas include:

- 85% of respondents surveyed in Baljuvon and Khovaling reported that they do not have any money saved for emergencies.

- 77% of respondents surveyed had sold an animal this winter to buy food (mostly cows and goats, though horses, donkeys, and sheep were also mentioned)

- At the time of the survey, at current consumption rates, households report that they have, on average 16 days left of food stocks.  42% had one week or less of food stocks left

- 54% described their overall health as ‘bad’, while 39% described the overall health of their family as ‘bad’.  Only 20% described their family health as ‘good’.

- Those that described their and their family’s overall health as ‘bad’, 63% have not sought medical attention due to lack of money.

- Freezing temperatures have caused severe damages to food stores at the household level.

CARE project staff held discussions with project beneficiaries,  stakeholders , and local government representatives to identify their current problems and their immediate needs.  The initial findings are as follows:

- Warm clothing for children (including tights, sweaters, jackets, hats, gloves, socks, and boots);

- Blankets for elderly and disabled people

- Non-electrical heaters and stoves.

- Metallic non electrical water boilers

- Fuel for stoves (coal)

- Generators & fuel for them

- Plastic containers with handles for carrying and storing water

- Food package  for the most vulnerable households

  - Justification for Intervention

While the energy crisis and impending power outages are primarily affecting urban populations, a series of economic and environmental shocks over the last few years have left rural populations with few remaining coping strategies for mitigating their increased level of food insecurity. As part of a rapid emergency assessment conducted by CARE staff, it was found that an alarming number of households were rapidly diminishing their food stocks as a result of the current freezing temperatures and fuel emergency and would face a prolonged lean season prior to the 2008 harvest. In addition, an increase in the sale of productive and household assets was documented, the sale of which compromises both household productivity and resiliency to cope with future ‘shocks’ and thereby inhibits their long term food security. Thus, there is serious concern that rural populations will not be able to take full advantage of the coming agricultural season as a result of fewer household resources for investment in agricultural inputs, the increased sale of productive assets and livestock during the winter, and the compromised health of household members which will limit the amount of labor for household garden food production. Many of the CARE program sites in rural areas including Varzob , Vakhdat, Yovon and Jilikul districts are without power, water, and fuel and also experiencing food shortages during the past 2-3 weeks. Winter crops have been destroyed and vegetables stored for consumption have spoiled or are in limited supply.  Dushanbe city and other cities throughout the country are also severely affected as they have no heating and cooking alternatives.   Elderly people living alone with little or no income are helpless victims of this crisis situation.

According to information published by Asia Plus, some children have already died in the Dushanbe Maternity Hospital for lack of heat or properly functioning life support equipment.  Reports from hospitals in secondary cities are scanty and not very reliable. Rural health services are being affected due to shortage of transportation, lack of healthcare providers and power cuts – in essence, people living in remote villages have no access to health services during this time.  According to the results of a Rapid Assessment of the energy and water supply to healthcare facilities, even the Central District Hospitals in most CARE operational areas don’t have energy and water supply. Already the number of cases of chronic and acute diseases is increasing. The situation is expected to deteriorate even if the power situation remained the same. Schools in CARE operational areas do not have generators, and special schools for the physically and mentally challenged, as well as homes for the elderly are poorly equipped to meet the demands of the severe winter.

In order to respond to the unique needs of the Tajik children and their families affected by the weather and fuel emergency and the rapid erosion of food security, CARE Tajikistan proposes to meet both the immediate survival needs of approximately 18400 emergency affected people and provide them with the means to enhance their food security while at the same time promote economic and market recovery.

- Program Description

  - Program Level

    - Goal

To prevent death, serious illness, and starvation of the most vulnerable members of rural and urban population in CARE operational areas, caused by the ongoing severe winter and energy crisis in Tajikistan.

    - Beneficiaries

With OFDA funding, the emergency response program will target directly approximately 4858 extremely vulnerable people and their families over a month period for a total beneficiary count of 18,600. CARE will focus its support by providing approximately 426 people with disabilities including mentally disabled children and blind, 91 institutionalized elderly, 589 other institutionalized children,  720 schoolchildren, estimated 732 pregnant women, and 2300 poor households with emergency assistance that is critical to their health and well-being.

    - Critical Assumptions

- USAID/OFDA resources are available as programmed and expected

- Security context stable as now in, allowing free movement of humanitarian staff and goods

- Continued and increasing humanitarian access and support from local authorities

- Favorable climatic conditions;

- Receipt of additional support from other donors and partners as planned.

    - Program-Level Coordination

The Tajikistan winter emergency is a slow onset emergency, exacerbated by the extreme winter weather. In response to the emergency, NGOs already operational within the country, have expanded their existing development portfolios to establish emergency response programs throughout the country. UN agencies (OCHA, WFP, UNICEF, WHO) have likewise expanded operations. The Government of Tajikistan (GoT) is represented through State Ministries for Health, Social Protection, Agriculture and Education, the Committee of Emergency Situations, and also at regional level by the District and Sub-District local governments and departments.  While the GoT and State Ministries are responsible for providing services in Tajikistan, CARE and the other agencies are committed to supporting emergency-affected populations until the capacity and resources of these State agencies can respond to the needs.

Given the large number of agencies responding to the crisis, coordination is a complex process. The Disaster Management Partnership in Tajikistan – Rapid Emergency Assessment and Coordination Team (REACT) has filled the coordination role to promote the sharing of information, logistics and other resources between partners (including over 50 state, local and international organizations). As a REACT member, CARE Tajikistan is committed to the process of coordination and upholds consensus arrangements, both at the strategic and area/locality level.  Current arrangements ensure coordination of activities and maximum coverage between all actors that participate in coordination.  CARE participates in all general and sector coordination meetings (cluster) in Tajikistan.

At the present CARE Tajikistan Country Office has sufficient human resources and management capacity to response to the current emergency situation. There are more that 100 staff including managers, field facilitators, engineers, doctors and drivers working for different CARE projects. Specifically, CARE has the Integrated Community Disaster Reduction Project with the qualified personal with long experience of working on Disaster Risk Reduction and response. CARE also has an excellent relationship with the local authorities at the national and district level as well as with the INGOs, such as Save the Children, Mercy Corps, CARITAS, UNICEF and many others. CARE can use its operational capacity to support the response required and make significant contribution to large and urgent humanitarian needs.

    - Safety and Security Plan for Program/Field Staff

CARE Tajikistan CO has a Safety & Security Manual. The safety and security of all CARE staff is the highest priority of the Tajikistan Country Office, and all security issues carefully and fully considered in the planning and implementation of all programs, projects and operations. The Country Director (CD) or the Acting Country Director (ACD) in the absence of the CD, is the responsible person as concerns security matters and issues, and will make decisions concerning security phase changes, implementation of enhanced security measures, evacuation matters including the timing, routes, and personnel to be evacuated. Such decisions shall be made after discussion with senior staff in CARE Tajikistan and consultation with CARE Atlanta senior staff, and after due consideration of all factors existing at the time of the decision.

The Safety and Security Manual covered several specific areas such as: facility, personal, travel, home and office security, evacuation/relocation plan, medical evacuation plan, crisis response procedure and etc.

    - Transition and Exit Strategy

CARE Tajikistan will implement programs in close collaboration with the stakeholders and local authorities to meet the immediate needs of the emergency affected population.

The transition or exit strategy will be considered during the implementation of this project in the following forms:

- Exit strategies will be communicated to communities in CARE Tajikistan program areas, thus informing communities that CARE assistance is a temporary relief

- Program interventions with strong links to future financial viability will be implemented with the strategy of integration into local systems

  - CARE Tajikistan Programs (Sector and Sub-Sector Level)

| Sector: Economy and Market Systems |  |
| --- | --- |
| Objective: To improve food security of extremely vulnerable population through provision of temporary cash distribution |  |
| Dollar Amount: | $ 123,338 |
| No. of beneficiaries targeted: | 16100 |
| No. of IDPs targeted: | n/a |
| Geographic Area: | Jilikul and Yovon districts in Khatlon region, Varzob, Shahrinav, Hissor and Faizobod districts in Regions of Republican Subordination and Dushanbe, Tajikistan |
| Sector Level Coordination: | All economic recovery activities will be implemented in partnership with UN agencies, NGOs and relevant Government Ministries and in collaboration with the REACT and FACT working group members. CARE Tajikistan leads the USAID FACT Consortium in Tajikistan and participates in food security coordination meetings in Dushanbe. CARE has a very good relationship with government agencies and other INGOs working in the implementation areas. This is essential to guarantee that vulnerable households are effectively targeted and that duplication of efforts is avoided. |

Sub-sector: Economic Recovery

Technical Design:

Cash distributions to emergency affected families will not only increase household short-term food security through the purchase of much needed food stocks, but such distributions will also provide families with the means to proactively reestablish their livelihoods through the purchase of productive assets which were sold during the winter emergency.  It has been found by CARE globally that recipients of cash distributions spend approximately 50-70% of the funds on food and the remaining balance on other items such as productive assets, medical treatment and needed household goods. In addition, because sufficient food stocks are available in the market, cash distributions will also rapidly infuse the economy with much needed capital thereby promoting market recovery. The supplemental food stocks and recovered productive assets will decrease family’s vulnerability to shocks and contribute to longer term food security.

CARE Tajikistan’s economic recovery programming will target the families of Fpoor farmers and vulnerable members of the community based organizations created by CARE Integrated Community Disaster Reduction Project in vulnerable communities, enabling them to meet their emergency needs and restore productivity. It is estimated that 2300 emergency-affected households will be targeted through the proposed project. CARE Tajikistan anticipates that 73 percent of these households will also benefit from the NFI distributions. Given the potential multiplier-effect of cash distribution on the economy, local traders and farmers are likely to be indirect beneficiaries of the proposed project

Subsector activities:

- Identification of targeted beneficiaries.

- Training of staff in cash distribution methodology and monitoring practices.

- Distribution of cash  to targeted households.

- Monitoring and Evaluation – usage of resources and impact on market prices

Beneficiary Issues:

The targeted households have been selected given their extreme vulnerability.

Indicators:

The following indicators will be used to measure results of Food distribution:

- USD amount increase in purchasing power per beneficiary

- Number of people who will benefit from the proposed activity

| Sector: Logistics/Relief Commodities |  |
| --- | --- |
| Objective: To improve access to fuel and heating and other essential supplies (warm clothes, blankets and water containers) for vulnerable population to counterbalance of the cold winter and energy crisis |  |
| Dollar Amount: | $ 254,472 |
| No. of beneficiaries targeted: | 14,400 |
| No. of IDPs targeted: | n/a |
| Geographic Area: | Jilikul and Yovon districts in Khatlon region, Varzob, Shahrinav, Hissor and Faizobod districts in Regions of Republican Subordination, and Dushanbe, Tajikistan |
| Sector Level Coordination: | All relief commodities activities will be implemented in partnership with UN agencies, NGOs and relevant Government Ministries and CARe Tajikistan will closely collaborate and coordinate its activities with members of the REACT and FACT working groups. CARE participates in REACT non food sector coordination meetings in Dushanbe and maintains good relations with the authorities and all international agencies working in the implementation areas. This is essential to guarantee that needy beneficiaries are effectively targeted. |

Sub-sector: Non-Food Items (NFI)

Technical Design:

CARE Tajikistan will provide children from poor households and those living in institutions with sets of warm clothing (boots, jackets, sweaters, scarves, socks and mittens).  Elderly people from the Association of the blind people in Dushanbe and CARE will provide secondary schools and Republican special school in Yovon with the heating stoves and one month supply of the coal.  CARE will provide nursery in Dushanbe with metallic non electrical water boiling tank which allow them to improve access to hot water for children and prevent spread of water born diseases among children.

The distribution of emergency non-food items to vulnerable elderly people, children and poor households in Dushanbe and rural areas will address their immediate survival needs.  CARE recognizes that NFI distribution must be implemented in a manner that does not encourage dependency on external aid nor exhaust local market supply. Therefore only children and households that can be classified as extremely vulnerable, and therefore do not have other means to procure the essential items will receive the distributed items.

CARE will also provide generators and one month supply of the fuel for them to maternity houses in its operational areas as well as to home for elderly people and Republican special school in Yovon and orphanage in Dushanbe the departments which enable those institutions to provide to vulnerable people including disabled children and elderly as well as pregnant women heating and lighting when its needed.

A rapid survey of the Dushanbe market as well as the effects of similar emergency procurements in recent weeks illustrates that sufficient stocks of supplies exist within Tajikistan to procure items without the negatively influencing the supply needed for normal use. It was also found that prices have not increased in major markets despite the sharp demand placed upon them by INGOs making large purchases of NFIs. Also, given that supplies will be procured in-country, items will be familiar and accepted by the beneficiaries.

Subsector activities:

- Identification of targeted children and families

- Procurement of non-food items in capital and regional city markets

- Distribution of items to institutions, schools, children and households

- Monitoring and Evaluation

Beneficiary Issues:

Given that CARe works in the mentioned above districts for many years,  extensive demographic information on the targeted communities is already available and will ensure the rapid delivery of aid to extremely vulnerable people

CARE works in close collaboration with REACT and FACT members to ensure that duplication of similar interventions is avoided.

CARE is also aware that given the depressed economic status of the country the majority of rural Tajiks could be classified as vulnerable. As it would not be feasible to distribute NFIs to entire communities, extremely vulnerable children and their families will be targeted. The targeting criteria will be made clear to the beneficiary community to promote transparence and reduce potential animosity toward the beneficiaries.

Indicators:

The following indicators will be used to measure results of NFI distributions:

- Number of beneficiaries receiving NFIs

- Number of NFIs per beneficiary by NFI type

Cross-Cutting Themes:

N/A

Indicators

Monitoring and Evaluation

Monitoring Plans: The Program Monitoring Matrix (attached in Annex 3) defines monitoring plans per sector in relation to each objective.  The source, method, time frame, responsible person, method of analysis and baseline comparison have been detailed for each indicator.  Sector heads will be responsible for the monthly collection and analysis of data on process indicators. This data will inform monthly and quarterly project reports to inform any needed program adjustments.  Data will be shared with community members through outreach as a critical part of their involvement in program design and implementation.  Quality assessments will also be conducted periodically, by sector, by the senior program team.

Evaluation Plans:  Impact and outcome indicators for this project are indicated and incorporated into an Evaluation Plan attached in Annex

Save the Children “Rapid Food Security Assessment in Baljuvon and Khovaling Districts”, January 28-20, 2008.

Oxfam’s “Rapid Needs Assessment Kulyab City”, 03-02-08.