## Sheet1
Annex - Indicative Activity Workplan
Post-Flood Rehabilitation Support for Victims of Flooding in 6 Districts of Eastern and Western Nepal
(1 September 2007 - 31 December 2007)
| Activity Description | Total cost (Euro)
|  |  | Month 1 | Month 2 | Month 3 | Month 4
1 | Project Start Up Activities
í | Office establishment
ii | Staff recruitment and project orientation
iii | Project start up and planning meeting with key stakeholders
2 | Support rehabilitation/construction of house
ii | Project planning meeting with stakeholders
iv | Design estimate of low cost house
vi | Rehabilitation and/or construction of house
3 | Rehabilitation/lnstallation of hand pumps
i | Design e/estimate
ii | Construction/rehabilitation
4 | Rehabilitation/lnstallation of school toilets
í | Design/estimate
ii | Construction/rehabilitation
5 | Reporting