CARE International in Tajikistan

Winter Emergency Response for the most

vulnerable people in Tajikistan

Contact Person:

Louis Alexander

Country Director

CARE International in Tajikistan

Bekhzod Str. 25, Dushanbe, 734003, Tajikistan

Tel.: 7-992372-211783; 907754537

Fax: 7-992372-211783

Email: louis@care.tj

February 2008

Project Title:

Winter Emergency Response to the

Most Vulnerable People in CARE Operational Areas

Project Area:  Yovon, Vahdat, Varzob, Jilikul, districts and Dushanbe

## Beneficiary Coverage: CARE plans to assist 25,800* people with IMMEDIATE LIFE SAVING SUPPORT through the provision of food, cash, heating and mobile health services to counterbalance the energy crisis and extended /severe winter.

Project Duration:  February – April 2008 (7 weeks)

Total Budget: (in USD) 230,000

Background Information

Tajikistan is experiencing its harshest winter in three decades with temperatures that have averaged minus 10 degree Celsius during the day and have dropped as low as -20 degrees at night in the capital Dushanbe and even lower in some parts of the country. Many antiquated water lines have either been broken or become frozen/ clogged, with a major impact on the availability of water for the past three weeks. Sub-zero temperatures and water shortages are continuing.

In rural areas population receive one or two hours of electricity a day, and some none at all. Even in Dushanbe, electric power is limited and many residential areas have no electricity overnight.

As a result of continuing heavy snowfall, the roads between and within several districts are blocked. These closed roads have also had an impact on local supplies of food and other basic commodities as well as medical services, so the impact at rural levels may be critical in some areas.  Winter crops have been destroyed and vegetables stored for consumption have frozen and spoiled or are in limited supply.  Elderly people living alone with little or no income are helpless victims of this crisis situation.

Rural health services are being affected due to shortage of transportation, lack of healthcare providers and power cuts – in essence, people living in remote villages have no access to health services during this time.  Already the number of cases of chronic and acute diseases is increasing. The situation is expected to deteriorate even if the power situation remained the same. Schools are ill equipped to meet the demands of the severe winter and school children are falling ill as the schools do not have adequate heating facility. Orphanages in CARE operational areas do not have generators, and special schools for the physically and mentally challenged, as well as homes for the elderly are poorly equipped as well, and are experiencing even worse conditions.

CARE Tajikistan took immediate action and started a rapid needs assessment of the impact of the energy shortage and exceptional climate conditions on vulnerable groups in its operational areas.  The needs assessment included visits to field sites, conversations with local beneficiaries, local mahalla leaders and institutions in the target areas. In addition, we have received numerous requests from all levels of society and used this information to compare to our own assessment as well as that of partner organizations – collectively we were able to get a more comprehensive picture of the situation. Specifically, we coordinated and cross-checked information with UNICEF, ACTED, Mercy Corps, Save the Children, CARITAS, IFRC, District level Ministry of Education and Health offices, Jamoat offices, and a local women’s federation based in Vahdat. Based on The results of the assessment and meetings with  partner NGOs, UN agencies and government representatives, the following critical food and non-food requirements were identified:

- Cash for buying basic food items

- Fuel supplies such as wood, charcoal, gas, kerosene etc.

- Heating equipment such as coal or wood burning stoves

- Power generators & fuel for them

- Plastic water containers, soap

- Health services, medicines

- Wheat flour and vegetable oil

- Emergency credit for micro businesses

Goal:

To provide immediate life saving support to rural and urban populations to prevent starvation, serious illness, and death among the most vulnerable members of society caused by the ongoing severe winter and energy crisis in the country.

Objectives:

1.  To improve food security of extremely vulnerable population

2.  To improve access to essential fuel and heating supplies for vulnerable population

3.  To improve access to health services to pregnant and vulnerable women and children

Implementation Strategy:

CARE will implement an emergency response with partners, including UN agencies, district and sub-district government bodies, INGOs and local organizations such as the Yovon Women’s Federation for rural areas.

CARE will provide cash for a one-month food package with the value of US $58 to the most vulnerable people including pregnant women in CARE operational areas including Dushanbe, Yovon, Varzob, and Vakhdat districts. Cash distributions to emergency affected families will not only increase household short-term food security through the purchase of food stocks which have been depleted, but such distributions will also provide families with the means to proactively re-establish their livelihoods through the purchase of productive assets which were sold during the winter emergency.  It has been found by CARE globally that recipients of cash distributions spend approximately 50-70% of the funds on food and the remaining balance on other items such as productive assets, medical treatment and needed household goods. The supplemental food stocks and recovered productive assets will decrease the vulnerability of households to shocks and contribute to longer term food security.

CARE will distribute generators donated by DFID and one month supply of fuel to the rural and urban health institutions and schools.

To provide emergency health services to the vulnerable groups in remote areas, CARE established four mobile health teams. Each team will have qualified doctors, who will be provided with the necessary medical kit containing essential drugs required for an emergency health response. Each mobile team will conduct daily field trips to the most remote Jamoats (townships) of Yovon, Varzob and Vakhdat districts. The teams will work in close collaboration with the district health care providers who are well known to CARE through other projects and provide health service as per need.  This strategy will help to ensure coverage of the most vulnerable patients, proper referral and follow-up medical care to the patients.

CARE will also support the most vulnerable clients of the Micro Lending Foundation (MLF) HUMO affected by the hard winter by helping them to manage repayment of loans and interest rates. HUMO will select clients for restructuring loans based on the following: late repayment, monitoring report of credit staff about damages or losses because of hard winter, application of the client, and decision of Credit Committee. The funds from Emergency Fund will be used for subsidy of interest rates mostly.

CARE will use its operational capacity to implement the project and make a significant contribution to urgent humanitarian needs. CARE will implement the emergency distribution using the standard non food items system established by CARE in former and current programs. CARE Monitoring and Evaluation Manager and two temporary hired monitors will ensure proper monitoring of the emergency response.

The beneficiaries of this program include a wide range of people, such as:

- Single headed households and widows

- Families with disabled children and elderly

- Pregnant and lactating women

- Orphanages

- Disabled pensioners and other vulnerable elderly people

- People with health needs who are not able to access medical services

- School children

- Poor and vulnerable micro-credit clients

The impact on these people will be to immediately access food and life saving health services. The impact expected is to enhance households’ food and resource stocks, and strengthen their immune system to deal with the shocks that the climactic conditions have created, as well as the depletion of their resources. Beneficiaries will also receive short and long term service from generators to provide heating, lighting and cooking. Some beneficiaries will also benefit from emergency loan funds so as not to default on their existing loans and thus prevent further erosion of their capacity to bounce back from this emergency.

CARE will also receive funds from USAID to support its winter emergency response. This DFID funded program will complement the USAID funded program by allowing CARE to:

- Reach people with similar services in other districts that will not be reached with the USAID funds (Dushanbe, Yovon and portions of Vahdat, Jillikul and Varzob)

- Support the emergency micro credit fund of HUMO, a local micro-finance organization formed by CARE in 2004. This fund will support the poorest borrowers who are having trouble paying back their loans or need emergency loan funds

- Provide more generators in a complementary manner to the USAID program for health and educational institutions which are not part of the USAID program.

- staffing from the DFID funded program will support both DFID and USAID field support and monitoring activities

## Main implementation activities:

- Staff recruitment and orientation

- Orientation meeting with GoT authorities

- Selection and beneficiaries and preparation of list for distribution

- Pre distribution survey

- Procurement of the required items including fuel, medicines

- Distribute of cash for purchasing of food package for household to 2700 the most vulnerable people in CARE operational areas

- Provide 15 generators and one month supply of fuel for them to selected health, and social institutions and schools in CARE operational areas

- Support district health departments with provision of immediate basic health services & medicines through mobile health clinics to estimated 800 families.

- Establish emergency micro-credit fund to support the 300 poorest clients of Micro Credit Foundation, HUMO for restructuring of their loans.

- Monitoring of implementation of the project

- Implementation of visibility actions

- Post distribution evaluation survey

- Preparation and submission of final narrative and financial reports

Please see the attached implementation plan for more details and timing on procurement and distribution of all project related inputs. Distribution of most items will be done with CARE vehicles and in some instances, rented trucks may be needed. CARE drivers will also be available for all transportation needs.

Management, Monitoring and Reporting:

CARE will ensure proper monitoring of all project activities, under the guidance of CARE’s manager for Program Quality and M&E. In addition, two monitors will be hired on a part time basis to conduct on-going monitoring and recording of all activities. CARE Tajikistan has many years of food and other forms of distribution, including response to three recent natural emergencies (earthquake in Qumsangir, mud slides in Tursonzada, earthquake in Rash) – in all these cases we applied CARE systems for M&E, including tools for capturing information and analysis and reporting. CARE has M&E officers on hand who can also offer their support when needed. This M&E team will also support the production of a final report as well as with any monitoring visits that donors may require. Finally, on a random sample basis, CARE will also conduct a post response survey through interviews and focus group discussions to assure the impact of the program.

CARE senior staff will over all aspects of this program. This includes CARE’s program manager, Administration manager and procurement officer. On a temporary basis, other technical and support staff will be called upon to support the emergency program, under the advise of CARE Tajikistan Emergency Response Team.

Note: The numbers indicated against the vulnerable people including pregnant women and HUMO clients are to be multiplied by 7 to include family members.

Attachments:

Attachment 1- Detailed Implementation Plan

Attachment 2- Budget

Attachment 3- Budget Narrative