## Proposal Summary

Request for a New Award

| CARE USA | CARE Vietnam |
| --- | --- |
| Rigoberto Giron | Hanoch Barlevi |
| Director Emergency and Humanitarian Assistance Unit | Disaster Management Coordinator |
| 151 Ellis Street Atlanta, GA 30303 | 66 Xuan Dieu PO Box 20 Tay Ho, Hanoi |
| Ph: (404) 979 9539 Fax: (404) 577 4840 | Ph: (84 4) 716 1930 Fax: (84 4) 716 1935 Mobile: +84 912 794 939 |
| Email: rigirion@care.org | Email: hbarlevi@care.org.vn |

Country:  Vietnam

Submission date: 22 October 2007

Program Title:  Typhoon Lekima Emergency Relief and Rehabilitation

Program Duration (number of months): 6 months

Proposed Start Date: 5 November 2007

Proposal includes the following categories of restricted goods:

| Restricted Goods | Check box if applicable |
| --- | --- |
| Agricultural commodities | X (seeds) |
| Vehicles not manufactured in the U.S. |  |
| Pharmaceuticals - Human and Veterinary |  |
| Pesticides |  |
| Fertilizer |  |
| Used equipment |  |
| USG-owned excess property |  |

Dollar Amount Requested from OFDA		$ 200,000

Dollar Amount from Other Sources	$ 0

Dollar Amount of In-Kind Contributions	$ 0

Total Dollar Amount of Program	$ 200,000

Program Goal: To assist two disaster affected Districts in Thanh Hoa Province recover from Typhoon Lekima.

Total Number of Individuals Affected in the Targeted Area: 73,250 people

Total Number of Beneficiaries Targeted (Individuals): 69,240 (this is a cumulative total, actual no. of beneficiaries will be less as there will be overlap of sectors)

Total Number of IDP Beneficiaries Targeted (Individuals): 0

A separate Sector Table should be used for EACH sector.

| Sector 1: |  | Agriculture and Food Security |
| --- | --- | --- |
| Objective: |  | To increase food security |
| Dollar Amount Requested: |  | $70,401 |
| Number of Beneficiaries Targeted: |  | 56,000 people |
| Number of IDP Beneficiaries Targeted:* |  | 0 |
| Geographic Area(s): |  | Thach Thanh and Hau Loc District, Thanh Hoa Province |
| Sub-Sector: |  | Seed Systems and Agricultural Inputs |
| Indicator (A): |  | Number and percent of seed recipient farmers with sufficient seeds to plant fields for next agricultural seasons |

*Individuals – a subset Number of Beneficiaries Targeted

| Sector: |  | Water, Sanitation, and Hygiene (WASH) |
| --- | --- | --- |
| Objective: |  | To improve access to clean water and sanitation and reduced risk of water-borne diseases |
| Dollar Amount Requested: |  | $120,016 |
| Number of Beneficiaries Targeted: |  | 13,000 |
| Number of IDP Beneficiaries Targeted:* |  | 0 |
| Geographic Area(s): |  | Thach Thanh and Hau Loc District, Thanh Hoa Province |
| Sub-Sector: |  | Water |
| Indicator (A): |  | Number of beneficiaries receiving water from protected water points |
| Sub-Sector: |  | Sanitation (Household level) |
| Indicator (A): |  | Number of communal/institutional latrines constructed |

*Individuals – a subset Number of Beneficiaries Targeted

| Sector: |  | Risk Reduction (Natural and Technological Disasters) |
| --- | --- | --- |
| Objective: |  | To enhanced disaster preparedness and response capacity by local authorities and communities |
| Dollar Amount Requested: |  | $3,400 |
| Number of Beneficiaries Targeted: |  | 240 |
| Number of IDP Beneficiaries Targeted:* |  | 0 |
| Geographic Area(s): |  | Thach Thanh and Hau Loc District, Thanh Hoa Province |
| Sub-Sector: |  | Disaster Preparedness, Mitigation and Management |
| Indicator (A): |  | Number of people trained in disaster risk reduction and management |

*Individuals – a subset Number of Beneficiaries Targeted

One (1) Cross-Cutting Theme (CCT) table should be completed per proposal.  This table should include information for all CCTs:

| Name of CCT | Relevant Sector and Sub Sector | Indicators |
| --- | --- | --- |
| CCT (A) Children | Water, Sanitation, and Hygiene (WASH); Sanitation (Household level) | Number of children assisted |

PROPOSAL OUTLINE

A) Justification

1. Problem Statement

Typhoon Lekima hit several provinces in Vietnam on Wednesday 3 October.  Since then, more than 90 people have been reported as killed or missing.

Thanh Hoa Province in north-central Vietnam was one of the hardest hit by torrential rains and strong winds in the aftermath of typhoon Lekima.  The flooding and landslides in the aftermath of the typhoon caused massive devastation affecting an estimated 140,000 people.  Total damage is estimated at 1,000 billion VND (equivalent to ~US $62 million).

Thousands of people have lost their livelihoods following the storm.  Flood waters inundated over 12,000 ha. of rice paddies, submerged or damaged a further 50,000ha. of farm land and caused the loss of over 70,000 livestock.  Re-establishing livelihoods and ensuring food security for vulnerable populations are critical concerns.

Approximately one third of Thanh Hoa province was covered by flood waters, submerging and contaminating a significant number of wells and clean water systems.  This has led to a shortage of safe drinking water and increased the risk of disease in the flood affected areas.

Along with health clinics, houses and other community buildings, over 530 classrooms in Thanh Hoa were damaged, disrupting classes and destroying teaching equipment and student supplies.  As school buildings are repaired and students return to schools it is necessary to ensure the long term health care needs of children are addressed through the provision of adequate water and sanitation facilities.

The Government of Vietnam is responding, however current needs outweigh the support provided so far and the Government has issued a statement saying that any efforts of international partners are welcomed and appreciated.  Further information on the Government’s response efforts will be presented at a meeting coordinated by the Central Committee of Flood and Storm Control and UNDP on Tuesday 23 October.

2. Needs Assessment Summary

The following information is taken largely from the ‘Joint Rapid Assessment on Damage and Needs in Thanh Hoa Province, Vietnam caused by Typhoon Lekima (No.5)’ Report which was finalized on 12 October.  A targeted needs analysis will be undertaken prior to commencement of the project.

Livelihoods

Rice crop: Planting for the next rice crop will commence in December 2007.  The total area for rice crop in the 22 affected communes of Thach Thanh District of Thanh Hoa Province is 4,100 ha.  Each year a total of 255 tons of rice seed are needed to maximize local output. In the 7 most affected communes 46 tons of rice seed are needed to replace the quantity lost or destroyed as a result of the flooding.

Corn seeds: It is imperative that a quick winter sub-crop can be planted as soon as possible.  There are at least 1500 ha in Thanh Hoa that now require seed for a winter crop.  Local authorities have committed to providing 50% of the cost of necessary corn seed, a quick growing crop with which local farmers are very familiar.  To cover the remaining requirement for corn seed external assistance is required.

CARE has on-going rural development programs in Thanh Hoa.  Staff have a good understanding of local markets and any purchase and distribution of seeds will be done in such a way as to not distort local market systems.  Seed will be purchased locally and land tenure and associated regulations are well established in Vietnam, making it possible to accurately target affected farmers with seeds and quantities through existing district and commune structures.

Water

Water resource pollution: Water for consumption in Thanh Hoa Province comes from wells and stored rain-water. Due to the heavy rain and flooding, open dig wells were polluted. Without chemical disinfection the water from these wells is not suitable for drinking. Some chemicals have been provided by health authorities and this is being used for drinking water however the flood water is being used for washing and all other purposes.  A longer term solution is needed.

12, 2007

Disease occurrence: Interviews with the health officers and the local people found that water-related diseases including red-eye, skin fungus and diarrhea are being reported.  In addition, 90% of local women were experiencing gynecological problems due to the unhygienic living conditions.  It was observed that women, children and elder people were the most affected groups, due to poor resistance status and health sensitivity.

Disaster and Risk Management

According to the Central Committee for Flood and Storm Control (CCFSC), the chief coordinating body responsible for disaster management in Vietnam, Vietnam is one of the most disaster-prone countries in the world. Water-related disasters are the most serious and cause regular and substantial suffering, loss of life and economic damage. On average, 4 to 6 typhoons reach Vietnam each year, and hundreds of people are killed. It is anticipated that the number of heavy storms and typhoons to hit Vietnam will increase both in number and intensity with global warming.  Work with local government and more importantly – communities, on risk management and mitigation is critical to save lives and reduce socio-economic vulnerability to disasters.

3. Justification for Intervention

The Central Committee of Flood and Storm Control reported that Thanh Hoa and Nghe An Provinces were the worst affected by Typhoon Lekima and subsequent flooding.  Immediately following Typhoon Lekima, CARE received requests from the Peoples Aid Coordinating Committee of Vietnam (PACCOM), Thanh Hoa Provincial and District authorities for support.  CARE has responded by providing emergency supplies of rice, blankets, mosquito nets and student kits.  On-going discussion with local authorities and reports from the field indicate that the scale of needs in the wake of this disaster exceeds the level of support that is currently being provided by government and other sources and further assistance is needed.

CARE’s emergency relief efforts so far have focused in Thanh Hoa as CARE is already implementing a number of rural development programs in the area and has well established networks and partnerships with Government and local communities.

CARE has experience implementing Water and Sanitation activities in post-disaster settings and is currently finalising a water and sanitation focused project in Ben Tre Province to assist communities recover from Typhoon Durian in 2006.  CARE will build on its rural development experience to effectively implement agricultural interventions including the purchase and distribution of seed varieties (CP999 corn seed, D527 hybrid rice seed and Q5 rice).

All proposed interventions address needs identified in the Joint Needs Assessment Report (12 October) prepared by a team of INGOs and government personnel and subsequent needs identified by staff in the field through discussions with local authorities and community members.

B) Program Description

1. Program Level

a. Goal: To assist two disaster affected Districts in Thanh Hoa Province recover from Typhoon Lekima.

b. Beneficiaries: Total beneficiaries 69,240.  N.B This is a cumulative total, however the actual number of beneficiaries will be less as there will be overlap of beneficiaries across sectors)

Total: $200,000

c. Critical Assumptions

| Critical Assumptions | Mitigation |
| --- | --- |
| That CARE is not duplicating the activities of Government, civil organizations and other INGOs. | To avoid duplication CARE is liaising closely with key coordinating bodies including the Natural Disaster Mitigation Partnership and Disaster Management Working Group and closely monitoring on-going relief efforts through established networks. |
| That seeds can be distributed before December, to allow planting in time for the next harvest. | Seed distribution and related activities will be prioritized at the beginning of the project. CARE is well established in the target area and will be able to procure and distribute in a timely way. |
| Thanh Hoa Province will not be hit by further storms or natural calamities in the next 6 months. | CARE will carefully monitor meteorological updates for Thanh Hoa. If a storm is imminent, activities will be reassessed and adapted to ensure positive impacts are not mitigated by further disasters. |

d. Program-Level Coordination

If/once approved the Typhoon Lekima Emergency Relief and Rehabilitation’s objective level interventions (Agriculture and Food Security, Water and Risk Reduction) will be coordinated at the central level with the Peoples Aid Coordinating Committee of Vietnam (PACCOM).  PACCOM is a coordinating body tasked with reinforcing the partnership between foreign NGOs and Vietnamese institutions and localities.

CARE is already working closely with Provincial and District authorities in Thanh Hoa Province through it’s current self-resourced emergency relief operations (provision and distribution of rice, household and student kits).  Close liaison and coordination will continue to ensure timely and efficient implementation of activities.

CARE is a key member of the Disaster Management Working Group (DMWG), which supports information sharing and coordination of relief activities in Vietnam.  CARE is actively engaged with this group and is receiving daily updates on relief activities being undertaken by government and other INGOs and civil society organizations.

e. Safety and Security Plan for Program/Field Staff

Generally security is not an issue in Vietnam.  However CARE has nominated Safety and Security Officers in all workstations.  These staff are responsible for monitoring changes in the security situation and ensuring CARE safety policies are adhered to as outlined in the CARE International Safety and Security Handbook.  All staff assigned to this project will receive a safety and security briefing before project commencement.

f. Transition and Exit Strategy

CARE will be informing all the stakeholders, with emphasis on the affected communities, that this is only an emergency, six-month intervention.

Technical advice will be provided with the livelihoods components to ensure the transfer of necessary skills and expertise.  Education and training will accompany the water components to ensure communities have the necessary information and skills required to correctly utilize and maintain these facilities.

CARE has ongoing projects in the target areas which will facilitate staff monitoring and follow up on interventions past the completion of the project.

2. Sector Level

a. Sector

The following sectors have been prioritized for the Typhoon Lekima Emergency Relief and Rehabilitation Project

- Agriculture and Food Security

- Water and Sanitation

- Risk Reduction

b. Objective

| # | Objective | Sector |
| --- | --- | --- |
| 1 | To increase food security | Agriculture and Food Security |
| 2 | To improve access to clean water and sanitation and reduced risk of water-borne diseases | Water and Sanitation |
| 3 | To enhance disaster preparedness and response capacity amongst local partners | Risk Reduction |

c. Dollar Amount

| # | Budget | Sector |
| --- | --- | --- |
| 1 | $70,401 | Agriculture and Food Security |
| 2 | $120,016 | Water and Sanitation |
| 3 | $3,400 | Risk Reduction |

d. Beneficiaries

The Typhoon Lekima Emergency Relief and Rehabilitation Project anticipates assisting the same beneficiaries in each of 3 sectors, as shown in the table below.

| # | Sector | # Beneficiaries Targeted |  |  | # IDP Beneficiaries Targeted |
| --- | --- | --- | --- | --- | --- |
|  |  | Direct | Indirect | Total |  |
| 1 | Agriculture and Food Security | 56,000 | * |  | 0 |
| 2 | Water and Sanitation | 13,000 | * |  | 0 |
| 3 | Risk Reduction | 240 | * |  | 0 |

* Accurate figures could not be collected within the limited timeframe available for proposal submission however CARE will work in 2 communes in Hau Loc District (population 4,082 households, ~ 20,000 people) and 6 communes in Thach Thanh District (population 10,000 households, ~40,000 people).

e. Geographic Areas

The project will be implemented in Thach Thanh and Hau Loc Districts, Thanh Hoa Province, Vietnam.

f. Sector-Level Coordination

Agriculture and Food Security Sector

CARE staff will coordinate with the Provincial Department of Agriculture and Rural Development and local experts on the purchase and distribution of seeds.

Water, Sanitation and Health Sector

CARE staff will collaborate with personnel from the Department of Education to ensure latrines are constructed at schools in a timely and appropriate way.  Before beginning work CARE will liaise with Save the Children who intend to engage in school rehabilitation activities in the flood affected areas.

All activities that relate to the supply of clean water including the distribution of water tanks and cleaning of wells will also be done in collaboration with district and village authorities.

Risk Reduction Sector

Risk reduction activities will be developed in coordination with District People’s Committees with the participation of target communes.

3. Sub-sector Level

| Sector | Sub-Sector |
| --- | --- |
| - Agriculture and Food Security Sector | 1.1 Seed Systems and Agricultural Inputs |
| - Water, Sanitation and Health (WASH) | - Water - Sanitation (Household level) |
| - Risk Reduction | 3.1 Disaster Preparedness, Mitigation and Management |

a. Sub-Sectors

Agriculture and Food Security Sector, Seed Systems and Agricultural Inputs Sub-Sector

Needs Assessment Summary

A joint rapid needs assessment team identified the provision of seeds as a critical issue.  Flood affected communities lost stored and planted seed along with stored food.  While external sources, including government are responding with supplies of rice to meet short term food needs, seeds are required to help communities recover in the mid term.  Seeds are needed before December to ensure planting in time for the next harvest.  Traditional rice seed (one crop per year) will be supplemented with high quality hybrid rice seed (2 crops per year) to ensure mid and longer term food requirements can be met.

Intervention Summary

- Procurement and distribution of 25 ton of rice and 4 ton of corn seeds

- Deliver 25 technical trainings to farmers on agriculture techniques

Technical Design Issues

CARE is established in the target area and CARE staff have a good understanding of local markets and any purchase and distribution of seeds will be done in such as way as to not distort local market systems.  Seed will be purchased locally and land tenure and associated regulations are well established in Vietnam, making it possible to accurately target affected farmers with seeds and quantities through existing district and commune structures.

The proposed rice and corn seed varieties (CP999 corn seed, D527 hybrid rice seed and Q5 rice) are all of high quality and are widely accepted in target areas.  To assure quality, all procurement of seeds will be done in consultation with the consent of the Department of Agriculture and Rural Development (DARD) in Thanh Hoa.

A preliminary distribution plan has been developed however final distribution will be based on a targeted analysis of farmer needs if/once funding is approved.

Water, Sanitation and Health Sector, Water and Sanitation (Household Level) Sub-Sector

Needs Assessment Summary

Flood waters inundated homes and water supply systems severely restricting access to clean water for drinking.  Community wells are now contaminated with mud and debris and the water in these wells is unfit for use.  The Joint Rapid Needs Assessment team reported that as a result of dirty drinking water and unsanitary conditions in the wake of the flooding incidences of water-related diseases are increasing.  Existing water supply options require cleaning and rehabilitation.

To improve water and sanitation conditions for children in the affected areas, CARE proposes to construct latrines at 10 schools.  As the damage to school buildings caused by flooding is being repaired, it is an ideal time to work with Education authorities to construct latrines, which otherwise may not be provided, and begin educating teachers and students and local authorities on the necessity for and benefits of toilet facilities for children.

Intervention Summary

- Provision of 1,000 water filters and 600 water storage tanks

- Cleaning and rehabilitation of 400 contaminated shallow (open) wells

- Training to local authorities and target communities on clean water storage

- Construction of blocks of latrines at 10 flood affected schools. Construction of latrines will include water system, water pump and latrine blocks will be split to accommodate boys and girls separately.

- Training for teachers and students on correct use and maintenance of latrines, including good hygiene practices.  CARE has existing IEC materials for this purpose.

Technical Design Issues

Wells and water supply systems are being cleaned and rehabilitated, no new water supply structures are proposed.  All construction materials for this purpose and for the construction of latrines are available locally.  Staff are available to work in the target areas and are familiar with the existing water supply systems.  Requests to rehabilitate water supply systems have been received through Government channels and are therefore supported by the National Government.

Water filters and water storage tanks are also available locally and are in regular use by target populations.

Risk Reduction Sector, Disaster Preparedness, Mitigation and Management Sub-Sector

Needs Assessment Summary

Vietnam is prone to natural disasters and is hit by an average of 4 – 6 typhoons every year.  Thanh Hoa is located in central Vietnam, an area particularly prone to typhoons and flooding.  Floods may result in a loss of lives, housing, crops and livestock, damage infrastructure and an increased incidence of water-related disasters.

Government has invested significant resources in the provision of structural disaster management measures (eg. dykes, roads) and the development of effective emergency evacuations plans procedures.  A focus on preparedness is, to date lacking and community based disaster risk management (CBDRM) has proven to be a useful and effective way of introducing the concept of preparedness to communities.

It is an important mechanism for raising awareness among communities and local authorities on how best to prepare for and mitigate the negative impacts of flood and storms.  CARE has ongoing projects focused on or including CBDRM components and is well placed to incorporate this as part of its disaster response activities.

Intervention Summary

- 8 Introductory workshops on disaster risk management for local authorities and community representatives.

Technical Design Issues

CARE's experience in the affected areas so far indicates that local authorities and communities will be willing to participate in workshops to reduce their vulnerability to natural disasters.  Commitment to these activities is likely to be strengthened as the negative consequences of Typhoon Lekima are still being felt by populations in the target areas.

Government structures down to commune level are well established and staff have the capacity to actively participate in such workshops and the capacity to implement ongoing local disaster management plans once initiated.

b. Beneficiary Description

Demographics of target population at sub-sector level are not yet known.  This information will be collected as part of a baseline survey which will be conducted prior to implementation.

c. Indicators

The Typhoon Lekima Relief and Rehabilitation Project will utilize the following indicators. All are selected from the Dec 2006 USAID/OFDA Guidelines Summary Table.

1. Agriculture and Food Security Sector/Seed Systems and Agricultural Inputs Sub-Sector

1.1 Number and percent of seed recipient farmers with sufficient seeds to plant fields for next agricultural seasons

2a. WASH Sector/Water Sub-Sector

2a.1 Number of beneficiaries receiving water from protected water points

2b. WASH Sector/Sanitation (Household level)

2b.1 Number of communal/institutional latrines constructed

3. Risk Reduction Sector/ Disaster Preparedness, Mitigation and Management

3.1 Number of people trained in disaster risk reduction and management

4. Cross-Cutting Themes

a. Program Integration

The Typhoon Lekima Relief and Rehabilitation Project will address children as a cross-cutting theme.  Children will benefit from all interventions however they will benefit most directly from the construction of latrines at school and accompanying information and education on improved water and sanitation practices.

| Name of CCT | Indicators |
| --- | --- |
| CCT (A) Children | No of children assisted |

C) Monitoring and Evaluation

1. Monitoring Plans

CARE Vietnam staff based in the province will work closely with local authorities and targeted communities to monitor and assist with management and logistics for relief distribution and rehabilitation planning and assistance.

The Disaster Management Coordination Unit based in Hanoi, will travel to the project site for additional monitoring. Time has also been set aside for finance and administration staff to provide appropriate levels of support.

The following is the Typhoon Lekima Emergency Relief and Rehabilitation Project monitoring plan.

| Objectives | Indicators & Targets | Data Collection |  |  | Data Analysis & Report |  |  | Sources | Feedback |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Collection Methods | Frequency | Responsibility | Frequency |  | Responsibility |  | Frequency | Responsibility |
| Program Goal To assist two disaster affected Districts in Thanh Hoa Province recover from Typhoon Lekima. | Project Startup 0.1 Project HQ established within two weeks of project approval (100%) 0.2 CAREVN staff recruited to facilitate a rapid start up (temporary staff, vehicles, equipment, technical advice etc) (100%) 0.3 Project is providing critical assistance (seeds, water sanitation etc) 1 week after project approval (100%) | Approved Project document/ HR data base/ Monitoring visit/ | Beginning/middle, and end of project | CAREVN emergency staff | Beginning, middle and end of project |  | CAREVN Disaster Management Coordinator, with assistance from TLER Program Manager | Project startup plan that includes outputs, targets, date and other important comments Weekly status reports to Country Director and he will inform OFDA of general project status Final startup report to Country Director | Beginning of project Weekly for two months End of month two | CAREVN Disaster Management Coordinator CAREVN Disaster Management Coordinator CAREVN Disaster Management Coordinator |
| Project Objective 1 To increase food security in Thanh Hoa Province | Increase distribution of seeds to 35,000 beneficiaries (Targets to be determined per rapid village assessments/ baseline process to ensure approximately equitable distribution among the beneficiary population) 1.1 number and percent of seed recipient farmers with sufficient seeds to plant fields for next agricultural seasons | Use information gathered in assessment report as base line. Field visit interviews Other data will be recorded during seed distribution (e.g. amount of seeds given per group) compiled and analyzed for final M&E report. | Ongoing data collection | CAREVN emergency staff | Monthly reports submitted to Country Director |  | CAREVN Disaster Management Coordinator | Monitoring by staff and discussions with local authorities Activity records–based on project outputs kept by project staff. | Beginning, middle and end of project Ongoing data collection | CAREVN Disaster Management Coordinator CAREVN emergency staff |
| Project Objective 2 To improve access to clean water and sanitation and reduced risk of water-borne diseases | 2.1 number of beneficiaries receiving water from protected water points. 2.2 number of communal/ institutional latrines constructed. | See output 1, above except information will be gathered on improve access to water. | See Output 1 above. | See Output 1 above. | See Output 1 above. |  | See Output 1 above. | See Output 1 above. | See Output 1above. | See Output 1 above. |
| Project Objective 3 To enhance disaster preparedness and response capacity by local authorities and communities | 3.1 number of people trained in disaster risk reduction and management. | See output 1, above except information will be gathered on number of people trained in disaster risk reduction | See Output 1 above. | See Output 1 above. | See Output 1 above. | See Output 1 above. |  | See Output 1 above. | See Output 1 above. | See Output 1 above. |
| Project Closure 4 Effective closure of program | 4.1 Project reports submitted to donor | Project implementation plan check list. Planned versus actual spending, outputs per baseline and month project reports. |  |  |  |  |  |  | Within one month of project end | CAREVN Disaster Management Coordinator |

2. Evaluation Plan

The final evaluation will be conducted within one month of the end of the project. The baseline and final evaluation reports will be conducted by a CAREVN staff. A final end-of-project report will be compiled by CAREVN Disaster Management Coordinator and submitted to OFDA within 1 month of the end of project. This report will highlight lessons learned which than can be utilized by other CAREVN emergency projects in the future.

The following is the Typhoon Lekima Emergency Relief and Rehabilitation Project evaluation plan.

| Objectives | Indicators | Means of Verification | Outputs & Responsibility | Sources | Timing |
| --- | --- | --- | --- | --- | --- |
| Project Goal To assist two disaster affected Districts in Thanh Hoa Province recover from Typhoon Lekima. | 0.1 development of disaster mitigation plans by local authorities | Baseline and Final project surveys | Consultant, project staff, with involvement of target population and other stakeholders. | Baseline survey, mid-project review, and final project evaluation | Mid-Term Report: 3 months after project start up Final Project Report: one month after project ends. |
| Project Objective 1 The target population receives enhanced food security. | 1.1Procurement and distribution of 25 ton of rice and 4 ton of corn seeds 1.2 Deliver 25 technical trainings to farmers on agriculture techniques | Standard sampling methods will be employed USAID/OFDA requirements will be incorporated in the survey design in every possible degree. | See above Outputs and responsibility | See above sources | See above goal (baseline, mid-term, and final assessments). |
| Project Objective 2 The target population has more sustainable water sources. | 2.1 number of beneficiaries receiving water from protected water points. 2.2 number of communal/ institutional latrines constructed. | Visual survey of before the project will be conducted. | See above Outputs and responsibility | See above sources | See above goal |
| Project Objective 3 The target population has builds capacity in disaster response preparedness. | 3.1 number of people trained in disaster risk reduction and management. | Field visit interviews | See above Outputs and responsibility | See above sources | See above goal |
| Cross-Cutting Themes | 1. Children: % of children assisted in disaster relief |  |  |  |  |

# Appendices 1 (Required)

This section includes all required supporting information

Appendices 1 Contents

4.1	Documentation on Ineligible and Restricted Goods, 
Services, and Countries

4.1.1	Ineligible Goods and Services

4.1.2	Ineligible Suppliers

4.1.3	Restricted Goods

4.2	Budget Narrative

4.3	Detailed Itemized Budget

4.4	Branding Strategy and Marking Plan

4.5	SF-424

4.6    Completed/Signed Certifications and Representations

4.7	Required Supporting Administrative Documentation

4.7.1	Organizational Structure

4.7.2	Accountability

4.7.3	Cost Sharing and In-Kind Contributions

4.7.4	Sub-Award Arrangements

4.7.5	Past Performance References

4.7.6	Self-Certification for Compliance With USAID Policies and Procedures- See Attached

4.7.7	U.S. Government Negotiated Indirect Cost Rate Agreement

4.7.8	Project Income

4.7.9	Pipeline Analysis

4.7.10	New Vendor Information Form

## 4.1 Documentation on Ineligible and Restricted Goods, Services, and Countries

#### 1. Ineligible Goods and Services

CARE certifies that the Project Budget does not include any Ineligible Goods and Services as defined in the USAID/OFDA Guidelines for Unsolicited Proposals and Reporting (Dec 2006). Specifically the project budget does not include: military equipment; surveillance equipment; commodities and services for support of police or other law enforcement activities; abortion equipment and services; luxury goods and gambling equipment; weather modification equipment.

#### 2. Ineligible Suppliers

CARE certifies that the Project will not procure goods or services furnished by firms or individuals whose names appear on the “List of Parties Excluded From Federal Procurement and Non-procurement Programs,” as listed on the website: http://epls.arnet.gov/ per the General References Section of the USAID/OFDA Guidelines for Unsolicited Proposals and Reporting (Dec 2006).

In addition, CARE certifies that as a function of this project design and proposal preparation process, it has reviewed the list of specially designated nationals and blocked persons designated by the Office of Foreign Assets Control, U.S. Department of Treasury, and listed in the OFAC website: www.ustreas.gov/ofac per the General References Section of the USAID/OFDA Guidelines for Unsolicited Proposals and Reporting (Dec 2006).

3. Restricted Goods

CARE certifies that the following Restricted Goods will not be procured in the Typhoon Lekima Relief and Rehabilitation Project: Vehicles not manufactured in the U.S., pharmaceuticals, pesticides, fertilizers, used equipment, US Government-owned excess property.

However, CARE intends to procure three widely accepted and high quality seed varieties for this project:

- CP999 corn seed

- D527 hybrid rice seed

- Q5 traditional rice seed

To further assure quality, all procurement of seeds will be done in consultation and with the consent of  the Department of Agriculture and Rural Development (DARD).

CARE will therefore request approval from USAID/OFDA prior to procurement of said seedsas required per the USAID/OFDA Guidelines for Unsolicited Proposals and Reporting (Dec 2006).

## 4.2 Budget Narrative

The Typhoon Lekima Emergency Relief & Rehabilitation Project budget is described below, as necessary, for each budget category.

- International Staff

  - An international project manager/ emergency co-ordinator will be utilized for the project for 10 days (or approximately 5%).  The project manager will be responsible for overall project and personnel management, including ensuring the project is on schedule and within budget with respect to the project implementation plan outlined in this proposal, overseeing logistical support and preparation of donor reports.

  - The CARE-VN Country Director based in Hanoi, will contribute a minimum of 5 working days (or 3%) of his time to the project mainly focusing on contract compliance government liason and donor representation.

  - The CARE VN Deputy Director Finance and Administration based in Hanoi will contribute a minimum of 5 working days to the implementation of the project ensuring that donor reporting and procurement guidelines are adhered to.

- National Staff

In addition to the expatriate staff positions described above, the project will utilize:

  - A full time Project Manager will be responsible for the day to day implementation of the project as well as liaising/coordinating with local authorities.

  - A full time Project officer – for the organization of logistics and monitoring of field activities in the target communities.

- Non-Employee Labor

  - CARE will utilize local day labor to assist with the distribution of seed and rice.  The local labor will receive around 50,000 VND per day.

- Travel and Transport

  - CARE staff will be required to either rent a vehicle or use its own vehicle when traveling to the field.  The cost of renting a vehicle is approximately $60 per day.

  - Per diem has been budgeted at Hanoi based  staff when they travel to the project area this has been based on approximately 75% of time for project staff in the field.

- Project Supplies

Project Supply costs have been carefully estimated based on CARE-Vietnam experience in previous and ongoing relief and development initiatives in the region, as well as commune populations, approximate distances between -and access to- the target villages, and the agro-ecology of the target areas.

  - Rice and maize seeds required to resume agricultural activities and ensure next crop are considered in the Objective 1 (Seeds systems & Agricultural Input) The cost is USD 46,100. These calculations are based on previous experience and current prices at local market in the affected province. A 7% allowance has been made to allow an increase of the rice and maize seeds price due to seasonal high demand. Thus the Metric Ton of high-yield D527 rice seed comes to USD 2,000, the ton of traditional Q5 rice seed is USD 650, and the ton of high-yield CP999 corn seed is 2,400.

  - Water tanks and filtration devices are required to store rain water running of the roof and to reduce the occurrence of water-born diseases due to drinking water pollution. They are the Objective 2 (WASH). Cost is USD 88,094. Unit price is USD for village produced, 2 cubic meter, concrete water tanks including pipes, roof gutter, lid is USD 50. It is produced inside the affected village and generates labour income. The filters are produced in Vietnam under Korean license and cost USD 17 each.  This cost is valid for bulk purchase as was demonstrated in previous post flooding relief operations.

  - Rehabilitation/decontamination of shallow wells (also Objective 1) costs usually USD 25 per well as was determined in past operations. Very little construction material is involved. Mostly manpower is needed to clean up and rehabilitate. Total requested is USD10,000 for 400 wells. That is USD 25 per well.

  - School Latrines have been built in other rural development projects implemented by CARE Vietnam. We will use the same design. The whole school building latrine costs USD 3,566. We plan to build 9 units for a total of USD 32,094.

- Other Direct Costs

  - Rice Technical Training: Training is necessary to properly use the high-yield crop contemplated. They are not new to the users but it is better to make sure that farmers are fully aware of the particularities of those seeds. Therefore, 25 training sessions are foreseen in the communes and hamlets. Each training session costs no more than USD 80 for training material, refreshments, venue renting, and miscellaneous.  The total for this activity under objective 1 is USD 2,000.

  - CBDRM training: The Community Based Disaster Reduction Management awareness sessions under objective 3 cost USD 400 per commune considered. The cost is all-inclusive: venue, IEC material, training material, refreshment, stationary, etc.

  - Latrine User training: In the remote areas of the province where the project is to be implemented, flush latrines are somewhat a new concept: training on use and maintenance will ensure a longer lifetime to the building and facilities. We plan one training session to students and users in each school. Each session costs USD 400 and includes everything necessary. For 10 schools the cost becomes USD 4,000.

  - Office Rental and Utilities, Office supplies, Communications, and other related operation costs are allocated to the project as a proportion of overall costs.  These are estimated at approximately 3% of total costs.

- USAID Branding and Marketing

  - The project has budgeted $1000 to pay for “USAID/CARE” branded t-shirts for local labor and branding of distribution items for beneficiaries.

- Indirect Costs

  - The NICRA total for the Project is $13,232 based on the standard 7.25 percent rate.

- Total Project Cost Per the above, the total project cost is $200,000.

4.3 Detailed Itemized Budget – See Attached & Below

| Proposal Budget for OFDA Funding in response to Typhoon Lekima |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total |  |  |  |  |  |  |  |
|  |  |  | OFDA |  |  | Other |  |  | Project Total |  |
| Object Class Category | Qty | Unit (Days, Mos., Trips, Etc.) | No. of Units (E+K) | Notes no. of units | Amt (US$) (G+M) | No. of Units (H+N) | Notes no. of units | Amt (US$) (J+P) | Amt (US$) (S+V) |  |
| 1. Salaries |  |  |  |  |  |  |  |  |  |  |
| 1.1 Field Staff |  |  |  |  |  |  |  |  |  |  |
| 1.1.1 Expatriates |  |  |  |  |  |  |  |  |  |  |
| Emergency Officer | 1 | Days | 10 |  | $3,710 | 0 |  | $- | $3,710 |  |
| Country Director | 1 | Days | 6 | (0.08 FTE) | $1,806 | 0 |  | $- | $1,806 |  |
| Country Financial Officer | 1 | Days | 6 | (0.04FTE) | $1,806 | 0 |  | $- | $1,806 |  |
| 1.1.1 -SUBTOTAL: Expatriate Field Salaries |  |  | 22 |  | $7,322 | 0 |  | $- | $7,322 |  |
| 1.1.2 Local Staff |  |  |  |  |  |  |  |  |  |  |
| Project Manager | 6 | Months | 6 |  | $5,870 | 0 |  | $- | $5,870 |  |
| Project Officer | 6 | Months | 6 |  | $3,549 | 0 |  | $- | $3,549 |  |
| Finance and Admin staff | 6 | Months | 6 |  | $4,505 | 0 |  | $- | $4,505 |  |
| 1.1.2 -SUBTOTAL: Local Field Staff |  |  | 18 |  | $13,923 | 0 |  | $- | $13,923 |  |
| 1.1 -SUBTOTAL: Field Staff |  |  | 40 |  | $21,245 | 0 |  | $- | $21,245 |  |
| 1.2 Headquarters Staff |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Months | 0 |  | $- | 0 |  | $- | $- |  |
| 1.2 -SUBTOTAL: HQ Staff |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 1. – Total: Salaries |  |  | 40 |  | $21,245 | 0 |  | $- | $21,245 |  |
| 2. Fringe Benefits |  |  |  |  |  |  |  |  |  |  |
| 2.1 Non-Local Staff @ 30% of Salaries (Field and HQ) |  |  | 10460 | (Field Expat @ $145,000 + HQ Staff @ $8,500) | $3,138 | 0 |  | $- | $3,138 |  |
| 2.2 Local Staff @ 9% of Salaries (Field) |  |  | 15300 |  | $1,377 | 0 |  | $- | $1,377 |  |
| 2. – TOTAL: Fringe Benefits |  |  | 14,605 |  | $4,515 | 0 |  | $- | $4,515 |  |
| 3. Non-Employee Labor |  |  |  |  |  |  |  |  |  |  |
| Local distribution labour | 320 | days | 320 |  | $1,000 | 0 |  | $- | $1,000 |  |
| 3. – TOTAL: Non-Employee Labor |  |  | 320 |  | $1,000 | 0 |  | $- | $1,000 |  |
| 4. Travel and Transport |  |  |  |  |  |  |  |  |  |  |
| 4.1 International (Non-Regional) Air Travel |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 4.1 – SUBTOTAL: International (Non-Regional) Air Travel |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 4.2 International Per Diem |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 4.2 – SUBTOTAL: International (Non-Regional) Per Diem |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 4.3 International (Regional) Air Travel |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 4.3 – SUBTOTAL: International (Regional) Air Travel |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 4.4 International (Regional) Per Diem |  |  |  |  |  |  |  |  |  |  |
| 4.4 - SUBTOTAL: International (Regional) Per Diem |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 4.5 In-Country Air Travel |  |  |  |  |  |  |  |  |  |  |
| 4.5 – SUBTOTAL: In-Country Air Travel |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 4.6 In-Country Ground Travel |  |  |  |  |  |  |  |  |  |  |
| Project Manager |  | Days | 24 |  | $1,560 | 0 |  | $- | $1,560 |  |
| Project Officer |  | Days | 12 |  | $840 | 0 |  | $- | $840 |  |
| 4.6 – SUBTOTAL: In-Country Ground Travel |  |  | 36 |  | $2,160 | 0 |  | $- | $2,160 |  |
| 4.7 In-Country Per Diem |  |  |  |  |  |  |  |  |  |  |
| Project Manager |  | Days | 102 |  | $3,472 | 0 |  | $- | $3,472 |  |
| Project Officer |  | Days | 102 |  | $3,472 | 0 |  | $- | $3,472 |  |
| 4.7 -SUBTOTAL: In-Country Per Diem |  |  | 204 |  | $6,324 | 0 |  | $- | $6,324 |  |
| 4.8 Transport of Goods |  |  |  |  |  |  |  |  |  |  |
| Truck Rental |  | Days |  |  |  | 0 |  | $- | $- |  |
| 4.8 – SUBTOTAL: Transport of Goods |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 4. – TOTAL: Travel & Transport |  |  | 240 |  | $9,344 | 0 |  | $- | $9,344 |  |
| 5.Overseas Allowances |  |  |  |  |  |  |  |  |  |  |
| 5.1 Housing |  |  |  |  |  |  |  |  |  |  |
|  |  | Months | 12 |  | $- | 0 |  | $- | $- |  |
| 5.1 – SUBTOTAL: Housing |  |  | 12 |  | $- | 0 |  | $- | $- |  |
| 5.2 Danger Pay |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 5.2 – SUBTOTAL: Danger Pay |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 5. – TOTAL: Overseas Allowances |  |  | 12 |  | $- | 0 |  | $- | $- |  |
| 6. Program Supplies |  |  |  |  |  |  |  |  |  |  |
| Seeds system and Agricultural Input |  |  | 0 |  |  | 0 |  | $- | $- |  |
| CP999 corn seed | 4 | ton | 4 |  | $9,600 | 0 |  | $- | $9,600 |  |
| D527 Rice seed | 15 | ton | 15 |  | $30,000 | 0 |  | $- | $30,000 |  |
| traditional rice | 10 | ton | 10 |  | $6,500 | 0 |  | $- | $6,500 |  |
| Water and Sanitation |  |  |  |  |  |  |  |  |  |  |
| Water tanks | 600 | tanks | 600 |  | $30,000 | 0 |  | $- | $30,000 |  |
| water filters | 1000 | units | 1000 |  | $16,000 | 0 |  | $- | $16,000 |  |
| Well rehabilitation | 400 | wells | 400 |  | $10,000 | 0 |  | $- | $10,000 |  |
| School Latrines | 9 | schools | 9 |  | $32,094 | 0 |  | $- | $32,094 |  |
| 6. – TOTAL: Program Supplies |  |  | 2,038 |  | $134,194 | 0 |  | $- | $134,194 |  |
| 7. Other Direct Costs |  |  |  |  |  |  |  |  |  |  |
| Rice Technical training | 25 | training | 25 |  | $2,000 | 0 |  | $- | $2,000 |  |
| CBDRM training | 8 | training | 0 |  | $3,200 | 0 |  | $- | $3,200 |  |
| Latrine user training | 10 | training | 10 |  | $4,000 | 0 |  | $- | $4,000 |  |
| Office Rent | 1 | Months | 6 |  | $2,370 | 0 |  | $- | $2,370 |  |
| Office Supplies |  | Months | 6 |  | $900 | 0 |  | $- | $900 |  |
| Office Utilities |  | Months | 6 |  | $540 | 0 |  | $- | $540 |  |
| Communications |  | Months | 6 |  | $600 | 0 |  | $- | $600 |  |
| Other office operations |  | Months | 6 |  | $1,860 | 0 |  | $- | $1,860 |  |
| Vehicle |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 7. – TOTAL: Other Direct Costs |  |  | 0 |  | $15,470 | 0 |  | $- | $15,470 |  |
| 8. Staff Training |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 8.- TOTAL: Staff Training |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 9. USAID Branding and Marking |  |  |  |  |  |  |  |  |  |  |
| T-shirts and markings on relief items |  |  | 0 |  | $1,000 | 0 |  | $- | $1,000 |  |
| 9. – TOTAL: USAID Branding and Marking |  |  | 0 |  | $1,000 | 0 |  | $- | $1,000 |  |
| 1-9 SUBTOTAL |  |  | 17,255 |  | $186,768 | 0 |  | $- | $186,768 |  |
| 10. Contractual/Sub-Awards |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 4 |  | $- | 0 |  | $- | $- |  |
| 10. – TOTAL: Contractual/ Sub-Awards |  |  | 4 |  | $- | 0 |  | $- | $- |  |
| 1-10 - SUBTOTAL |  |  | 0 |  | $186,768 | 0 |  | $- | $186,768 |  |
| 10A. Contractual/Sub-Awards Included in Indirect Cost Base |  |  | 0 |  |  | 0 |  | $- | $- |  |
|  |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 10A. - SUBTOTAL: Contractual/Sub-Awards Included in Indirect Cost Base |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 1-10A –SUBTOTAL: Indirect Cost Base |  |  | 0 |  | $186,768 | 0 |  | $- | $186,768 |  |
| 11. Indirect Costs |  |  |  |  |  |  |  |  |  |  |
| 11. – SUBTOTAL: Indirect Costs |  | NICRA | 182508 |  | $13,232 | 0 |  | $- | $13,232 |  |
| 12. – 1-11 SUBTOTAL |  |  | 0 |  | $200,000 | 0 |  | $- | $200,000 |  |
| 12. Equipment > $5,000 |  |  | 0 |  |  | 0 |  |  |  |  |
|  |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| Total Estimated Amount Excluding A-133 Audits |  |  | 0 |  | $200,000 | 0 |  | $- | $200,000 |  |
| 13. OMB Circular A-133 Audits |  |  |  |  |  |  |  |  |  |  |
|  |  | All costs subject to A-133 audit | $- |  | $- | 0 |  | $- | $- |  |
| Total Estimated Amount |  |  | 0 |  | $200,000 | 0 |  | $- | $200,000 |  |
| 14. Pipeline (Required for modifications; not required for new awards) |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 0 |  | $- | 0 |  | $- | $- |  |
|  |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 14. – SUBTOTAL: Pipeline |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| New OFDA Funds Requested |  |  | 0 |  | $200,000 | 0 |  | $- | $200,000 |  |
| 16. Program Income |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| 17. Unallow-able Host Country Taxes |  |  | 0 |  | $- | 0 |  | $- | $- |  |
| TOTAL PROGRAM |  |  | 0 |  | $200,000 | 0 |  | $- | $200,000 |  |

Funding from Other Sources

  - Concurrently with the preparation of this proposal CARE- Vietnam is seeking funding from other sources to enhance project activities and/or expand coverage. To date CARE Vietnam has a further commitment of USD 98,928 for immediate emergency relief.

4.4  Branding Strategy and Marking Plan- See Attached

The Typhoon Lekima Relief and Rehabilitation project has budgeted $1,000 to pay for “USAID” Standard Graphic identifying stickers and banners for all the CARE project vehicles, signage to be posted at significant rehabilitated water catchments, as well as other water collection and storage structures. The new “USAID” Standard Graphic will also be placed on seed packaging provided to the target villages, using stickers or stenciling, as appropriate.  Provincial and district authorities and target communities will be informed that the funding is being provided by USAID.

4.5 SF-424- See Attached

4.6 Completed/Signed Certifications and Representation- See Attached

4.7 Required Supporting Administrative Documentation

1. Organizational Structure

CARE-Vietnam will provide oversight and support to the Typhoon Lekima Relief and Rehabilitation Project at several levels. If/once approved CARE will recruit two national staff members to manage and administer this project.  Critical support will be provided by staff members assigned to on-going projects in the target area.  Both Project Manager and Project Officer will be based in Hanoi but will spend 75% of their time in the target areas.

The Disaster Management Coordinator will be providing extensive support and oversight to this program.  Further support and technical advice will be Rural Development Coordinator in Hanoi.

### ORGANIZATION STRUCTURE OF CARE INTERNATIONAL IN VIETNAM – AUGUST 2007

#### Country Director

Deputy Director

Finance & Administration

Finance & Admin

Admin Officer

Admin  Assistant

Driver

Cleaner

HR Manager

HR Assistant

Translator

HCMC

Office

Manager

- Finance Officer

- Admin Officer

- Cleaner

- Guard

- Guard

Finance Manager

Accountants

## Deputy Director

## Programs

Rural Development Coordinator

Project Manager

Project Team

CRND Team Leader

Project Teams

Community Health Program  Coordinator

Health Project Managers (3)

Project Teams

AI Coordinator

AI Project Managers

PACODE

Team Leader

Rural Prog. Manager am Manager

Disaster Managem/t Coordinator

Water/ SanitationTeam Leader

Cross – Cutting

Positions

Project

Managers

Project Teams

Project Manager

Project

Managers (8)

Health training & IEC Specialist

Assessment & Participation Specialist

Gender & Diversity Specialist

Project

Manager

Project Team

Project Teams

Project Teams

2. Accountability

This will certify that CARE-International has written management plans, guidelines, and provides training that ensure staff members adhere to international humanitarian laws, codes of ethics, and standards of practice.

3. Cost Sharing (Matching) and Inkind Contributions- None

4. Sub-award Arrangements

CARE does not anticipate utilizing sub-award mechanisms in this project.

5. Past Performance References

| Project/Country | Donor | Contract No/ Type/Amount/ Term | Contact Info | Description |
| --- | --- | --- | --- | --- |
| Support, Basic Relief & Assistance for IDP Camps in East Timor | USAID | Contract No. DFD-G-00-06-00189-00 Contract Type: Cooperative Agreement Contract Value: $683,602 Term: 06//01/06-12/31/07 | Joseph Lentini jlenini@usaid.gov | Through the provision of basic relief supplies, service delivery and technical support, ensure that minimum basic living standards and safety for IDPs are achieved during their asylum in the centers and support to communities contributes to the process of reintegration. |
| Improving the Health and Nutrition Status of Children in Malema and Nampyla-Rapale Districts Mozambique | USAID | Contract No. Contract Type: Cooperative Agreement Contract Value: $1,300,000 Term: 10/01/01-9/30/06 | Susan Youll Tel: (202) 712-1444 Syoull@usaid.gov | Aims to improve Ministry of Health (MOH)’s capacity and organizing communities for health education and mobilization to create demand for services. |
| Community Led Innovation in Drought Preparedness & Mitigation Vietnam | USAID | Contract No. DFD-A-00-06-00150-00 Contract Type: Cooperative Agreement Contract Value: $347,414 Term: 9/14/2007-9/13/2008 | Robert Thayer rthayer@usaid.gov Robert Barton rbarton@usaid.gov | The enhancement of target communities’ capacity to undertake community based preparedness planning while also developing expertise in range of low cost and innovative drought mitigation and preparedness technologies. |
| Community Resilience to Natural Disasters in Mekong Delta (CRND) Vietnam | AusAID | Contract No. EOL 09791/30 Contract Value: AUD5,621,662 Term: 6/05 – 11/09 | Ms Nguyen Phuoc Nghi Dung Ph: 84.8.296035 | This project seeks to empower flood-prone communities in the proposed intervention areas to reduce the impact of natural disasters and secure and enhance their livelihoods. The project includes structural and non-structural measures that will be determined by communities in the design phase, and seed funding which will be provided through the project. The project also aims to strengthen the capacity of and reorient existing disaster management institutions to assist these communities by becoming more responsive to the short and longer term needs of the most vulnerable. |

6. Self-certification for Compliance with USAID Policies and Procedures for Personnel, Procurement, Property management, and Travel (U.S. NGOs only)- See Attached

7. U.S. Government Negotiated Indirect Cost Rate Agreement (NICRA)- See Attached

8. Program Income

The Typhoon Lekima Relief and Rehabilitation Project will not realize income/cost-recovery or other revenues.

9. Pipeline Analysis (Award Modifications Only)

This is a new award application, therefore a pipeline analysis is not required.

10. Restricted Goods- See Above 4.1

11. New Vendor Information Form (if the applicant has never received USAID awards.)

CARE has received USAID awards previously; therefore this form is not required.