## Лист1
CARE Tajikistan Winter Emergency Response Proposal (for immediate life saving purposes) Attachment 1
Detailed Implementation Plan (DIP)
Key Activities | 1st week | 2nd week | 3rd week | 4th week | 5th week | 6th week | 7th week
Preparation activities
Staff recruitment and orientation.
Orientation meetings with relevant G0T officials
Selection of the beneficiaries
Preparation of list of beneficiaries and distribution plan
Carry out beneficiary survey (for validation purposes only)
Procurement of required items
Procurement of required medicines for mobile team.
Procurement of petrol for generators.
Printing of the visibility logos
Translation and printing of recommendations on use of generators.
Distribution of humanitarian aid
Support of the poorest clients of Micro Lending Foundation HUMO through emergency microcredit fund
Distribution and installation of generators
Distribution of petrol for generators
Training on use of generators.
Medical mobile teams visit remote areas for provision of emergency medical services
Distribution of cash to 2700 targeted beneficiaries
Monitoring for use of provided assistance (cash, generators) and their impact.
Post distrubution survey
Preparation and submission of financial and narrative reports