| Disasters Emergency Committee | DISASTER RESPONSE PROGRAMME PHASE 1 PLAN (narrative) |
| --- | --- |
|  | The purpose of the Phase 1 Plan submission is to: - enable member agencies to set out their DEC appeal disaster response plans and budget - form the basis for monitoring, evaluation and accountability - provide early evidence of the disaster response to public external audiences as appropriate - To identify and assess risks to a quality disaster response |
|  | 28TH February 2010 |

| Appeal Name | HAITI EARTHQUAKE APPEAL |
| --- | --- |
| Agency Name | CARE International UK |
| Agency Contact Details Head Office: - Name - Position - Telephone - Email - Fax | Kate Akhtar Senior Emergency Programme Officer +44 (0)207 934 9314 akhtar@careinternational.org +44 (0)207 934 9335 |
| Agency Contact Details In Country: - Name - Position - Telephone - Email - Fax | Sophie Perez Country Director CARE-Haiti perez@pap.care.org Tel: (509) 2257 3573 |

| Return this form to: | Annie Devonport Humanitarian Programme Adviser email: adevonport@dec.org.uk |
| --- | --- |
| Return this form by: | 28th February 2010 |

| Completed by | Kate Akhtar |
| --- | --- |
| Job title | Senior Emergency Programme Officer |
| Reviewed by | Audrée Montpetit |
| Job title | CARE Haiti Proposal writer |
| Date submitted to Secretariat | February 26, 2010 |

| Phase 1 Plan Components Checklist Before submitting to the Secretariat all components must be included |  |
| --- | --- |
| Component | Check? |
| - Phase 1 Plan narrative: Form 6 | √ |
| - Phase 1 Plan financial: Form 7 | √ |
| - Generic Appeal Risk Register: Form 4 | √ |
| - Media: case studies to bpaddy@dec.org.uk | √ |

Section 1: Overall Member Agency Programme

For multi country responses provide a regional overview

A Context and Analysis

1. What is your analysis of the nature and scale of humanitarian need? (Please review your analysis in your Hotspot Information Service and Individual Agency Position form (DEC Forms 1 & 2)

On Tuesday, January 12th, 2010, an earthquake with a magnitude of 7.0 struck Haiti, with its epicentre located approximately 25 kms west of Port-au-Prince, the country’s capital. Buildings across the city collapsed or were extensively damaged, including the main hospital, Presidential Palace, UN HQ, schools and homes. The most affected areas were Léogâne (population 134,000) with a level of destruction of 80-90%, Carrefour (population 334,000) with a level of destruction of 40-50% and Jacmel (population 34,000) with a level of destruction of 50-60%. The overall population living in the earthquake affected areas is estimated at more than five million people. As of February 10, the Government of Haiti, OCHA and other UN agencies have confirmed 212,270 dead, over 300,000 injured, 692,000 displaced in Port-au-Prince only, and a total of 1.2 million people displaced. As of February 15, it is estimated that 511,405 people have left the earthquake-affected areas for different departments throughout the country, with the majority of arrivals in Artibonite (162,509 arrivals), Centre (90,997 arrivals), GrandAnse (55,167 arrivals), and North West (45,862). This number may continue to rise in the following weeks since approximately 50 percent of people in Port-au-Prince have family in other parts of the country. This situation is putting further pressure on already limited resources and service infrastructure. Some 50 percent of Haitians (total population is 9 million) live in the countryside and 80 percent of those people live on less than a dollar a day, according to FAO. One month after the earthquake, the situation continues to fluctuate. People are still moving between sites or leaving town; the government is still working on its policies with regards to the camp and shelter situation. In all likelihood, due to the upcoming rainy season, some of the camps will shift location or close entirely.

2. What assessments (including joint assessments) have been carried out using what methodologies?

Emergency relief needs have been identified with communities whilst gathering population data in the spontaneous settlements. This includes information for WASH, Shelter / NFI/s and Health. CARE is participating in the ongoing integrated assessments. Close coordination exists between the different sectoral areas and information freely shared.

3. Have your assessments enabled you to disaggregate beneficiaries by gender, age and ability; if so what are the findings?

During registration teams have collected data by gender and age and family status. Input and analysis of this data is ongoing.

4. Have your assessments identified any other specific vulnerable groups, and if so what are they?

The disaster situation increases the vulnerability of women and children to Sexual and Gender Based Violence (SGBV) therefore CARE interventions will incorporate best practice in order to mitigate against this.

5. What is your agency’s experience in the disaster area?

CARE has been operational in Haiti since 1954. Prior to the earthquake CARE Haiti employed over 133 staff in country, most of whom were involved in the emergency response to the floods caused by Hurricanes Hanna and Ike in September 2008. The Country Office has a comprehensive Emergency Preparedness Plan in place and is prepared with allocated staff roles and responsibilities to scale up to large emergency responses. A team of 20 emergency staff have been deployed to Haiti to support the country office. This includes the CARE International (London-based) Senior Shelter Specialist and the Senior Emergency Programme Officer Prior to the earthquake, CARE’s programme reflected an integrated approach, with projects in HIV/AIDS, reproductive health, maternal and child health, education, food security, and water and sanitation. CARE works closely with local NGOs, private companies, community organizations and the Haitian government to build local capacity and achieve programme objectives.

6. Assumptions: what external conditions are necessary for your response to be successful?

It is assumed that no further natural or political disaster occurs which would hamper our efforts and that communities continue to be receptive to our engagement.

7. Where are you working? Please provide a map with the locations of your projects identified.

For multi country responses provide a separate Sections 2, 3, 4 for each country

| Section 2: Overall Member Agency Programme |  |
| --- | --- |
| Country | Haiti |
| Location of country bases | Léogâne, Carrefour, and/or Pétionville, |

| B Planned Response |  |  |  |
| --- | --- | --- | --- |
| 1. GOAL – Overall Member Agency Programme |  |  |  |
| Earthquake affected households will have improved access to basic amenities |  |  |  |
| 2. What is the share to be funded by DEC appeal funds as a financial proportion? |  |  |  |
| Budget Category | Overall Programme £s | DEC Appeal Funds £s | DEC as a % age of Overall |
| A: Supplies/Materials |  | 878,247 |  |
| B: Logistics |  | 270,584 |  |
| C: Personnel |  | 246,158 |  |
| D: Personnel Support |  | 57,879 |  |
| E: Capital |  | 10,779 |  |
| F: Contingency |  | - |  |
| G: Management Support 7% |  | 102,455 |  |
| TOTALS | 7,792,208 | 1,566,103 | 20% |

| C First 4 Weeks – Update – for the DEC website |  |  |  |
| --- | --- | --- | --- |
| 1. What has your agency has delivered in the first 4 weeks since the DEC appeal? |  |  |  |
| Sector 1 | What has been delivered? (Volumes not financial values) | No. of Beneficiary Households | Mark the sectors where there is substantial overlap in Beneficiary Households |
| NFI | Mattresses Kitchen sets | 16,743 | X |
| WASH | Water bladders Latrines Daily water trucks | 6340 | X |
| Health | Safe delivery kits Newborn kits Hygeine kits | 919 individuals | X |
| Food | Food distributions as partner of WFP | 26202 | X |
| Shelter | Tents Temporary shelter kits | 1077 | X |
| 1 Sectors: health; water/sanitation; food; shelter; NFI; livelihoods; education and training; policy & protection; capacity building; other |  |  |  |
| 2. How many Beneficiary Households has your programme reached in the first 4 weeks of your response counting every household only once? |  |  |  |
| As of February 17th, the CARE response has reached more than 228,000 beneficiaries. Our Emergency Response Strategy focuses on Carrefour, Léogâne and Pétionville hence some degree of overlap will be expected across the sectoral interventions. |  |  |  |

| Section 3: DEC Appeal Funded Programme |  |
| --- | --- |
| Country | Haiti |

| D Programme Proposal |  |  |  |
| --- | --- | --- | --- |
| 1. Programme Title |  |  |  |
| Humanitarian Assistance to Earthquake Affected Households in Haiti |  |  |  |
| 2. Purpose [SMART] (Add rows as necessary) |  | Timeline: when do you expect each of these to be achieved? |  |
|  |  | 3 months | 6 months |
| a) Earthquake affected households have access to temporary shelter and essential non food items |  |  | X |
| b) |  |  |  |
| c) |  |  |  |
| 3. For details of projects to be implemented complete Table 1 at the end of this form. This seeks details of projects by sector and beneficiary household numbers. |  |  |  |
| 4. Will your agency be working through partners and/or sister agencies? If yes, name them |  |  |  |
| Location of Programme | Name of Partner |  |  |
| 1. N/A |  |  |  |
| 2. |  |  |  |
| 3. |  |  |  |
| 4. |  |  |  |
| 5. |  |  |  |
| 5. Any other issues? |  |  |  |

Section 5: DEC Appeal Funded Programme

For multi country responses provide a regional perspective

E Humanitarian Principles and Standards

1. Does your agency see any major constraints in meeting any element of the Code of Conduct or Sphere Standards? Consider whether issues noted here constitute risks which warrant inclusion in the Appeal Risk Register

Given the urban setting the Shelter Cluster whilst agreeing to strive to meet Sphere standards recognise that this may not be practical / achievable in this context due to the high density population of areas affected and the space available. The Shelter Cluster will work on producing guidelines for transitional shelter support.

2. How will you engage with beneficiaries in the planning and implementation of your programme?

During the first phase of the earthquake response programme, CARE will implement blanket distributions in affected areas. Through the coordination mechanisms in country, specific area locations will be allocated to avoid gaps or duplication and in order to ensure maximum coverage. Community volunteers have been engaged in finalising the beneficiary lists and also in distributing the relief items. Each area has a beneficiary representatives who maintain records for the beneficiaries and who are assigned to represent the communities with NGO’s.

3. Give details of beneficiary types if possible. (e.g. local community, IDPs, refugees)

The beneficiaries will include households displaced by the earthquake.

F Coordination

1. How is your agency linked at operational level to the relevant international and national bodies?

CARE has strong working relationships with UN agencies and humanitarian groups on the ground, as well as key government agencies. CARE staff are currently participating in the regular sectoral and general meetings to plan joint assessments and emergency response actions. CARE has made shelter one of the key priorities (along with WASH and Economic Recovery) of the response and has been a proactive member in the Shelter Cluster, deploying key staff into the Cluster mechanism as Technical Advisor and Information Manager.

2. Have you identified any gaps in coordination? If so what plans have you to help fill these?

With such a scale of disaster the information management requirements are significant. In order to address this CARE has seconded a staff member as Information Manager within the shelter Cluster.

| G Learning Lessons |  |
| --- | --- |
| 1. What relevant lessons have been learnt from previous disasters? | 2. How have these lessons been incorporated into programme design? |
| Funding for the longer term is essential for an effective shelter recovery programme | CARE is planning an overall five year response strategy and has been actively seeking funding to cover this time period since the earthquake |
| Considering the different recurrent crisis in Haiti, emergency preparedness is critical | CARE will hold an After Action Review in a few months to learn the lessons from this emergency response in order to include them in its Emergency Preparedness Plan |

| Disaster Response Phase 1 If you have more than 3 Purposes copy and paste the Programme Deliverables table | Section 3: Use of DEC Appeal Funds (only) Item D: Programme Proposal Question D3: Projects and Deliverables | Table 1 |  |
| --- | --- | --- | --- |
|  |  | Country | Haiti |

| PROGRAMME DELIVERABLES |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Purpose: (copy and paste from D2 a, b, c etc) | To improve access to shelter and essential non food items for earthquake affected households |  | Location (at district level): | Léogâne, Carrefour and/or Pétionville | No. of Beneficiary Households |  |  |
| Planned Outputs | Sector [¦Using code below only] | Indicator | Key Activities |  | Individuals/ HHs I/HH | Planned | Mark the sectors with substantial overlap in Beneficiary Households |
| Families have improved security and protection through the provision of temporary shelter materials | Shelter | - Families receive appropriate temporary shelter support - Households receive reconstruction toolkits | - 8500 tarpaulins distributed along with ropes - Distribution of 2000 ridge tents - Distribution of 2000 reconstruction tool kits |  | 21,250 / 4,250 10,000 / 2,000 5,000 / 1,000 |  | X |
| Improved access to essential non food items | NFI | - # families receive non food items | - Distribution of 3000 kitchen sets - Distribution of 10,000 mattresses |  | 17,500 / 3,500 50,000 / 10,000 |  | X |
| 1 Sectors: health; water/sanitation; food; shelter; NFI; livelihoods; education and training; policy & protection; capacity building; other |  |  |  |  |  |  |  |

| What is the net number of beneficiary households i.e. counting every household only once? | 10,000 |
| --- | --- |
| What is your assumption about the number of members in each household? | Average family size of 5 (1HH) |