SECTION  III

FORMAT FOR HUMANITARIAN PROJECT PROPOSALS

The following format applies to all humanitarian project proposals, though not all questions will be necessarily relevant to all types of projects.

Project proposals should contain the following sections:

*	a basic data sheet (1 page)

*	a logical framework (2 pages)

*	the project rationale (3 pages)

*	project management arrangements (2 pages)

*	analysis of risks and undertakings (1 page)

*	budget (2 pages)

*	annexes, as appropriate.

(NB: page guides are a maximum. Start each section on a separate page)

Basic data sheet

This will be at the front of the project document giving the following ordered information:

- Name of agency - and name, designation, address, telephone, fax and email (if available) of the contact point in the agency dealing with the proposal;

- Name of project - and location;

- Project cost - total project cost and duration; contribution sought from DFID, broken by year if appropriate;

- Grant payment details - Agency's nominated bank account number and name, bank name, address and sort code, into which DFID is requested to make payments;

- Problem addressed - a sentence that identifies the issue or problem that is tackled by the project and the people affected.  If a rapid onset disaster, indicate type, location, intensity, date, and duration;

- Project summary - an initial sentence that identifies the purpose and key outputs of the project, followed by a brief paragraph outlining essential details.

Logical framework

"Logframes" are recommended for all projects and are an essential requirement for projects greater than £100,000.  See Annex A for recommended format.  For smaller projects, if a logframe is not used, a narrative statement including a clearly stated purpose, outputs, activities, indicators and risks must be provided.

Project Rationale

The background to the project, and the approach adopted should be explained.  The following points are not an exhaustive list and will not be applicable in all cases but they illustrate considerations in the justification of the project rationale:

Agency background

- How did the agency come to be involved in this issue or situation?

- What experience does the organisation have of working on this issue or in the country/province/region?

- Is the organisation a signatory to the "Code of Conduct for the   International Red Cross and Red Crescent Movement and NGOs in Disaster Relief"? Does it plan to implement the "Code of Best Practice in the Recruitment and Management of Aid Personnel"? Is it involved in any other quality and/or standards initiative?

Project approach

- What problem(s) does the project address?  What specific assessments have been made and by whom?

- How do the proposed outputs and activities help solve these problems? How does the project fit in with overall aims or policies of the system (agencies collectively, government where applicable) responding to the problems? What would happen without the project?

- What are the essential features of the project's operating environment including the problems and opportunities provided by the social, political, institutional and economic context, as relevant? Background analyses where necessary can be presented in annex(es).

- Were any alternative approaches considered to the ones proposed?  If so why were they rejected?

- What are the expected benefits?

- Who are the main beneficiaries, and how will they benefit? Are there other stakeholders who may gain or lose as a result of the project? How will stakeholder participation be handled?

- Are the needs of particularly vulnerable or marginalised groups addressed? How?

- Will the beneficiaries of the project participate in it's development and delivery?  How?

- Will men and women benefit from the project?  How will any gender inequalities be handled?

- Are there specific issues in relation to conflict? How will they be handled?

- Do indigenous systems or services already exist that would normally be expected to address the needs outlined in this project?  Does this project strengthen and underpin these or could it undermine them?

- Are any of the structures or services to be established by this project intended to be sustainable?  If so how will sustainability be attained?

- What lessons have been learnt from previous experience in this area or type of project?

Management arrangements

Give a brief description of project implementation and monitoring arrangements to ensure the cost-effective and efficient attainment of the outputs identified in the logical framework, including:

- project implementation and supervision arrangements; indicate in-country capacity of agency including length of presence and staff; indicate names, track record and expertise of any implementing partners;

- extent of agency participation in any national/local co-ordination arrangements eg by national/local government authorities or United Nations system; specify any operating agreements with them; indicate if proposal has followed official request for help and (where appropriate) the project is within the framework of a DHA Inter-Agency Appeal;

- other agencies operational in the area, and what goods/services they are supplying or intend to supply;

- indicate the overall timeframe for the project, workplan, and timetable for specific activities;

- reliability of the costing of project inputs; arrangements for procuring and transporting project inputs, to ensure local appropriateness and acceptability, as well as security and value-for-money under the circumstances;

- systems for project monitoring (including financial tracking and accounting audit), quality control (including lesson learning, and corrections), and impact assessment; methods for data collection and monitoring specifying dates for any proposed visits by agency staff; responsibility for reporting.

Analysis of risks and undertakings

Key assumptions with regard to external factors that are outside project control but nevertheless necessary to the achievement of project outputs and purpose should be stated in the logframe. Many of the projects funded from emergency aid funds are recognised to operate under high levels of risk. In this section, indicate:

- the risk assessment that has been carried out to identify the main potential causes of failure, their likelihood of occurrence, and the seriousness of consequences that would be suffered;

- options considered and the steps taken in project design and implementation to address, and minimise or mitigate the potential risks;

- measures planned or taken to minimise the risk to agency personnel and assets, in areas of actual or potential violent conflict;

- any undertakings or agreements made with partners which impact on project implementation; how observance of undertakings will be monitored; the implications of non-compliance.

Project budget

See Annex B for recommended format.

Lists of supplies and equipment

Specify details including a brief technical description and information on sourcing; costs need not be repeated if already included in the footnotes to the project budget (Annex B).