## Instructions
DEC Generic Appeal Risk Register
Risk Register Instructions
Member Agencies are required to tailor this register to reflect the circumstances of the disaster and their disaster response. The tailored register must be submitted to the Secretariat with the Phase 1 Plan.
Risk - | To help the speedy production of an appeal risk register by Member Agencies this generic register has been pre-populated with various risks to a successful DEC disaster response programme. Add other relevant risks below the pre-populated risks.
Risk Category - | Each risk has been categorised using: financial (Fin), fraud (Frd), operational (Op), reputational (Rep), security and safety (Sec), legal and regulatory (Leg), other (Oth). Please use these categories for any risks you add.
Impact - | Select the level of impact the risk will have if it occurs from High, Medium or Low, using the drop down list
Likelihood - | Select the likelihood of the risk actually occuring from High, Medium or Low, using the drop down list
Score - | Based on the selections made in the Impact and Likelihood columns a numerical score will be calculated automatically
Gross Risk Ranking - | Based on the score the risk will be given a gross ranking of either High, Medium or Low automatically
Current Controls - | For all risks other than those ranked 'low low' 'low medium' 'medium low' describe the controls and mechanisms currently in place in your disaster response which contribute to reducing the risk
Strength of Current Controls - | For the risks with current control details completed select the strength of current controls designed to contribute to reducing the risk (impact and/or likelihood) from Weak, Medium or Strong, using the drop down list
Score - | Based on the selections made in the Impact, Likelihood and Strength of Current Controls areas, a numerical score will be calculated automatically
Net Risk Ranking - | Based on the score the risk will be given a net risk ranking of either High, Medium or Low automatically
Planned Controls - | For those risks with a ranking of high or medium describe the controls and mechanisms you plan to put in place which will contribute to further reducing the risk
Risk Owner - | In this cell the person with responsibility for overseeing the risk should be noted (or the DEC contact for the appeal risk register if preferred)

## Risk Register
[19 empty] | Medium | Medium
DEC Generic Appeal Risk Register | [8 empty] | CARE International UK | [9 empty] | Low | Strong
[9 empty] | Haiti Earthquake Appeal | [9 empty] | High | Weak
DEC Ref | Risk | Risk Category | Impact | Likelihood | Impact Score | Likelihood Score | Score | Gross Risk Ranking | Current Controls | Strength of Current Controls | Score | Net Risk Ranking | Planned Controls | Risk Owner | I | L | A | T
1 | Hasty programming or intervention leading to poor value for money | Fin,Op | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
2 | Beneficiaries are inaccessible | Op | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
3 | Vulnerable groups or individuals are overlooked | Op | High | Low | 3 | 1 | 3 | Medium | The immediate relief phase is working towards blanket coverage in the areas of operation | Strong | 3 | Low |  |  | 3 | 1 | 1 | 3
4 | Insufficient agency capacity in country | Op | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
5 | Insufficient agency skills in country | Op | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
6 | Poor partner choice | Op | Low | Low | 1 | 1 | 1 | Low |  |  | 0 |  |  |  | 1 | 1 | 0 | 0
7 | Insufficient local skills | Op | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
8 | Engagement with partners with low capacity | Op | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
9 | Engagement with partners with inadequate financial and/or governance arrangements | Op | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0 |  |  | Financial/Resource
10 | Unrealistic programming – timing | Op | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
11 | Unrealistic programming – deliverables | Op | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
12 | Unrealistic programming – benefits | Op | Low | Low | 1 | 1 | 1 | Low |  |  | 0 |  |  |  | 1 | 1 | 0 | 0
13 | Programme planning does not address disaster risk reduction | Op, Rep | High | Low | 3 | 1 | 3 | Medium | DRR is not highly prioritised during the relief phase but the rehab and recovery phase will integrate DRR best practise | Strong | 3 | Low |  |  | 3 | 1 | 1 | 3
14 | Agencies do not change practices in light of lessons learnt | Op, Rep | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
15 | Agency staff are not aware of or skilled in agreed codes of conduct and standards | Rep | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
16 | Lack of rigour in staff recruitment processes | Rep | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
17 | Knowledge of local protocols/regulations is inadequate | Leg | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
18 | Disaster responses overlap | Oth | High | Low | 3 | 1 | 3 | Medium | Regular attendance of coordination meetings | Strong | 3 | Low |  |  | 3 | 1 | 1 | 3
19 | Gaps in disaster response – types of programme | Oth | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
20 | Gaps in disaster response – geographical | Oth | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
21 | Success is not clearly defined | Oth | Low | Low | 1 | 1 | 1 | Low |  |  | 0 |  |  |  | 1 | 1 | 0 | 0
22 | Expectations are not clearly defined | Oth | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
23 | Appeal funds are used for purposes outside the terms of the restricted funds | Fin | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
24 | Sub standard inputs are used | Fin | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
25 | Overfunding of partners resulting in poor value for money | Fin | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
26 | Unforeseen tax demands | Fin | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0 | Low | Strong | Internal Business Development
27 | Organisational stretch at local agency or partner level resulting in poor resource management | Fin, Op | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0 |  |  | People
28 | Fraud at agency level (theft, corruption, procurement) | Frd | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
29 | Fraud at partner level (theft, corruption, procurement) | Frd | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
30 | Poor community participation | Op | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
31 | Sabotage through inadequate or inappropriate consultation | Op | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
32 | Aid provided is not the most appropriate | Op | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
33 | Insufficient programme inputs, eg materials, equipment, food | Op | High | Low | 3 | 1 | 3 | Medium | Target s are based on our capacities and resources | Strong | 3 | Low |  |  | 3 | 1 | 1 | 3
34 | Loss of staff due to competition | Op | High | Low | 3 | 1 | 3 | Medium | CARE Haiti HR staff are attending regular coordination meetings with other HR representatives in PaP. The staff and salary review is underway | Strong | 3 | Low |  |  | 3 | 1 | 1 | 3
35 | Input/resources are insufficient to meet agreed standards | Op, Rep | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
36 | Lesson learning is not invested in | Op, Rep | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
37 | Aid provided is not in accordance with beneficiary wishes | Op, Rep | Medium | Low | 2 | 1 | 2 | Low | CARE is carrying out full needs assessments | Strong | 2 | Low |  |  | 2 | 1 | 1 | 2
38 | Excessive amounts of funds used for administration and/or management (>50% should be on category A) | Rep | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
39 | Disaster response too slow | Rep | High | Medium | 3 | 2 | 6 | High | Maximixing rapid blanket coverage in the relief phase as agreed as part of the Shelter Cluster recommendation | Strong | 6 | Low |  |  | 3 | 2 | 1 | 6
40 | Agreed codes of conduct are not upheld | Rep | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
41 | Standards are not met | Rep | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
42 | Agency aid is used for political gain | Rep | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
43 | Lack of inter-agency coordination | Rep | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
44 | Adherence to agreed codes of conduct/standards not measured or valued | Rep | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0 | High | Weak | Customer/Stakeholder
45 | Hostile government or political instability curbs or terminates disaster response in a particular area or country | Sec | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
46 | Personnel fall seriously ill, or are hurt, kidnapped or killed in the course of their work | Sec | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
47 | Government protocols not observed | Leg | Low | Low | 1 | 1 | 1 | Low |  |  | 0 |  |  |  | 1 | 1 | 0 | 0
48 | Funds used to support terrorism | Leg | Low | Low | 1 | 1 | 1 | Low |  |  | 0 |  |  |  | 1 | 1 | 0 | 0
49 | Restriction on operations due to failure to comply with local tax legislation. | Leg | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
50 | Government bureaucracy has a negative impact on disaster response | Oth | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
51 | Irresponsible exiting | Rep | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
52 | Impact analysis is not undertaken | Oth | Medium | Low | 2 | 1 | 2 | Low |  |  | 0 |  |  |  | 2 | 1 | 0 | 0
53 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
54 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
55 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
56 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
57 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
58 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
59 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
60 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
61 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
62 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
63 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
64 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
65 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
66 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
67 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
68 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
69 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
70 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
71 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
72 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
73 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
74 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
75 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
76 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
77 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
78 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
79 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
80 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
81 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
82 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
83 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
84 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
85 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
86 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
87 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
88 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
89 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
90 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
91 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
92 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
93 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
94 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
95 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
96 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
97 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
98 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
100 |  |  |  |  | 0 | 0 | 0 |  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0
2026-07-29 09:49
'file:///tmp/in/input.xls'#$Risk Register