Country Office Emergency Response Human Resources Management Systems Checklist

| DOCUMENTS/ SYSTEMS | COMMENTS | COUNTRY OFFICE NOTES |
| --- | --- | --- |
| International staff recruitment |  |  |
| CO staffing matrix | See template |  |
| Develop a staffing plan | Include needs to relocate existing national and international staff to the crisis location, bringing in new international staff for the emergency, bringing in new international staff to cover ongoing programmes and hiring new national staff for the emergency or ongoing programmes. Ensure sufficient staffing for programme support as well as programme positions. |  |
| General CO organigram and emergency programme organigram | Update staffing structure as required and circulate – particularly back to the lead member |  |
| TORs | See generic CERT TORs that can be utilised or modified as necessary. Ensure all existing CO staff have clearly defined roles for the emergency and incoming staff have TORs. Ensure reporting lines are clear. Review and update TORs as necessary. |  |
| Personnel budgeting | Ensure proposal writers and finance staff include all necessary personnel related expenses within budgets. Include salaries, accommodation, international and national travel, per diems, visas, medical, insurances, personal items such as mosquito nets, tents & sleeping gear and psycho-social support costs such as briefings and debriefing (this may require actual psychologist and welfare staff deployments). |  |
| Requisition form | See template. Upon selection of staff a requisition should be sent to the employing national member to be completed for the CO finance dpt. |  |
| Travel/Invitation letter | To be produced either by the CO or employer for staff entrance to the country. |  |
| Visa processing | Visa extensions may be required. |  |
| Work or travel permits | These may be required in some countries for staff travelling to crisis areas or for staff being employed on long contracts. |  |
| Pre-departure |  |  |
| Pre-departure checklist | See template to be modified for each emergency. Send to all employing national members for circulation to selected staff. |  |
| Visitors briefing pack | See generic kit list for modification. CO to develop and send to all employers to give to staff prior to travel. |  |
| On-arrival in country |  |  |
| In-country orientation, information kit and security briefing | See template of orientation topics. Information kit to be developed by the CO. This usually contains information that is regularly changing with the crisis and thus cannot be contained in the pre-departure kit. |  |
| Entry interview | See template. To be completed by all staff on arrival as part of the CO orientation/briefing |  |
| CO staff master chart - register of arrival and departure travel ticket dates, contract start and end dates, visa validity dates, record of embassy registrations, insurance | See template. These items may be captured in the one CO staff tracking spreadsheet by utilising information from the entry interview form. |  |
| CO Record of Emergency Data form (RED) | Template available in the CET |  |
| Personnel files with copies of – TORs, requisitions forms, copies of passports, travel tickets and CO entry interview form |  |  |
| Asset register | All equipment going to the field must be registered and signed in upon return |  |
| Staff contacts sheet | To be produced by the CO and provided as part of staff orientation and carried by all staff at all times |  |
| CARE ID cards | Employers should provide these to staff prior to travel however COs should be prepared to make them up if staff arrive without them |  |
| Leave application and leave tracking forms | As in use in CO |  |
| Duty travel form | As in use in CO |  |
| Staff welfare |  |  |
| Psycho-social support and staff welfare policy/program | See HR chapter in the CET |  |
| Country departure |  |  |
| Exit interview | To be completed for all staff departing the CO. |  |
| Appraisal | To be completed by line managers with each employee prior to departure and send to the employing national member. |  |
| Separation and employer specific departure/ termination requirements |  |  |
| In-country remuneration and benefits |  |  |
| Salary structure – multiple member rates |  |  |
| R & R policy |  |  |
| Per diem policy |  |  |
| Accommodation |  |  |
| National staff |  |  |