## Writing Advocacy Strategies(adapted from Oxfam international) – Format and Guidelines

An advocacy strategy is essentially a plan of work that brings together actions including lobbying, media and popular mobilisation, designed to achieve changes in policy and practice.

The purpose of developing an advocacy strategy is to ensure that our plans are well thought through, commonly understood and adequately resourced before we begin advocacy work on a specific issue.

Developing an advocacy strategy involves addressing the following basic questions:

- What is the problem?

- What is the solution?

- What changes are necessary to get us from one to the other?

- What are the most effective ways of making that change happen ?

Standard Advocacy Strategy Format

Title: Date: Duration of strategy: Status: - Problem - Overall Aim - Specific Objectives - Rationale for CARE engagement - Targets - Power Analysis - Allies - Messages - Tools/Actions - Research - Policy Development - Lobbying - Media - Popular Mobilisation - Funding of others - Opportunities and Events 10. Human and Financial Resources 11. Risks - Monitoring, Evaluation, Planning and Learning

Guidelines for Content

Give the length of time the strategy covers, and the status of the document (ie draft, signed-off, CARE-Sudan or CARE International etc.). Our strategies should not be too long.  Additional information should be attached as an Annex.

- What is the problem?

Give a brief (two paragraph) description of the problem we want to solve, always explaining how it affects men and women differently, and also considering other relevant factors (eg class, race, religious denomination), why there is a problem, and what is currently preventing change.

2.  Overall Aim

Describing the solution to the problem will set out our overall aim.  One to two sentences only.

3.  Specific Objectives

Set out the specific changes we need to achieve as a contribution to realising the overall aim. You should have no more than four of these objectives and consider at least one addresses the issue of gender justice. Try to keep objectives SMART (Specific, Measurable, Achievable, Realistic, Timebound).

- Rationale for CARE engagement

State briefly the reasons for CARE’s engagement with this issue, and our added value.

5.  Targets – who makes the key decisions?

Who are the actors who have the power to solve the problem or achieve our objectives, and whom we therefore want to influence? These may be government departments, international institutions or private companies. List the key people within these institutions.

6. Power Analysis – what will influence the decision-makers? (link to specific tool on power analysis)

# Undertaking a power analysis helps you to target the right actions, to the right people, at the right time, in order to secure change.

Summarise power analysis in three paragraphs or so, but provide a more detailed power analysis as an Annex, as this is a critical part of the strategy - it determines basic viability of strategy and informs detailed action-planning.

7.  Allies

The power analysis will identify some broad ‘allies’, eg governments that support our aim at the UN. In this section, we should detail other potential allies including those we are already in formal coalition with, those we can collaborate on an ad hoc basis, or those we can stimulate into action. These may include other civil society organisations such as development/environment/human rights NGOs, community-based organisations, journalists, academics, think-tanks or trade unions. (link to specific tool on working with allies)

- Key Messages

Define the three (at most, four) critical messages we wish to convey to our targets. These should be repeated in all of our communications, written and oral, though there may be some messages that we only want to convey to decision-makers in private. One way to draft your key messages is to imagine you have a minute or so on the radio and want to get three points across. At least one should be a call to act. Look for win-win solutions, where the decision-maker also stands to gain from your proposals.

9.  Tools/actions

There are many different actions we can take to influence our target. We need to decide which would be the best tactic or combination of tactics to employ at any one time to achieve maximum influence. This section is the heart of the strategy, and needs to be fully developed in our plans. Some areas may require specific strategies eg media – for which there is also a standard format – or lobbying. These should be an integral part of the broader strategy. Bear in mind links to programme, which is our source of information and legitimacy. List our actions under these headings:

- Research (from human interest material and case studies to major reports)

- Policy Development (agreeing where we stand, in general and detail, and rationale)

- Lobbying (plan for face-to-face contact with range of targets, letters….)

- Media (targets, angles, products, paper launches, use of celebrities, etc)

- Popular Mobilisation (email/postcard actions, stunts, etc)

- Funding of others (grants third parties in support of aims e.g. human rights groups)

10.  Opportunities and Events

Identify the main political processes, key meetings, decision-making moments, or events that can affect, or be used to promote our objectives. It may be useful to do a calendar. The big opportunities could be those we create ourselves - sometimes there may not be high profile external events.

11. Human and Financial Resources

The commonest failing of advocacy strategies is willing the end without willing the means.

Name the CI affiliates who are needed to deliver the strategy, and all of the individuals involved (including the proportion of their time required). This is not just the people working full time on this issue, it should include managers, media people and programme staff. It should cover HQ, Regional Management Units and country-based staff.

A project manager must be identified, and given responsibility for ensuring the delivery of the whole strategy, ensuring that those responsible for tasks carry them out by the agreed time.

Where necessary, give a budget for supporting advocacy activities, eg research, production of materials, extra posts, costs of facilitating field staff and partners to attend national and international lobbying meetings etc. Specify what funds should be available to fund third parties such as other NGOs.

12.  Risks

Think about what might stop us achieving our objectives, particularly in politically sensitive work, and what can be done to reduce these risks. Consider whether our advocacy might bring any risks to CARE’s programme, staff, allies or partners.

Observe the checks and balances in place to minimise risk, namely sign-off procedures. They should ensure accountability checks on security implications, reputation risk, and consistency with Charity Law.

13.  Monitoring, Evaluation, Planning and Learning

A strategy is dynamic, and the most effective strategies are those where we plan-and-act on an ongoing basis. We need to monitor actions, evaluate their success, and learn from evaluations (this should not be a laborious exercise), and continue to plan-and-act. The project manager should lead this process in regular meetings or telecons by asking the right questions. You might want to plan a mid-term review or stock-take following the role out of the strategy, and a final review. For major pieces of advocacy work that represent a significant investment of resources, you may want to consider commissioning an independent external evaluation at the end of project.