CARE International Strategic Direction #1: Emergency Preparedness & Response

Part 1. Detailed Performance Metrics Report: FY08 First 6 Months (July – December, 2007)

Type 2 emergencies included in by this report

- Pakistan cyclone & floods (July 2007)

- India monsoon floods (July 2007)

- Bangladesh monsoon floods (July 2007)

- Nepal monsoon floods (August 2007)

- Peru earthquake (August, 2007)

- Uganda floods (September 2007)

- North Kivu (DR Congo) conflict (July 2007 onwards )

- Somalia escalation of fighting in Mogadishu & significant increase of number of IDPs (October, 2007)

- Bangladesh cyclone Sidr (November 2007)

Timeliness

| Indicator | FY08 Results Against Benchmark (%) | Remarks |
| --- | --- | --- |
| Decisions on rapid onset emergencies are made & communicated throughout CI within 24 hours. |  |  | 60 % met |
|  | 2012 Benchmark = 90% |  |  |
| Material emergency response interventions are launched within 48 hours after of the disaster. |  |  | 53 % met |
|  | 2012 Benchmark = 80% |  |  |
| Appropriate level of CARE ERF funds to start-up emergency responses are allocated within 48 hours. |  |  | 78% met |
|  | 2012 Benchmark = 90% |  |  |
| Additional international staffs are deployed (en-route) within 72 hours after staffing requests. |  |  | 90% met |
|  | 2012 Benchmark = 90% |  |  |
| Additional national staffs are redeployed (en-route) within 48 hours after staffing requests. |  |  | 90% met |
|  | 2012 Benchmark = 90% |  |  |
| Senior staff from lead member visit disaster site within appropriate timeframe. |  |  | 10% met |
|  | 2012 Benchmark = 90% |  |  |
| Statements about CARE’s response are issued throughout CI and to the media within 24 hours of the disaster event. |  |  | 40% met |
|  | 2012 Benchmark = 90% |  |  |

Quality & Accountability of Response

| Indicator | FY08 Results Against Benchmark (%) | Remarks |
| --- | --- | --- |
| Country, regional and CI member offices have emergency preparedness plans that have been reviewed/revised within the past 6 months & there is evidence of readiness and use. |  | No evidence yet collected of use of EPPs. |
|  | 2012 Benchmark = 90% |  |  |
| Emergency strategies are developed within one week of the disaster event and revised as necessary. |  |  | 75% met |
|  | 2012 Benchmark = 90% |  |  |
| Disaggregated population information is provided for CARE’s beneficiaries within 2 weeks. |  |  | 10% met |
|  | 2012 Benchmark = 90% |  |  |
| Monitoring and evaluation of CARE responses indicate minimum levels of appropriate and applicable humanitarian accountability standards are met or exceeded. |  |  | 33% met |
|  | 2012 Benchmark = 90% |  |  |

Competence in Core Sectors

| Indicator | FY08 Results Against Benchmark (%) | Remarks |
| --- | --- | --- |
| Significant interventions in at least one of the core sectors. |  |  | 50% met |
|  | 2012 Benchmark = 70% |  |  |
| Monitoring and evaluation of CARE responses indicate technical quality in core sectors exceed accepted standards. | No info yet… | AARs & evaluations scheduled during final six months of FY08 |
|  | 2012 Benchmark = 90% |  |  |

Emergency Revenue Trends - Funding

| Indicator | FY08 Results Against Benchmark (%) | Remarks |
| --- | --- | --- |
| 70% of disaster response funding targets have been met within 3 months. |  |  | 37% met |
|  | 2012 Benchmark = 90% |  |  |
| Average annual leverage of ERF allocations across CI. | No info yet… | Data system under development |
|  | 2012 Benchmark = 6 |  |  |
| Annual CI emergency total revenue. | No info yet… | Data system under development |
|  | 2012 Benchmark = see below |  |  |
| Annual percentage growth rate of CI emergency revenue. | No info yet |  | Data system under development |
|  | 2012 Benchmark = TBD based on verified FY06 baseline |  |  |

Emergency Revenue Trends - Emergency capacity

| Indicator | FY08 Results Against Benchmark (%) | Remarks |
| --- | --- | --- |
| Cost recovery on international staff deployed to emergency assignments. |  |  | 67% met |
|  | 2012 Benchmark = 80% |  |  |
| Percentage of CI members’ and CEG’s emergency unit costs covered by restricted funding sources. | No info yet… | Data system under development |
|  | 2012 Benchmark = 50% |  |  |