Accountability monitoring (Draft)

The term ‘accountability monitoring’ is used to mean the monitoring of our performance on accountability. It is essentially the demonstration of our compliance with the CARE HAF.

Accountability monitoring can help CARE to:

- Adopt a ‘Good Enough’ approach to implementing HAF during an emergency by adopting quick and simple approaches and building on this as the situation changes

- Check that the accountability systems that have been set up are working effectively

- Focus our monitoring on approach, processes, relationships and behaviours, quality of work, satisfaction as well as outputs and activities,

- Priortise listening to the views of disaster affected people to assess our impact and identify improvements

- Provide a feedback opportunity for staff, communities and other key stakeholders to comment on our response and how we are complying with our standards and benchmarks

Accountability monitoring contributes to CARE’s overall monitoring and evaluation activities. Aspects can be integrated into other project monitoring tools, or carried out as a specific activity e.g. a beneficiary satisfaction survey or FGD to solicit feedback and complaint from vulnerable groups in isolated communities as part of a formal complaints mechanism. Ideally, accountability should already be built into project proposals and their logical frameworks.

CARE’s HAF and Sphere can be used to help develop staff design monitoring tools for use with staff, partners, communities and local authorities. In developing these monitoring tools, take into consideration good practice such as a balance between quantitative and qualitative data etc (link M&E chapter).

Examples of monitoring tools and activities

- Checklist for use by senior managers across all units / teams

- Simple questionnaire to help research into staff awareness, understanding and views on accountability

- Focus group discussion tool to help explore  specific issues in depth with a particular group of staff

- Review tool to help a group of staff to discuss and assess current levels of accountability, and to identify improvements for their specific context

- Monitoring tool to help research into local communities' views of how accountable CARE and staff are in practice, and how useful they find the CARE's work.

Summary reports will help senior managers to understand the level of accountability achieved in different projects. Key issues should be reported to senior management on a regular basis so to bring to their attention the views, concerns, feedback and complaints of communities in a timely manner.

Accountability data (including complaints data) therefore needs to be incorporated into monitoring reporting, alongside monitoring of project progress. Including quantified data will help managers make their decisions.

Some example monitoring tools are provided in the table below.

CARE’s HAF and Sphere Standards are intentionally coherent with one another (e.g. Participation is one of Sphere’s 8 Common Standards).  At the same time CARE’s HAF (Benchmark 3 and Outcome 2) also ask us to systematically use and reach accepted quality standards such as Sphere in our core sectors.

Challenges of assessing compliance with Sphere

- There is plenty of anecdotal evidence that a large majority of the humanitarian community believe meeting the quantitative indicators is a primary objective of achieving ‘sphere compliance’ e.g. we are Sphere compliant because we have provided 15 liters of water per day. This is wrong and is a misuse of Sphere which can cause more harm than good! See “What is Sphere? And a Myth busting quiz” - Because of this Myth, where Sphere has been incorporated into project log frames, we have there tended to focus solely on the quantitative aspects of Sphere, rather than on common e.g. targeting criteria clearly defined and widely disseminated, or other quality aspects relating to technical sectors found in Sphere e.g. privacy, equity, appropriateness etc - Sphere compliance however is a lot more than this: it means application of Sphere principles, common standards and relevant technical standards. This can sum up to many indicators, but only a few can realistically be used. This requires selecting the most relevant to which we want to hold ourselves accountable, adapting indicators to the context as appropriate (based on analysis of the context) and complementing these indicators with others. - A participatory accountability review can help staff review a project through the lens of CARE HAF and Sphere

Annex - Examples

This document contains example questions as a starting point to help develop self assessment or review tools for use by/with staff to assess progress against the 8 accountability benchmarks of CARE’s HAF, such as a checklist, simple questionnaire, FGD, workshop review tool (to be completed)

Example of a Focus Group Discussion tool on Information Sharing, Participation and Food Security – developed by staff in order to solicit community views as part of a participatory accountability review (CARE Ghana). Staff used CARE HAF and Sphere Food Security Chapter to inform the tool.

Example from CARE Myanmar

CARE Myanmar biweekly accountability monitoring report

Example from WV of a Focus Group Discussion tool to analyse information sharing, participation and raising complaints with staff and communities HAP website

Oxfam GB’s staff toolkit includes Community Voting Notes for staff to use with communities. It is a simple means of voting that can be used to solicit feedback in a non-threatening and often fun way, and it can be used as a preliminary activity to stimulate focus group discussions or community meetings. These notes include a few example questions that could be used with this method to assess degrees of accountability. HAP website