## CfW Workplan template
CFW WORK PLAN TEMPLATE
ACTIVITIES | PERSON RESPONSIBLE | COORDINATION WITH | TIMELINE
|  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
CFW planning
Identify or help establish+A5 a community committee and liaise with local authorities
Develop a CFW operational plan including: logframe, risk matrix, HR plans, budget and work plan
Define roles and responsibilities (SOPs)
Develop ToRs and recruit staff
Establish a supervision and monitoring strategy
CFW project selection
Select projects in collaboration with communities and local authorities
Verify technical specifications for work to be undertaken
Assess environmental issues and include risk reduction measures
Set assistance agreements with communities
Establish MoU with local authorities and implementing partners
Beneficiary communication and accountability (BCA)
Develop a BCA plan
Design and set up a CRM
Financial service provider selection and contracting
Research potential service providers
Conduct a tendering process to select service providers
Contract and define ways of work
CFW preparation
Select CFW participants
Establish and agree on working procedures
Establish wages rates with communities
Plan and prepare for registration and identification
Register CFW beneficiaries
CFW distribution
Estimate CFW material needs and costs
Order necessary materials
Plan and carry out distributions
CFW encashment
Assess encashment capacity
Plan encashment and mobilize agents
Train staff and service providers
Carry out encashment
Close out encashment
M&E planning
Develop an M&E strategy
Set up a whistle-blowing system
Programme monitoring
Establish baselines
Monitor encashment
Monitor post-distribution
Market monitoring
Monitor traders
Monitor prices
Evaluation
Plan evaluation (including ToR elaboration)