## Project site observation
CFW - Project site observation form template |  | Date: |  | Location: |  | Name and signature:
1. GENERAL
1.2 Total number of beneficiaries:
1.3 Implementation period (from/to): |  |  | Delays: ¨ Y ¨ N ____ weeks
2. BENEFICIARY PRESENCE
2.1 Actual number of participants working at the time of the visit |  |  | Men ______ Women _____
2.2 Does the actual number of participants present match the planned number of participants? |  |  | Y | N | If no, why?
If no, what was the planned total?
2.3 Are there children working on the sites? |  |  | Y | N | If yes, why?
3. WORK AND OUTPUTS
3.1 Planned volume of work (precise unit) | 3.2 Actual volume of work achieved |  | 3.3 Planned workdays |  | 3.4 Actual workdays |  | Percentage achieved so far:
[7 empty] | Work | Workdays
3.5 Are activities being implemented according to the original and approved plan? | Y | If no, what is different and why?
N
3.6 Is the project site on schedule? (Field monitor can check with person in charge of works). |  |  | Y | N
If no, why? ¨ Weather ¨ Lack of NFIs/tools ¨ Lack of technical guidance ¨ Security ¨ Political reasons ¨ Other: specify ____________________________
If no, how many days is it delayed by?
3.7 Describe the quality of technical supervision . |  |  | ¨ Needs improvement |  | ¨ Satisfactory |  | ¨ Very good
3.8 Is there a CFW supervising team on the site? |  |  | Y | N | Comment:
3.9 If the project requires NFI/materials (such as cement/tools), are they available in time and in adequate quantities for the completion of the work? |  |  | Y | N | If yes, who provided them?
If no, what is the problem?
3.10 What are the constraints and difficulties for the achievment of the work? |  |  | Constraints:
Solutions:
4. RECORD
4.1 Is there a daily attendance sheet or payroll for CFW participants? |  |  | Y | N | Comment:
4.2 Who checks and certifies the daily records (measuring quality and quantity of work and number of participants)?
4.3 Are registers/payrolls properly maintained and updated? |  |  | Y | N | Comment:
4.4 How do you rate the record keeping for accuracy and reliability? |  |  | ¨ Needs improvement |  | ¨ Satisfactory |  | ¨ Very good
4.5 (supervisor): Do you face difficulties in accurately recording the presence of workers? |  |  | Y | N | Comments
4.6 (supervisor): Do you face difficulties supervising the work? |  |  | Y | N | Comments
5. BENEFICIARY WORKER INFORMATION. Conduct a focus group discussion with four or five CFW participants.
5.1 Do you face difficulties working in the project? |  |  | Y | N | Comment:
5.2 How does the project support individuals and the community? |  |  | Provide list of possible answers
5.3 Did you receive your payment on time? |  |  | Y | N | Comment:
5.4 Was the amount as expected? |  |  | Y | N | Comment:
5.5 Could you use it to buy what you needed? |  |  | Y | N | Comment:
5.6 How do you cope with childcare and other household responsibilities while working? |  |  |  |  | Comment:
5.7 Are there any security risks during the work? Are you satisfied with the working conditions? |  |  | Y | N | Comment:
5.8 Have you heard of any discontentment in the community because of the project? |  |  | Y | N | Comment:
5.9 Do you think that the type of work is suitable for men and women (socially acceptable)? |  |  | Y | N | Comment:
5.10 Could the project be improved? |  |  | Y | N | Comment:
6. FINDINGS AND RECOMMENDATIONS
6.1. Explain issues that require follow-up, actions you have taken and any additional recommendations you feel you need to make.